## PROJECT_LIST
id | name | active | color | region
VNPT 4G Phase 10 | VNPT 4G Phase 10 | TRUE | #1d4ed8 | Nationwide

## CONFIG
project_name | VNPT 4G Phase 10
client | VNPT Vietnam
start_date | 2025-09-01
end_date | 2026-12-31
region | Nationwide
pm | Nguyen Van An
weekly_target | 35
contract_value | USD 45M
vendor | Huawei
target_onair | 260 sites

## DATA
site_id | site_name | province | status | project | site_type | build_type | lat | lng | ms_TSS | ms_TSSR | ms_RFI | ms_BTS_MOS | ms_BTS_On_Air | ms_PAT | ms_PAC | ms_SSV | ms_MW_On_Air | ms_Power_On_Air | ms_TX_Readiness | ms_BTS_HI | ms_BTS_Integration | ms_Dismantle | ms_OSS_KPI | ms_FAC
VNPT-SW-0001 | Site 0001 An G | An Giang | Installation Complete | VNPT 4G Phase 10 | 5G | swap | 10.275 | 104.8232 | 2025-11-22 | 2025-12-23 | 2026-03-18 | [5 empty] | 2025-12-02
VNPT-SW-0002 | Site 0002 Tuyê | Tuyên Quang | PAT Complete | VNPT 4G Phase 10 | 4G+5G | swap | 21.4022 | 105.0799 | 2026-01-12 | 2026-03-30 | 2025-11-24 |  |  |  |  | 2026-02-11 | 2026-01-04 | 2026-01-25
VNPT-SW-0003 | Site 0003 Kon | Kon Tum | On Air Complete | VNPT 4G Phase 10 | 4G+5G | swap | 14.1627 | 107.5553 | 2025-10-27 | 2025-10-30 | 2026-02-07 | 2026-01-17 |  |  |  | 2026-01-20 | 2026-01-03 | 2025-10-29
VNPT-SW-0004 | Site 0004 Tuyê | Tuyên Quang | On Air Complete | VNPT 4G Phase 10 | 4G+5G | swap | 22.1847 | 105.3429 | 2026-03-06 | 2025-11-18 | 2025-11-12 | 2025-12-05 | 2026-03-01 |  |  |  | 2025-11-12 | 2026-02-13 |  | 2026-03-29
VNPT-SW-0005 | Site 0005 Bình | Bình Dương | PAT Complete | VNPT 4G Phase 10 | 4G | swap | 11.2803 | 106.3146 | 2026-02-01 | 2026-01-13 | 2025-12-20 | 2025-12-03 | 2025-11-01 |  |  |  | 2026-04-10
VNPT-SW-0006 | Site 0006 Bình | Bình Phước | PAT Complete | VNPT 4G Phase 10 | 5G | swap | 11.5242 | 106.4195 | 2026-01-22 | 2026-02-08 | [7 empty] | 2025-12-07 |  |  | 2025-10-24
VNPT-SW-0007 | Site 0007 Hà G | Hà Giang | On Air Complete | VNPT 4G Phase 10 | 4G+5G | swap | 23.2951 | 105.1499 | 2025-11-29 | 2026-02-06 | 2026-01-14 | 2026-03-24 | 2026-02-09 |  |  |  | 2025-11-20 | 2026-02-13 | 2025-10-31
VNPT-SW-0008 | Site 0008 Than | Thanh Hóa | PAT Complete | VNPT 4G Phase 10 | 4G+5G | swap | 19.4904 | 105.3969 | 2025-12-23 | 2026-03-28 | 2025-10-27 | 2026-02-20 | 2026-02-06 | 2025-11-21 |  |  | 2025-12-28 |  |  | 2025-12-17 | 2026-02-23
VNPT-SW-0009 | Site 0009 Hưng | Hưng Yên | PAT Complete | VNPT 4G Phase 10 | 4G | swap | 20.3663 | 106.0856 | 2025-12-29 | 2026-02-27 | 2026-01-01 | 2026-02-21 |  | 2025-11-12 |  |  | 2025-12-15 | 2025-11-19 |  | 2026-03-27
VNPT-SW-0010 | Site 0010 Lâm | Lâm Đồng | RFI Complete | VNPT 4G Phase 10 | 4G | swap | 11.3685 | 107.568 |  | 2025-11-16 | 2025-11-09 | [5 empty] | 2026-03-21
VNPT-SW-0011 | Site 0011 Hải | Hải Dương | RFI Complete | VNPT 4G Phase 10 | 5G | swap | 21.3985 | 106.7961 | 2026-02-15 | 2026-03-08 |  | 2025-11-22
VNPT-SW-0012 | Site 0012 Nam | Nam Định | Installation Complete | VNPT 4G Phase 10 | 4G | swap | 20.3424 | 105.8554 | 2026-02-16 |  | 2025-10-30 | 2025-12-23 | [6 empty] | 2026-03-28 |  | 2026-01-15
VNPT-SW-0013 | Site 0013 Hải | Hải Dương | PAT Complete | VNPT 4G Phase 10 | 5G | swap | 21.3039 | 106.3456 | 2025-11-12 | 2025-12-21 | 2026-01-22 | [5 empty] | 2026-03-31 |  | 2026-02-06 | 2025-11-18
VNPT-SW-0014 | Site 0014 Khán | Khánh Hòa | RFI Complete | VNPT 4G Phase 10 | 5G | swap | 12.6245 | 109.2824 | 2026-02-06 | 2026-03-14 | 2026-04-01 | [6 empty] | 2025-12-14
VNPT-SW-0015 | Site 0015 Kiên | Kiên Giang | PAT Complete | VNPT 4G Phase 10 | 5G | swap | 9.8311 | 104.1276 | 2026-02-03 | 2026-02-02 | 2025-11-09 | 2026-03-30 |  |  |  |  | 2026-01-20 | 2025-12-01 | 2025-11-14 |  | 2025-11-24
VNPT-SW-0016 | Site 0016 Đồng | Đồng Tháp | Installation Complete | VNPT 4G Phase 10 | 4G | swap | 10.7198 | 105.4003 | 2025-12-27 | 2026-01-25 | 2026-02-20 |  | 2026-01-27 |  |  |  | 2026-01-03
VNPT-SW-0017 | Site 0017 Lâm | Lâm Đồng | On Air Complete | VNPT 4G Phase 10 | 5G | swap | 11.4697 | 107.5848 | 2025-10-30 | 2026-03-18 |  | 2026-03-30 | [6 empty] | 2026-02-19 | 2025-12-10
VNPT-SW-0018 | Site 0018 Ninh | Ninh Bình | On Air Complete | VNPT 4G Phase 10 | 4G | swap | 20.4927 | 106.2604 |  | 2026-02-13 | 2025-11-29 | [5 empty] | 2025-11-19 | 2026-03-10 | 2025-12-13
VNPT-SW-0019 | Site 0019 Vĩnh | Vĩnh Phúc | On Air Complete | VNPT 4G Phase 10 | 4G+5G | swap | 21.1501 | 105.8518 | 2026-01-30 | 2025-11-28 | 2026-02-08 | 2025-11-23 |  |  |  | 2025-12-27 | 2026-03-22 |  | 2026-01-15 | 2026-03-03 | 2026-03-02
VNPT-SW-0020 | Site 0020 Hồ C | Hồ Chí Minh | PAT Complete | VNPT 4G Phase 10 | 4G | swap | 11.0567 | 106.9656 | 2026-04-09 |  | 2026-01-01 |  | 2025-12-07 |  |  | 2026-01-14 |  |  | 2025-11-22
VNPT-SW-0021 | Site 0021 Đồng | Đồng Tháp | On Air Complete | VNPT 4G Phase 10 | 4G+5G | swap | 10.5919 | 105.763 | 2025-12-22 | 2025-12-13 | 2026-02-03 | 2025-12-24 |  |  |  | 2026-01-11 | 2026-02-15 | 2026-01-14 |  | 2026-03-21
VNPT-SW-0022 | Site 0022 Than | Thanh Hóa | Installation Complete | VNPT 4G Phase 10 | 4G | swap | 19.9213 | 105.5385 | 2026-03-12 | 2026-02-14 | 2026-02-04 | [6 empty] | 2025-11-06
VNPT-SW-0023 | Site 0023 Hà G | Hà Giang | RFI Complete | VNPT 4G Phase 10 | 5G | swap | 23.1306 | 104.7428 |  | 2025-11-08 | [8 empty] | 2025-11-25
VNPT-SW-0024 | Site 0024 Ninh | Ninh Bình | On Air Complete | VNPT 4G Phase 10 | 5G | swap | 20.1217 | 106.0505 | 2025-11-24 | 2025-12-12 | 2025-11-10 | 2025-12-13 |  |  |  |  | 2026-02-07 |  | 2025-12-16
VNPT-SW-0025 | Site 0025 Long | Long An | On Air Complete | VNPT 4G Phase 10 | 4G+5G | swap | 10.7558 | 106.1166 | 2026-02-08 | 2025-12-06 | 2026-02-08 | [8 empty] | 2026-02-13
VNPT-SW-0026 | Site 0026 Quản | Quảng Nam | On Air Complete | VNPT 4G Phase 10 | 4G+5G | swap | 15.3066 | 107.7305 | 2026-01-20 | 2025-11-24 |  |  | 2026-02-20 |  |  |  |  | 2025-12-08 | 2025-11-11
VNPT-SW-0027 | Site 0027 Bắc | Bắc Ninh | On Air Complete | VNPT 4G Phase 10 | 5G | swap | 21.5441 | 106.2379 | 2026-03-15 |  | 2025-12-11 | 2026-03-25 |  |  |  |  | 2026-01-13 | 2026-03-28 | 2025-12-09 |  | 2025-10-31
VNPT-SW-0028 | Site 0028 Khán | Khánh Hòa | On Air Complete | VNPT 4G Phase 10 | 5G | swap | 11.9257 | 109.0226 | 2025-12-18 | 2025-11-11 |  | 2026-02-15 |  |  |  |  | 2025-11-03 | 2026-03-16 |  | 2026-03-21 | 2026-02-25
VNPT-SW-0029 | Site 0029 Quản | Quảng Bình | On Air Complete | VNPT 4G Phase 10 | 4G+5G | swap | 17.0712 | 106.0334 | 2025-11-01 | 2026-02-19 | 2025-11-22 | 2026-02-27 |  |  |  |  | 2026-03-03
VNPT-SW-0030 | Site 0030 Tây | Tây Ninh | On Air Complete | VNPT 4G Phase 10 | 4G | swap | 11.498 | 106.4894 | 2025-11-07 | 2026-03-18 | 2025-11-14 | 2026-03-31 |  |  |  |  | 2026-04-05 |  |  |  | 2025-11-29
VNPT-SW-0031 | Site 0031 Quản | Quảng Nam | On Air Complete | VNPT 4G Phase 10 | 4G+5G | swap | 15.6701 | 108.3577 | 2025-12-05 | 2025-12-29 | [5 empty] | 2025-11-29 | 2025-12-15 | 2026-02-05 | 2025-12-28 |  | 2025-11-23
VNPT-SW-0032 | Site 0032 Bình | Bình Dương | Installation Complete | VNPT 4G Phase 10 | 4G+5G | swap | 11.0381 | 106.8983 | 2025-10-31 | 2026-02-08 | [6 empty] | 2026-04-07 |  | 2026-03-12 | 2026-03-02
VNPT-SW-0033 | Site 0033 Bình | Bình Định | Installation Complete | VNPT 4G Phase 10 | 5G | swap | 14.1082 | 109.2793 |  | 2025-12-25 | 2025-12-02 | [5 empty] | 2026-04-10 | 2026-01-24
VNPT-SW-0034 | Site 0034 Than | Thanh Hóa | On Air Complete | VNPT 4G Phase 10 | 4G | swap | 20.156 | 105.7108 | 2025-12-10 | 2026-01-03 | 2025-10-23 | 2025-11-10 | 2025-12-15 |  |  | 2026-03-05 |  |  | 2026-04-01 |  | 2025-12-19
VNPT-SW-0035 | Site 0035 Đà N | Đà Nẵng | On Air Complete | VNPT 4G Phase 10 | 4G+5G | swap | 16.2498 | 108.5518 | 2025-11-25 | 2026-01-19 | 2025-12-07 |  | 2025-10-30 |  |  |  |  | 2026-03-24 | 2026-01-27
VNPT-SW-0036 | Site 0036 Bắc | Bắc Ninh | Installation Complete | VNPT 4G Phase 10 | 4G+5G | swap | 21.0307 | 105.8442 | 2026-02-23 | 2026-03-21 |  | 2025-10-29 | 2025-12-12 |  |  |  | 2026-02-08
VNPT-SW-0037 | Site 0037 An G | An Giang | PAT Complete | VNPT 4G Phase 10 | 5G | swap | 10.2501 | 105.4453 | 2026-01-02 | 2026-03-14 | 2025-11-15 | 2026-04-08 |  |  |  | 2025-11-06 | 2026-01-25 |  | 2025-10-24
VNPT-SW-0038 | Site 0038 Quản | Quảng Nam | Installation Complete | VNPT 4G Phase 10 | 4G | swap | 15.6209 | 108.1778 | 2025-10-24 |  | 2026-03-17 | 2026-01-07 | [6 empty] | 2025-12-19 |  | 2026-01-25
VNPT-SW-0039 | Site 0039 Hà T | Hà Tĩnh | PAT Complete | VNPT 4G Phase 10 | 4G+5G | swap | 18.714 | 106.4442 | 2026-01-25 | 2026-01-14 | 2025-12-12 |  |  |  | 2025-11-24 |  |  | 2026-02-12
VNPT-SW-0040 | Site 0040 Nghệ | Nghệ An | On Air Complete | VNPT 4G Phase 10 | 5G | swap | 19.6403 | 104.4083 | 2026-04-04 | 2025-11-18 | 2025-11-05 | [5 empty] | 2026-03-25 |  | 2026-01-23 | 2026-03-30
VNPT-SW-0041 | Site 0041 Tây | Tây Ninh | On Air Complete | VNPT 4G Phase 10 | 5G | swap | 11.6266 | 106.4854 | 2025-12-06 | 2026-01-29 | 2026-01-06 | 2026-01-06 |  |  |  |  | 2025-12-18
VNPT-SW-0042 | Site 0042 Tiền | Tiền Giang | On Air Complete | VNPT 4G Phase 10 | 4G | swap | 9.9506 | 106.1335 |  | 2026-02-17 | 2025-11-20 | [5 empty] | 2026-02-14 |  | 2026-03-04
VNPT-SW-0043 | Site 0043 Quản | Quảng Nam | PAT Complete | VNPT 4G Phase 10 | 4G | swap | 15.5889 | 107.5158 | 2026-03-09 | 2025-11-27 | 2026-03-25 |  |  | 2025-12-09 |  |  | 2026-01-08 | 2026-03-14 | 2026-02-13 | 2025-10-24
VNPT-SW-0044 | Site 0044 Bình | Bình Thuận | RFI Complete | VNPT 4G Phase 10 | 4G | swap | 10.9221 | 107.6483 | 2025-11-02 | [7 empty] | 2025-11-09
VNPT-SW-0045 | Site 0045 Đà N | Đà Nẵng | PAT Complete | VNPT 4G Phase 10 | 4G+5G | swap | 16.016 | 107.7951 | 2025-10-22 | 2026-03-02 | 2025-12-10 | 2026-03-08 |  |  |  |  | 2026-03-20 | 2026-03-17
VNPT-SW-0046 | Site 0046 Bắc | Bắc Ninh | PAT Complete | VNPT 4G Phase 10 | 5G | swap | 20.9124 | 105.7036 | 2026-03-02 | 2026-02-12 |  |  |  | 2025-10-24 |  |  | 2025-11-19 | 2026-01-29 | 2025-12-22
VNPT-SW-0047 | Site 0047 Quản | Quảng Trị | PAT Complete | VNPT 4G Phase 10 | 4G+5G | swap | 16.3061 | 107.4699 | 2025-12-29 | 2025-10-30 |  | 2026-01-17 | 2026-03-28 | 2026-03-21 |  | 2025-11-03 | 2025-11-26 | 2025-12-24 | 2026-03-01
VNPT-SW-0048 | Site 0048 Hà T | Hà Tĩnh | Installation Complete | VNPT 4G Phase 10 | 5G | swap | 17.9138 | 105.9299 | 2025-11-10 | 2025-10-22 | 2026-02-13 | [5 empty] | 2025-11-08 | 2026-02-17 | 2026-02-15
VNPT-SW-0049 | Site 0049 Cần | Cần Thơ | PAT Complete | VNPT 4G Phase 10 | 4G | swap | 9.8971 | 106.042 | 2025-12-14 |  |  | 2026-01-17 |  |  |  |  | 2025-11-15 | 2025-10-29 | 2026-03-12 | 2025-11-03
VNPT-SW-0050 | Site 0050 Quản | Quảng Trị | On Air Complete | VNPT 4G Phase 10 | 4G | swap | 16.6331 | 106.7681 | 2026-03-12 | 2026-02-20 |  | 2026-02-25 |  |  |  |  | 2025-10-27 |  | 2026-03-04
VNPT-SW-0051 | Site 0051 Đồng | Đồng Nai | On Air Complete | VNPT 4G Phase 10 | 5G | swap | 10.9232 | 107.671 | 2025-12-19 | 2025-12-18 | 2026-01-30 | 2026-01-27 |  |  |  |  | 2026-01-10 | 2026-01-21 | 2026-04-01 | 2026-03-18
VNPT-SW-0052 | Site 0052 Tiền | Tiền Giang | Installation Complete | VNPT 4G Phase 10 | 5G | swap | 10.3756 | 105.9509 | 2026-03-15 | [8 empty] | 2025-10-27 | 2026-02-06
VNPT-SW-0053 | Site 0053 An G | An Giang | On Air Complete | VNPT 4G Phase 10 | 4G | swap | 10.3297 | 105.158 | 2026-02-05 | 2025-10-24 | [6 empty] | 2026-03-03 | 2025-11-12 |  | 2025-10-25
VNPT-SW-0054 | Site 0054 Cần | Cần Thơ | On Air Complete | VNPT 4G Phase 10 | 5G | swap | 10.4972 | 106.2124 | 2025-12-23 | 2026-04-06 | 2026-02-23 | 2026-01-25 | [5 empty] | 2025-12-07 | 2026-03-06 |  | 2025-11-23
VNPT-SW-0055 | Site 0055 Vĩnh | Vĩnh Phúc | Installation Complete | VNPT 4G Phase 10 | 5G | swap | 21.4711 | 105.909 | 2025-12-19 | 2026-01-07 | [6 empty] | 2025-12-18
VNPT-SW-0056 | Site 0056 Quản | Quảng Bình | PAT Complete | VNPT 4G Phase 10 | 5G | swap | 17.5275 | 106.7663 | 2025-11-07 | 2026-02-05 | 2025-12-08 | 2026-03-10 | 2025-12-20 |  |  | 2026-02-13 |  | 2026-03-15 |  | 2026-02-28 | 2025-11-30
VNPT-SW-0057 | Site 0057 Quản | Quảng Ngãi | Installation Complete | VNPT 4G Phase 10 | 4G | swap | 14.6749 | 108.1282 | [9 empty] | 2026-01-27
VNPT-SW-0058 | Site 0058 Long | Long An | On Air Complete | VNPT 4G Phase 10 | 4G | swap | 10.9762 | 105.8376 | 2026-02-08 | 2025-11-02 | 2026-03-13 |  | 2026-01-10 |  |  |  |  | 2025-11-24 | 2025-11-30
VNPT-SW-0059 | Site 0059 Bình | Bình Phước | On Air Complete | VNPT 4G Phase 10 | 5G | swap | 11.7542 | 106.7905 | 2025-10-30 | 2026-01-05 | 2026-04-06 |  | 2025-11-22 |  |  |  | 2026-03-24 | 2025-10-24
VNPT-SW-0060 | Site 0060 Lào | Lào Cai | PAT Complete | VNPT 4G Phase 10 | 4G | swap | 22.516 | 104.2436 | 2026-02-18 | 2026-02-18 |  |  | 2025-10-25 |  |  |  | 2026-01-21 | 2025-11-22 | 2026-04-01 | 2026-01-09
VNPT-SW-0061 | Site 0061 Bình | Bình Định | Installation Complete | VNPT 4G Phase 10 | 4G | swap | 14.0962 | 108.8975 |  | 2026-03-20 | [6 empty] | 2025-11-07 |  | 2026-01-25 | 2025-10-23
VNPT-SW-0062 | Site 0062 Đồng | Đồng Tháp | PAT Complete | VNPT 4G Phase 10 | 4G+5G | swap | 10.6395 | 105.8915 | 2025-10-29 | 2025-11-30 | 2026-03-01 | 2026-03-09 | [5 empty] | 2025-11-06 |  | 2025-10-27
VNPT-SW-0063 | Site 0063 Đồng | Đồng Nai | Installation Complete | VNPT 4G Phase 10 | 4G+5G | swap | 10.998 | 107.3496 | 2026-03-12 | 2026-02-22 | 2026-01-01 | 2025-11-05 | [5 empty] | 2026-02-03
VNPT-SW-0064 | Site 0064 Kiên | Kiên Giang | PAT Complete | VNPT 4G Phase 10 | 4G+5G | swap | 10.1678 | 104.8095 | 2026-01-26 | 2026-03-01 | 2025-10-29 | [5 empty] | 2026-01-08 | 2026-03-10 |  | 2025-12-05 | 2025-11-20
VNPT-SW-0065 | Site 0065 Gia | Gia Lai | On Air Complete | VNPT 4G Phase 10 | 4G+5G | swap | 14.1233 | 107.7738 |  | 2025-12-16 | 2025-11-29 | [5 empty] | 2025-11-20 |  | 2026-03-08 |  | 2026-03-10
VNPT-SW-0066 | Site 0066 Quản | Quảng Bình | PAT Complete | VNPT 4G Phase 10 | 4G+5G | swap | 17.1963 | 106.7564 | 2025-11-01 | 2025-11-25 | 2025-10-28 |  | 2025-10-28 |  |  |  | 2025-11-13 | 2025-10-24 |  | 2025-11-17 | 2026-04-03
VNPT-SW-0067 | Site 0067 An G | An Giang | On Air Complete | VNPT 4G Phase 10 | 5G | swap | 10.9567 | 105.0829 | 2025-12-28 | 2026-03-23 | 2026-03-01 | 2026-01-19 |  |  |  |  | 2025-12-08 | 2026-01-13
VNPT-SW-0068 | Site 0068 Than | Thanh Hóa | Installation Complete | VNPT 4G Phase 10 | 4G | swap | 19.5902 | 105.6841 | 2026-02-06 |  |  | 2026-03-01
VNPT-SW-0069 | Site 0069 Quản | Quảng Nam | RFI Complete | VNPT 4G Phase 10 | 4G+5G | swap | 15.4949 | 108.3823 |  | 2025-11-24 | 2026-03-14
VNPT-SW-0070 | Site 0070 Đồng | Đồng Tháp | On Air Complete | VNPT 4G Phase 10 | 4G | swap | 10.1287 | 105.1967 | 2026-01-14 | 2026-01-07 |  |  | 2025-11-30 |  |  |  | 2025-12-01 | 2026-03-31 | 2026-03-06
VNPT-SW-0071 | Site 0071 Hồ C | Hồ Chí Minh | Installation Complete | VNPT 4G Phase 10 | 5G | swap | 10.7323 | 106.9087 | 2026-04-06 | 2026-03-13 | [9 empty] | 2025-12-10
VNPT-SW-0072 | Site 0072 Đồng | Đồng Tháp | PAT Complete | VNPT 4G Phase 10 | 4G+5G | swap | 10.1478 | 105.7807 | 2026-03-13 | 2025-12-19 | 2026-03-03 | [5 empty] | 2026-02-17 | 2025-11-05 |  |  | 2026-03-06
VNPT-SW-0073 | Site 0073 Tây | Tây Ninh | Installation Complete | VNPT 4G Phase 10 | 4G+5G | swap | 11.5759 | 106.4677 | 2026-02-02 | 2026-02-20 | [6 empty] | 2026-01-24 | 2026-01-24
VNPT-SW-0074 | Site 0074 Phú | Phú Yên | PAT Complete | VNPT 4G Phase 10 | 4G | swap | 12.8905 | 108.8876 | 2026-01-12 |  | 2025-12-09 | 2025-11-04 |  |  |  |  | 2025-11-24 | 2025-11-18 |  |  | 2026-03-29
VNPT-SW-0075 | Site 0075 Nam | Nam Định | RFI Complete | VNPT 4G Phase 10 | 5G | swap | 20.5779 | 105.8579 |  |  | 2025-10-26 | [5 empty] | 2026-01-27
VNPT-SW-0076 | Site 0076 Quản | Quảng Ninh | PAT Complete | VNPT 4G Phase 10 | 4G+5G | swap | 21.488 | 106.8863 | 2026-01-26 | 2026-04-08 | 2025-11-07 |  | 2026-03-13 |  |  |  | 2026-01-15 | 2025-10-28 | 2025-12-05 | 2025-12-02
VNPT-SW-0077 | Site 0077 Quản | Quảng Bình | On Air Complete | VNPT 4G Phase 10 | 4G | swap | 17.1755 | 106.6561 |  |  | 2026-03-19 | 2026-01-02 |  |  |  |  | 2026-03-17 | 2026-03-06 | 2026-02-06 | 2026-02-01
VNPT-SW-0078 | Site 0078 Quản | Quảng Trị | Installation Complete | VNPT 4G Phase 10 | 5G | swap | 16.8025 | 107.4951 | 2026-01-21 | [8 empty] | 2026-02-13 | 2026-03-07
VNPT-SW-0079 | Site 0079 Kiên | Kiên Giang | PAT Complete | VNPT 4G Phase 10 | 4G | swap | 10.0255 | 104.6282 | 2025-11-17 | 2025-11-21 |  | 2026-02-17 |  | 2026-03-08 |  |  | 2025-11-24 | 2026-01-17
VNPT-SW-0080 | Site 0080 Quản | Quảng Trị | On Air Complete | VNPT 4G Phase 10 | 4G+5G | swap | 16.5545 | 106.603 | 2026-03-23 | 2026-01-12 | 2025-11-23 | 2025-12-27 | [6 empty] | 2025-12-11 | 2026-03-07
VNPT-NE-0081 | Site 0081 Bình | Bình Định | RFI Complete | VNPT 4G Phase 10 | 5G | new | 14.4746 | 108.533 |  | 2025-11-24 | 2026-03-09 | [6 empty] | 2026-04-10
VNPT-NE-0082 | Site 0082 Thái | Thái Bình | RFI Complete | VNPT 4G Phase 10 | 5G | new | 20.3192 | 106.6661 |  | 2026-02-17 | 2025-11-09 | [5 empty] | 2025-11-08 |  |  | 2025-12-19
VNPT-NE-0083 | Site 0083 Đồng | Đồng Nai | Installation Complete | VNPT 4G Phase 10 | 5G | new | 11.3725 | 107.5184 | 2026-03-05 |  | 2025-12-26 | [5 empty] | 2026-03-26 |  |  | 2025-12-22
VNPT-NE-0084 | Site 0084 Khán | Khánh Hòa | Installation Complete | VNPT 4G Phase 10 | 4G+5G | new | 11.8839 | 109.0379 | 2026-02-12 | 2026-03-05 | [9 empty] | 2026-02-07
VNPT-NE-0085 | Site 0085 Bắc | Bắc Ninh | Installation Complete | VNPT 4G Phase 10 | 5G | new | 21.205 | 105.6395 | 2025-11-11 |  | 2025-12-09 | [5 empty] | 2026-01-15 | 2026-04-07 | 2026-02-21 | 2025-12-09
VNPT-NE-0086 | Site 0086 Kon | Kon Tum | On Air Complete | VNPT 4G Phase 10 | 4G+5G | new | 14.3084 | 107.5596 |  | 2025-12-11 | [6 empty] | 2026-02-17 | 2025-12-26 | 2026-02-13 | 2025-11-20
VNPT-NE-0087 | Site 0087 Đắk | Đắk Lắk | On Air Complete | VNPT 4G Phase 10 | 5G | new | 12.6376 | 108.4634 | 2025-10-28 | 2025-12-14 | 2026-01-10 |  | 2026-03-29 |  |  |  | 2025-11-22 | 2025-11-23
VNPT-NE-0088 | Site 0088 Hà N | Hà Nội | Installation Complete | VNPT 4G Phase 10 | 4G+5G | new | 20.8732 | 105.9178 | 2025-11-04 | [7 empty] | 2025-11-25 |  | 2025-11-26
VNPT-NE-0089 | Site 0089 Bình | Bình Phước | Installation Complete | VNPT 4G Phase 10 | 4G | new | 11.8198 | 106.6524 | 2025-12-30 | 2025-12-28 | 2026-02-07 | [6 empty] | 2026-03-21 |  |  | 2026-01-03
VNPT-NE-0090 | Site 0090 Tiền | Tiền Giang | PAT Complete | VNPT 4G Phase 10 | 5G | new | 10.8773 | 106.7738 | 2026-03-31 | 2025-11-16 | 2026-03-30 | [7 empty] | 2025-11-22 | 2026-01-20 | 2026-02-16
VNPT-NE-0091 | Site 0091 Than | Thanh Hóa | On Air Complete | VNPT 4G Phase 10 | 4G+5G | new | 19.977 | 105.8406 | 2026-03-06 | 2026-03-21 | 2026-01-12 |  | 2026-01-31 |  |  |  | 2025-12-20 | 2026-03-22 | 2025-11-04
VNPT-NE-0092 | Site 0092 Lào | Lào Cai | On Air Complete | VNPT 4G Phase 10 | 5G | new | 22.1801 | 104.0722 | 2026-02-06 | 2026-03-20 | 2026-01-03 | 2026-03-14 | [7 empty] | 2026-01-22
VNPT-NE-0093 | Site 0093 Hà N | Hà Nam | RFI Complete | VNPT 4G Phase 10 | 4G+5G | new | 20.5542 | 106.0969 |  |  | 2025-12-26 | [5 empty] | 2026-03-20
VNPT-NE-0094 | Site 0094 Hà T | Hà Tĩnh | On Air Complete | VNPT 4G Phase 10 | 4G+5G | new | 18.5827 | 105.8611 |  | 2025-12-05 | 2026-02-19 | 2026-01-16 |  |  |  |  | 2026-03-07 | 2025-12-30 | 2025-11-03
VNPT-NE-0095 | Site 0095 Gia | Gia Lai | Installation Complete | VNPT 4G Phase 10 | 4G+5G | new | 14.2687 | 107.9914 | 2025-12-06 |  |  | 2025-11-17 |  |  |  |  | 2026-01-29 |  |  | 2025-11-22
VNPT-NE-0096 | Site 0096 Hải | Hải Dương | PAT Complete | VNPT 4G Phase 10 | 4G+5G | new | 21.073 | 105.9392 | 2026-02-05 | 2025-12-23 | 2026-03-23 |  |  | 2026-02-06 |  |  | 2025-11-08 | 2025-12-29 | 2025-12-24 |  | 2025-11-24
VNPT-NE-0097 | Site 0097 Quản | Quảng Ninh | On Air Complete | VNPT 4G Phase 10 | 5G | new | 21.3775 | 107.0996 | 2025-12-21 | 2026-03-16 | 2025-12-01 | 2025-11-11 | [5 empty] | 2025-11-14 | 2026-01-05 |  | 2026-04-04
VNPT-NE-0098 | Site 0098 Quản | Quảng Nam | Installation Complete | VNPT 4G Phase 10 | 4G+5G | new | 15.7843 | 108.0211 | 2026-03-17 | 2025-12-16 | 2026-01-24 | [5 empty] | 2026-03-12 | 2026-01-13 |  | 2026-02-07
VNPT-NE-0099 | Site 0099 Lào | Lào Cai | On Air Complete | VNPT 4G Phase 10 | 4G+5G | new | 22.1956 | 104.0374 |  | 2025-12-22 | 2026-02-15 | [5 empty] | 2026-03-25 |  |  |  | 2026-03-12
VNPT-NE-0100 | Site 0100 Hồ C | Hồ Chí Minh | Installation Complete | VNPT 4G Phase 10 | 4G+5G | new | 11.0455 | 106.8174 |  |  | 2025-11-04 | [7 empty] | 2026-02-08 | 2026-03-05
VNPT-NE-0101 | Site 0101 Tiền | Tiền Giang | PAT Complete | VNPT 4G Phase 10 | 4G | new | 10.4549 | 106.2896 | 2026-01-20 | 2025-11-03 | 2026-01-09 | [6 empty] | 2026-02-20
VNPT-NE-0102 | Site 0102 Yên | Yên Bái | Installation Complete | VNPT 4G Phase 10 | 4G+5G | new | 21.4248 | 104.2887 |  | 2025-12-05 | 2026-03-13 | [6 empty] | 2025-11-22 |  |  | 2025-12-19
VNPT-NE-0103 | Site 0103 Quản | Quảng Ninh | On Air Complete | VNPT 4G Phase 10 | 4G+5G | new | 21.5622 | 106.787 | 2026-03-11 | 2026-02-09 | 2025-11-11
VNPT-NE-0104 | Site 0104 Quản | Quảng Bình | Installation Complete | VNPT 4G Phase 10 | 4G+5G | new | 17.9524 | 106.3144 |  |  | 2025-12-26 | 2026-03-08
VNPT-NE-0105 | Site 0105 Khán | Khánh Hòa | On Air Complete | VNPT 4G Phase 10 | 4G | new | 12.3336 | 109.3801 | 2025-11-30 | 2026-01-06 | 2025-12-07 | 2025-12-14 |  |  |  |  | 2026-04-10
VNPT-NE-0106 | Site 0106 T.T. | T.T. Huế | PAT Complete | VNPT 4G Phase 10 | 4G+5G | new | 16.4473 | 107.1306 | 2026-01-13 | 2026-03-29 | 2025-11-01 | 2025-12-15 | [5 empty] | 2026-03-10 |  | 2025-12-22 | 2026-03-08
VNPT-NE-0107 | Site 0107 Hưng | Hưng Yên | On Air Complete | VNPT 4G Phase 10 | 5G | new | 20.3655 | 105.9963 | 2026-02-10 | 2026-03-18 | 2026-04-10 | [5 empty] | 2026-03-22 | 2026-02-12 |  | 2026-01-13
VNPT-NE-0108 | Site 0108 Hà N | Hà Nam | Installation Complete | VNPT 4G Phase 10 | 4G+5G | new | 20.881 | 105.6371 |  |  | 2026-03-05 | [5 empty] | 2025-11-17 | 2025-10-26 | 2026-01-11
VNPT-NE-0109 | Site 0109 Hồ C | Hồ Chí Minh | On Air Complete | VNPT 4G Phase 10 | 4G+5G | new | 11.1632 | 106.5145 | 2026-01-30 | 2026-02-06 | 2025-11-08 | [6 empty] | 2026-04-04 |  | 2025-11-29
VNPT-NE-0110 | Site 0110 Bình | Bình Định | Installation Complete | VNPT 4G Phase 10 | 4G+5G | new | 14.2381 | 108.471 |  | 2026-01-08 |  |  | 2026-03-24 |  |  |  | 2025-11-16 | 2025-11-22
VNPT-NE-0111 | Site 0111 Quản | Quảng Bình | On Air Complete | VNPT 4G Phase 10 | 5G | new | 17.7671 | 106.2236 | 2025-10-29 | 2025-11-04 | 2026-03-20 | 2026-01-17 |  |  |  |  | 2025-12-01
VNPT-NE-0112 | Site 0112 Bắc | Bắc Ninh | Installation Complete | VNPT 4G Phase 10 | 4G+5G | new | 20.716 | 106.2123 | 2025-10-22 | [7 empty] | 2026-03-06 |  | 2026-01-12
VNPT-NE-0113 | Site 0113 Hải | Hải Phòng | Installation Complete | VNPT 4G Phase 10 | 4G+5G | new | 20.572 | 106.2639 | 2025-11-14 | 2025-12-04 | 2026-01-08 |  | 2026-04-07 |  |  |  | 2025-11-16 | 2026-03-01 | 2026-03-15 |  | 2025-12-01
VNPT-NE-0114 | Site 0114 Quản | Quảng Ninh | On Air Complete | VNPT 4G Phase 10 | 5G | new | 21.4407 | 107.1194 | 2025-12-25 |  | 2026-03-22 | [5 empty] | 2026-03-11 | 2026-03-28 | 2025-11-29 |  | 2025-12-12
VNPT-NE-0115 | Site 0115 Quản | Quảng Bình | On Air Complete | VNPT 4G Phase 10 | 4G+5G | new | 17.7396 | 106.0426 | 2025-12-05 |  |  | 2025-11-23 | [5 empty] | 2026-02-07 | 2025-12-27
VNPT-NE-0116 | Site 0116 Hà N | Hà Nam | Installation Complete | VNPT 4G Phase 10 | 4G | new | 20.4198 | 106.4612 |  | 2026-01-29 | 2026-02-10 | [9 empty] | 2026-03-17
VNPT-NE-0117 | Site 0117 Nam | Nam Định | Installation Complete | VNPT 4G Phase 10 | 4G+5G | new | 20.4509 | 106.626 | 2026-01-17 | 2026-01-31 | 2026-02-18 | [5 empty] | 2025-11-12 | 2026-03-14 | 2025-12-12 | 2026-01-09
VNPT-NE-0118 | Site 0118 Long | Long An | RFI Complete | VNPT 4G Phase 10 | 4G+5G | new | 10.3483 | 106.3112 |  | 2026-03-29 | [6 empty] | 2026-02-25 | 2025-12-28
VNPT-NE-0119 | Site 0119 Hà G | Hà Giang | PAT Complete | VNPT 4G Phase 10 | 4G+5G | new | 22.9863 | 105.4376 | 2025-11-11 | 2026-03-22 | 2026-03-25 | 2025-12-13 |  |  |  |  | 2025-10-27 | 2026-03-09 | 2026-01-16 | 2025-11-15
VNPT-NE-0120 | Site 0120 Hà T | Hà Tĩnh | Installation Complete | VNPT 4G Phase 10 | 4G | new | 17.8346 | 106.1192 | 2026-01-25 | 2025-11-21 | 2026-03-19 | [5 empty] | 2026-03-06 | 2025-10-28
VNPT-NE-0121 | Site 0121 Đồng | Đồng Nai | On Air Complete | VNPT 4G Phase 10 | 4G+5G | new | 10.8704 | 106.7261 | 2026-04-03 | [7 empty] | 2025-12-11 | 2025-11-12 |  | 2025-10-24
VNPT-NE-0122 | Site 0122 Bình | Bình Định | On Air Complete | VNPT 4G Phase 10 | 4G | new | 13.7761 | 108.9925 | 2026-01-09 |  | 2026-01-10 | 2025-12-05 | 2026-02-10 | [7 empty] | 2026-04-01
VNPT-NE-0123 | Site 0123 Nam | Nam Định | Installation Complete | VNPT 4G Phase 10 | 4G | new | 20.5188 | 106.5443 | 2026-04-05 | 2026-03-05
VNPT-NE-0124 | Site 0124 Đắk | Đắk Lắk | On Air Complete | VNPT 4G Phase 10 | 4G | new | 13.0072 | 108.262 |  | 2026-01-09 | 2025-11-11 | [6 empty] | 2026-01-25 | 2026-04-10
VNPT-NE-0125 | Site 0125 Yên | Yên Bái | On Air Complete | VNPT 4G Phase 10 | 4G | new | 22.1367 | 104.1406 | 2026-02-09 | 2026-01-19 | 2026-03-19 | 2026-04-08 | [7 empty] | 2026-02-06
VNPT-NE-0126 | Site 0126 Vĩnh | Vĩnh Phúc | PAT Complete | VNPT 4G Phase 10 | 4G+5G | new | 21.5818 | 105.4512 | 2025-12-09 | 2025-11-14 | 2026-02-12 | 2026-03-15 | 2026-03-22 |  |  |  | 2026-03-23 |  | 2026-04-05 | 2026-02-26
VNPT-NE-0127 | Site 0127 Gia | Gia Lai | On Air Complete | VNPT 4G Phase 10 | 4G+5G | new | 14.2424 | 107.865 |  | 2026-03-16 | 2026-02-21 | 2026-01-28 |  |  |  |  | 2025-11-20 |  |  | 2026-03-17 | 2025-11-15
VNPT-NE-0128 | Site 0128 An G | An Giang | On Air Complete | VNPT 4G Phase 10 | 4G | new | 10.097 | 104.807 | 2026-03-21 | 2026-03-12 | 2025-12-30 | 2026-01-03 |  |  |  |  | 2025-10-23 | 2025-10-28
VNPT-NE-0129 | Site 0129 Cần | Cần Thơ | RFI Complete | VNPT 4G Phase 10 | 5G | new | 9.8438 | 105.8414
VNPT-NE-0130 | Site 0130 Bình | Bình Phước | PAT Complete | VNPT 4G Phase 10 | 5G | new | 12.1828 | 106.5474 | 2025-12-17 | 2026-02-27 |  | 2025-11-01 | 2025-11-19 |  |  |  |  | 2025-12-23 | 2025-12-20 | 2025-11-09 | 2026-03-24
VNPT-NE-0131 | Site 0131 Đồng | Đồng Tháp | On Air Complete | VNPT 4G Phase 10 | 4G+5G | new | 10.1125 | 105.2496 | 2025-11-12 | 2026-03-16 | [6 empty] | 2026-03-16
VNPT-NE-0132 | Site 0132 Kiên | Kiên Giang | On Air Complete | VNPT 4G Phase 10 | 4G | new | 9.8958 | 104.979 | 2026-03-29 | 2026-02-01 | [6 empty] | 2026-01-23 | 2025-12-06 |  |  | 2026-01-24
VNPT-NE-0133 | Site 0133 Hà G | Hà Giang | On Air Complete | VNPT 4G Phase 10 | 4G+5G | new | 23.0409 | 105.2595 | 2026-03-27 | 2026-03-01 | 2025-12-02 | [5 empty] | 2025-11-27 |  | 2026-02-20 | 2026-03-27
VNPT-NE-0134 | Site 0134 An G | An Giang | PAT Complete | VNPT 4G Phase 10 | 5G | new | 10.0306 | 104.9725 | 2026-02-24 |  | 2025-11-20 | 2026-01-02 | 2026-02-13 |  |  |  | 2026-02-28 |  | 2026-03-18 | 2025-11-15
VNPT-NE-0135 | Site 0135 Kiên | Kiên Giang | RFI Complete | VNPT 4G Phase 10 | 4G | new | 10.1474 | 104.7011 | 2026-02-05
VNPT-NE-0136 | Site 0136 Cần | Cần Thơ | PAT Complete | VNPT 4G Phase 10 | 4G+5G | new | 10.0615 | 105.8938 | 2026-03-14 | 2026-01-14 |  | 2026-02-08 |  |  |  |  | 2026-01-30 | 2025-10-26 | 2026-03-03
VNPT-NE-0137 | Site 0137 Quản | Quảng Bình | Installation Complete | VNPT 4G Phase 10 | 4G+5G | new | 17.4046 | 106.5367 | 2025-11-15 |  | 2026-02-13
VNPT-NE-0138 | Site 0138 Bình | Bình Dương | PAT Complete | VNPT 4G Phase 10 | 4G | new | 11.5469 | 107.0996 | 2026-02-13 | 2026-01-22 | 2026-01-16 | [5 empty] | 2025-11-12 | 2026-03-11 | 2025-10-30 |  | 2026-02-20
VNPT-NE-0139 | Site 0139 Nam | Nam Định | PAT Complete | VNPT 4G Phase 10 | 4G+5G | new | 20.0092 | 106.2694 | 2025-12-14 | 2026-02-23 | 2025-12-07 | 2026-02-26 | 2025-12-20 |  |  |  | 2026-02-24 | 2026-03-27 | 2026-01-30 |  | 2026-03-19
VNPT-NE-0140 | Site 0140 Hà G | Hà Giang | On Air Complete | VNPT 4G Phase 10 | 4G | new | 23.192 | 105.2568 | 2026-04-06 | 2025-11-01 |  | 2026-03-25 |  |  |  |  | 2026-01-12 | 2026-03-15 | 2025-11-11
VNPT-NE-0141 | Site 0141 Đà N | Đà Nẵng | PAT Complete | VNPT 4G Phase 10 | 4G+5G | new | 15.9593 | 107.8884 | 2025-12-28 | 2026-02-12 | 2026-03-08 |  |  | 2026-03-14 |  |  | 2026-04-05 | 2026-02-26 | 2025-10-26 | 2025-10-29 | 2025-11-25
VNPT-NE-0142 | Site 0142 Khán | Khánh Hòa | On Air Complete | VNPT 4G Phase 10 | 4G | new | 12.2473 | 108.9744 | 2025-10-31 | 2025-12-24 | 2025-10-23 | [5 empty] | 2025-11-02 |  | 2026-03-15
VNPT-NE-0143 | Site 0143 Quản | Quảng Nam | On Air Complete | VNPT 4G Phase 10 | 4G+5G | new | 15.1604 | 108.0481 |  | 2025-12-08 | 2026-04-10 |  | 2026-03-16 |  |  |  | 2026-03-19 |  |  | 2026-03-18
VNPT-NE-0144 | Site 0144 Bắc | Bắc Ninh | RFI Complete | VNPT 4G Phase 10 | 4G | new | 21.4741 | 106.4522 | 2026-01-20 | 2026-03-12 | 2026-03-30 | [5 empty] | 2026-03-06 |  | 2026-01-09
VNPT-NE-0145 | Site 0145 Bình | Bình Định | On Air Complete | VNPT 4G Phase 10 | 4G+5G | new | 14.3999 | 109.0488 | 2026-03-13 | 2026-03-26 | [7 empty] | 2025-11-10
VNPT-NE-0146 | Site 0146 Gia | Gia Lai | PAT Complete | VNPT 4G Phase 10 | 4G | new | 14.1876 | 108.1407 | 2025-10-25 | 2025-11-27 | 2025-11-14 | 2025-11-28 |  |  |  |  | 2026-02-12
VNPT-NE-0147 | Site 0147 Bình | Bình Dương | PAT Complete | VNPT 4G Phase 10 | 5G | new | 10.6546 | 106.8434 | 2025-12-11 | 2026-02-27 | 2025-12-06 | [5 empty] | 2026-01-16 |  | 2026-02-12 | 2026-02-09 | 2025-12-18
VNPT-NE-0148 | Site 0148 Tiền | Tiền Giang | RFI Complete | VNPT 4G Phase 10 | 4G+5G | new | 10.3123 | 106.3571 | 2026-03-18
VNPT-NE-0149 | Site 0149 Cần | Cần Thơ | On Air Complete | VNPT 4G Phase 10 | 4G+5G | new | 9.614 | 106.0593 | 2026-01-13 | 2025-10-30 | [6 empty] | 2025-11-28 | 2026-03-14 | 2026-02-27
VNPT-NE-0150 | Site 0150 Hà G | Hà Giang | On Air Complete | VNPT 4G Phase 10 | 4G | new | 23.0571 | 104.5465 | 2025-11-11 | 2025-12-16 | 2025-11-11 | [6 empty] | 2025-12-04 | 2026-03-29
VNPT-NE-0151 | Site 0151 Hà N | Hà Nam | On Air Complete | VNPT 4G Phase 10 | 5G | new | 20.6062 | 105.8218 |  | 2025-11-06 | [7 empty] | 2026-01-13 |  | 2025-12-26
VNPT-NE-0152 | Site 0152 Bình | Bình Dương | On Air Complete | VNPT 4G Phase 10 | 4G | new | 10.8097 | 106.9144 | 2026-03-08 |  | 2026-02-24 | [5 empty] | 2025-10-29 | 2026-03-12
VNPT-NE-0153 | Site 0153 Hà N | Hà Nội | On Air Complete | VNPT 4G Phase 10 | 4G | new | 20.8809 | 105.3531 | 2026-02-01 | 2026-02-28 |  | 2025-11-23 | [5 empty] | 2026-03-26 |  | 2025-12-16 | 2025-11-18
VNPT-NE-0154 | Site 0154 Quản | Quảng Bình | On Air Complete | VNPT 4G Phase 10 | 4G | new | 17.9265 | 106.1876 |  |  | 2025-11-20 | [5 empty] | 2026-02-05 | 2025-12-18
VNPT-NE-0155 | Site 0155 Lào | Lào Cai | PAT Complete | VNPT 4G Phase 10 | 4G | new | 21.987 | 103.4738 | 2026-01-04 | 2026-01-29 | 2026-03-08 | 2026-03-02 |  |  |  |  | 2026-02-04 | 2025-12-12
VNPT-NE-0156 | Site 0156 Hải | Hải Dương | PAT Complete | VNPT 4G Phase 10 | 4G+5G | new | 20.9254 | 106.757 | 2025-12-02 | 2025-11-22 | 2026-03-18 | [5 empty] | 2026-02-15 | 2026-01-16 | 2026-02-14
VNPT-NE-0157 | Site 0157 Tiền | Tiền Giang | On Air Complete | VNPT 4G Phase 10 | 5G | new | 10.1438 | 105.8399 |  | 2026-03-12 | 2025-11-23 | 2025-12-01 | [5 empty] | 2025-11-29 |  |  | 2025-10-26
VNPT-NE-0158 | Site 0158 Hà N | Hà Nội | On Air Complete | VNPT 4G Phase 10 | 4G | new | 21.1703 | 106.0736 | 2025-12-23 |  | 2025-12-20 | 2025-12-14 | 2026-02-05 | [7 empty] | 2026-03-23
VNPT-NE-0159 | Site 0159 An G | An Giang | On Air Complete | VNPT 4G Phase 10 | 4G+5G | new | 10.0169 | 105.2733 | 2025-10-28 | 2026-03-25 | [5 empty] | 2026-03-01 | 2026-03-23 | 2025-12-03 | 2026-01-23 | 2025-12-19
VNPT-NE-0160 | Site 0160 Tây | Tây Ninh | Installation Complete | VNPT 4G Phase 10 | 5G | new | 11.0441 | 106.2773 |  |  |  | 2026-04-09 |  |  |  |  | 2026-04-08
VNPT-NE-0161 | Site 0161 Tiền | Tiền Giang | PAT Complete | VNPT 4G Phase 10 | 4G | new | 10.061 | 106.0208 | 2026-02-20 | 2025-11-16 |  | 2025-11-21 | [7 empty] | 2026-03-24 | 2026-02-19
VNPT-NE-0162 | Site 0162 Đồng | Đồng Tháp | RFI Complete | VNPT 4G Phase 10 | 4G | new | 10.3178 | 105.5506 | 2026-01-22 |  | 2025-11-16 | [5 empty] | 2026-01-20 |  | 2026-01-20
VNPT-NE-0163 | Site 0163 Quản | Quảng Nam | PAT Complete | VNPT 4G Phase 10 | 4G+5G | new | 15.5517 | 107.6758 | 2026-01-29 | 2026-03-06 |  |  |  |  | 2026-02-03 |  | 2025-11-01 | 2026-03-22
VNPT-NE-0164 | Site 0164 Gia | Gia Lai | On Air Complete | VNPT 4G Phase 10 | 4G | new | 13.6658 | 107.9233 | 2026-01-26 | 2025-12-03 | 2025-12-30 |  | 2026-03-01 |  |  |  | 2026-04-08 |  |  |  | 2025-11-30
VNPT-NE-0165 | Site 0165 Gia | Gia Lai | PAT Complete | VNPT 4G Phase 10 | 4G | new | 13.5188 | 108.1876 | 2026-01-06 | 2026-02-17 | 2026-01-08 | 2025-11-28 |  |  |  |  | 2025-12-15 |  | 2025-10-26 |  | 2026-02-02
VNPT-NE-0166 | Site 0166 Hải | Hải Dương | On Air Complete | VNPT 4G Phase 10 | 4G+5G | new | 21.3727 | 106.0229 | 2026-01-12 | 2025-12-08 |  | 2026-03-03 |  |  |  |  | 2026-03-06 | 2026-02-11 | 2025-10-28 | 2026-01-08
VNPT-NE-0167 | Site 0167 Gia | Gia Lai | Installation Complete | VNPT 4G Phase 10 | 4G | new | 13.9473 | 108.1109 | 2026-03-09 | 2026-02-28 | 2025-11-30 | [5 empty] | 2025-11-15 | 2026-02-27 | 2026-02-23
VNPT-NE-0168 | Site 0168 Long | Long An | PAT Complete | VNPT 4G Phase 10 | 4G+5G | new | 10.3706 | 106.4304 | 2025-11-12 | 2026-02-23 | 2025-12-01 | 2026-01-02 |  |  |  |  | 2026-01-13 |  | 2026-03-24 | 2026-04-06 | 2025-12-02
VNPT-NE-0169 | Site 0169 Tây | Tây Ninh | On Air Complete | VNPT 4G Phase 10 | 4G | new | 10.9932 | 106.2594 |  | 2026-04-10 |  | 2026-03-30
VNPT-NE-0170 | Site 0170 Đồng | Đồng Nai | RFI Complete | VNPT 4G Phase 10 | 4G | new | 10.8545 | 107.4659 |  | 2025-11-08 |  | 2026-04-09 | [5 empty] | 2026-04-09
VNPT-NE-0171 | Site 0171 Tây | Tây Ninh | On Air Complete | VNPT 4G Phase 10 | 4G+5G | new | 11.5119 | 106.5918 | 2026-02-17 | 2025-11-19 | 2026-01-06 |  | 2026-02-11 |  |  |  | 2025-12-08 | 2026-01-22 |  |  | 2025-10-24
VNPT-NE-0172 | Site 0172 Đà N | Đà Nẵng | PAT Complete | VNPT 4G Phase 10 | 5G | new | 16.2971 | 108.4068 | 2025-10-30 | 2026-03-18 | 2025-12-11 | 2026-04-01 | [5 empty] | 2026-03-25 | 2026-01-06
VNPT-NE-0173 | Site 0173 Lào | Lào Cai | On Air Complete | VNPT 4G Phase 10 | 4G+5G | new | 21.8107 | 104.1506 |  | 2026-02-20 | 2025-11-08 | 2025-10-25 |  |  |  |  | 2026-02-10 |  |  | 2026-03-01 | 2026-01-30
VNPT-NE-0174 | Site 0174 Hải | Hải Dương | PAT Complete | VNPT 4G Phase 10 | 5G | new | 20.6845 | 106.6298 | 2026-01-11 | 2026-01-30 | 2026-02-20 | 2026-03-23 |  |  |  |  | 2025-12-28 | 2026-02-03 | 2025-12-02 |  | 2026-03-12
VNPT-NE-0175 | Site 0175 Bình | Bình Định | On Air Complete | VNPT 4G Phase 10 | 4G | new | 14.3575 | 109.3612 | 2025-12-14 |  |  | 2026-02-11 |  |  |  |  | 2026-02-03 | 2025-10-30
VNPT-NE-0176 | Site 0176 Đà N | Đà Nẵng | RFI Complete | VNPT 4G Phase 10 | 4G | new | 16.0766 | 108.0535 |  | 2026-02-21 | [6 empty] | 2026-02-08 |  | 2026-02-18
VNPT-NE-0177 | Site 0177 Tây | Tây Ninh | PAT Complete | VNPT 4G Phase 10 | 4G+5G | new | 11.2712 | 105.9154 | 2025-11-14 | 2025-12-06 | 2025-12-01 | [5 empty] | 2026-02-13 |  | 2025-11-27
VNPT-NE-0178 | Site 0178 Kon | Kon Tum | Installation Complete | VNPT 4G Phase 10 | 4G | new | 14.0118 | 107.4108 | 2026-01-17 | 2026-02-03 | 2026-02-02 | [5 empty] | 2025-12-11 |  | 2026-02-22
VNPT-NE-0179 | Site 0179 Yên | Yên Bái | PAT Complete | VNPT 4G Phase 10 | 5G | new | 21.4699 | 104.2358 | 2026-01-03 | 2026-03-03 | 2026-04-08 |  | 2026-03-16 | 2026-02-04 |  |  | 2025-12-04 | 2025-10-31 | 2026-01-20 | 2025-11-18
VNPT-NE-0180 | Site 0180 Đà N | Đà Nẵng | Installation Complete | VNPT 4G Phase 10 | 4G+5G | new | 16.1604 | 108.6318 | 2026-04-05 | 2026-01-11 | [7 empty] | 2025-11-14
VNPT-NE-0181 | Site 0181 Kon | Kon Tum | On Air Complete | VNPT 4G Phase 10 | 4G | new | 14.8683 | 107.8406 |  | 2025-11-05 | 2026-03-23 | [5 empty] | 2026-01-13 | 2026-01-19
VNPT-NE-0182 | Site 0182 Vĩnh | Vĩnh Phúc | Installation Complete | VNPT 4G Phase 10 | 4G | new | 20.825 | 105.3346 | 2026-03-21 | 2025-12-30 | 2026-03-25 | [7 empty] | 2025-12-30 |  | 2025-11-03
VNPT-NE-0183 | Site 0183 An G | An Giang | Installation Complete | VNPT 4G Phase 10 | 5G | new | 10.8385 | 104.6286 | 2026-01-17 |  | 2025-11-23 | 2025-11-09 | [6 empty] | 2025-11-23
VNPT-NE-0184 | Site 0184 Yên | Yên Bái | PAT Complete | VNPT 4G Phase 10 | 4G+5G | new | 21.5079 | 104.4122 | 2026-04-08 | 2026-03-07 | 2025-12-11 | [5 empty] | 2025-12-06 |  | 2026-04-08
VNPT-NE-0185 | Site 0185 Tiền | Tiền Giang | On Air Complete | VNPT 4G Phase 10 | 4G+5G | new | 10.1206 | 105.8792 | 2025-11-29 | 2025-11-05 |  |  | 2025-12-15 |  |  |  |  | 2025-11-25 |  |  | 2026-01-26
VNPT-NE-0186 | Site 0186 Bắc | Bắc Ninh | PAT Complete | VNPT 4G Phase 10 | 4G | new | 20.7859 | 105.7023 | 2025-12-19 | 2026-02-10 | 2026-04-07 | 2026-04-02 | 2025-12-11 |  |  | 2026-02-05 | 2026-01-13 | 2025-12-04 |  | 2026-03-04 | 2025-12-31
VNPT-NE-0187 | Site 0187 Than | Thanh Hóa | On Air Complete | VNPT 4G Phase 10 | 4G+5G | new | 19.5472 | 106.2945 | 2026-03-17 | 2026-02-16 | 2026-01-21 | [6 empty] | 2026-03-31 |  | 2025-12-08
VNPT-NE-0188 | Site 0188 T.T. | T.T. Huế | RFI Complete | VNPT 4G Phase 10 | 4G+5G | new | 16.4847 | 107.3958 | 2026-03-31 | [8 empty] | 2026-03-19
VNPT-NE-0189 | Site 0189 Hà N | Hà Nam | Installation Complete | VNPT 4G Phase 10 | 4G | new | 20.3167 | 106.0584 | 2026-01-12 |  | 2026-02-20 | [5 empty] | 2026-01-04 | 2026-03-07 | 2026-03-31
VNPT-NE-0190 | Site 0190 Long | Long An | PAT Complete | VNPT 4G Phase 10 | 5G | new | 10.3603 | 106.1311 | 2026-02-02 | 2025-12-15 | 2025-10-29 | 2025-11-03 |  |  |  |  | 2026-02-22 |  |  | 2026-03-25
VNPT-NE-0191 | Site 0191 T.T. | T.T. Huế | On Air Complete | VNPT 4G Phase 10 | 4G+5G | new | 16.0105 | 107.5232 | 2026-03-08 | 2026-04-02 | 2025-12-07 | [5 empty] | 2026-04-02
VNPT-NE-0192 | Site 0192 Đắk | Đắk Lắk | PAT Complete | VNPT 4G Phase 10 | 4G | new | 12.7681 | 108.3389 | 2025-12-25 | 2026-03-27 | 2026-02-01 |  | 2025-11-27 |  |  |  | 2026-03-23 |  | 2026-02-14 | 2026-02-10
VNPT-NE-0193 | Site 0193 Hà N | Hà Nam | PAT Complete | VNPT 4G Phase 10 | 5G | new | 20.358 | 105.9587 | 2026-03-15 | 2026-02-23 | 2025-12-02 | [5 empty] | 2026-03-01 | 2025-11-08 | 2026-01-10
VNPT-NE-0194 | Site 0194 Tây | Tây Ninh | Installation Complete | VNPT 4G Phase 10 | 5G | new | 11.8261 | 105.8541 |  | 2025-12-30 | 2026-04-02
VNPT-NE-0195 | Site 0195 Bình | Bình Dương | On Air Complete | VNPT 4G Phase 10 | 5G | new | 11.5259 | 106.3547 | 2026-01-09 | 2026-02-02 | 2025-11-12 | [5 empty] | 2026-02-04 |  | 2025-12-29 | 2026-03-22
VNPT-NE-0196 | Site 0196 Long | Long An | On Air Complete | VNPT 4G Phase 10 | 4G | new | 10.9308 | 106.1763 | 2026-03-27 |  | 2025-12-20 |  |  |  |  | 2025-11-27 | 2026-03-11 |  | 2025-10-25
VNPT-NE-0197 | Site 0197 Yên | Yên Bái | Installation Complete | VNPT 4G Phase 10 | 5G | new | 21.9316 | 104.3929 | 2025-11-09 | 2026-03-18 | 2026-01-26 | [6 empty] | 2026-01-14 | 2025-11-15
VNPT-NE-0198 | Site 0198 Phú | Phú Yên | On Air Complete | VNPT 4G Phase 10 | 4G | new | 13.1612 | 109.5971 | 2026-02-07 | 2025-12-21 | 2025-11-14 | [5 empty] | 2025-12-26 | 2026-01-11 | 2026-01-12 | 2026-01-22 | 2026-01-11
VNPT-NE-0199 | Site 0199 Hà G | Hà Giang | On Air Complete | VNPT 4G Phase 10 | 4G | new | 23.0577 | 105.3528 | 2026-03-28 | 2025-11-03 |  | 2025-12-11 | [6 empty] | 2026-03-13 | 2026-02-16
VNPT-NE-0200 | Site 0200 Cần | Cần Thơ | RFI Complete | VNPT 4G Phase 10 | 5G | new | 10.406 | 105.8268 | 2026-03-26 | 2025-11-03 | 2025-12-12 | [6 empty] | 2026-01-01
VNPT-EX-0201 | Site 0201 Hà N | Hà Nam | PAT Complete | VNPT 4G Phase 10 | 4G+5G | expansion | 20.8668 | 106.0316 | 2025-12-03 |  | 2026-04-05 | 2026-01-10 | 2026-03-26 |  |  |  | 2025-11-26 | 2025-12-06 | 2026-03-01 | 2026-01-23 | 2025-12-03
VNPT-EX-0202 | Site 0202 Bình | Bình Dương | PAT Complete | VNPT 4G Phase 10 | 4G | expansion | 10.7517 | 107.0972 | 2026-03-19 | 2025-11-28 |  | 2026-01-21 | 2025-10-25 |  |  | 2025-11-23 | 2025-11-01 |  | 2025-11-15 |  | 2025-11-23
VNPT-EX-0203 | Site 0203 Bình | Bình Phước | PAT Complete | VNPT 4G Phase 10 | 4G+5G | expansion | 12.1957 | 107.3758 | 2025-11-17 | 2026-01-19 | 2025-11-25 | 2026-04-03 | [5 empty] | 2026-01-19
VNPT-EX-0204 | Site 0204 Hà T | Hà Tĩnh | Installation Complete | VNPT 4G Phase 10 | 4G | expansion | 17.9068 | 105.6847 |  | 2026-02-01 | [8 empty] | 2026-04-04
VNPT-EX-0205 | Site 0205 Nam | Nam Định | Installation Complete | VNPT 4G Phase 10 | 4G | expansion | 19.6322 | 106.4645 | 2026-01-31 |  | 2026-02-18 | [6 empty] | 2025-12-19
VNPT-EX-0206 | Site 0206 Đồng | Đồng Tháp | PAT Complete | VNPT 4G Phase 10 | 5G | expansion | 10.5938 | 105.6252 | 2026-04-01 | 2025-12-16 | 2026-03-31 |  | 2026-01-26 |  |  |  |  | 2025-11-24 | 2026-03-31
VNPT-EX-0207 | Site 0207 Quản | Quảng Bình | On Air Complete | VNPT 4G Phase 10 | 4G | expansion | 17.69 | 106.7037 | 2025-10-27 | 2025-12-03 | 2025-11-12 | 2026-04-04 | [6 empty] | 2025-12-26 | 2025-11-10
VNPT-EX-0208 | Site 0208 Vĩnh | Vĩnh Phúc | On Air Complete | VNPT 4G Phase 10 | 4G | expansion | 20.7912 | 105.8062 | 2026-03-20 | 2026-01-02 |  | 2026-02-26 | [6 empty] | 2025-11-21
VNPT-EX-0209 | Site 0209 Quản | Quảng Trị | On Air Complete | VNPT 4G Phase 10 | 4G+5G | expansion | 16.5888 | 106.7807 |  |  | 2026-02-05 | 2025-12-05 |  |  |  |  | 2025-12-04 |  |  | 2025-11-11
VNPT-EX-0210 | Site 0210 An G | An Giang | On Air Complete | VNPT 4G Phase 10 | 4G | expansion | 10.0489 | 104.7483 | 2026-04-01 | 2026-04-02 | 2025-11-07 | 2026-01-28 |  |  |  |  | 2026-03-19 | 2025-12-25
VNPT-EX-0211 | Site 0211 Hưng | Hưng Yên | PAT Complete | VNPT 4G Phase 10 | 4G+5G | expansion | 20.5686 | 105.9789 | 2025-12-22 | 2026-03-25 | 2026-03-07 |  | 2025-11-07 |  |  |  | 2026-01-30 | 2025-12-26 | 2026-02-16 | 2025-10-31
VNPT-EX-0212 | Site 0212 Bình | Bình Phước | On Air Complete | VNPT 4G Phase 10 | 5G | expansion | 11.5539 | 106.5297 | 2025-11-28 | 2025-12-04 | 2026-02-23 | 2026-04-04 | [5 empty] | 2026-01-26
VNPT-EX-0213 | Site 0213 An G | An Giang | Installation Complete | VNPT 4G Phase 10 | 5G | expansion | 10.2012 | 104.8816 |  | 2025-12-02 | 2026-04-09 | 2026-02-25 |  |  |  |  | 2026-01-15 | 2025-11-16 |  | 2026-01-14
VNPT-EX-0214 | Site 0214 Tây | Tây Ninh | PAT Complete | VNPT 4G Phase 10 | 4G+5G | expansion | 11.684 | 106.014 | 2025-11-28 | 2026-01-20 | 2026-04-06 | 2026-03-03 |  |  |  |  | 2026-01-16 |  |  | 2026-04-03 | 2026-01-04
VNPT-EX-0215 | Site 0215 Quản | Quảng Trị | On Air Complete | VNPT 4G Phase 10 | 4G+5G | expansion | 17.0098 | 106.8715 | 2026-02-09 | 2026-01-23 | 2026-01-23 | [5 empty] | 2026-01-05 |  |  |  | 2025-12-08
VNPT-EX-0216 | Site 0216 T.T. | T.T. Huế | Installation Complete | VNPT 4G Phase 10 | 4G | expansion | 16.7221 | 107.938 | 2026-03-08 | 2026-04-01 | 2025-11-28 | [5 empty] | 2026-01-21 |  |  | 2025-12-12
VNPT-EX-0217 | Site 0217 Tuyê | Tuyên Quang | Installation Complete | VNPT 4G Phase 10 | 4G | expansion | 21.5866 | 105.2323 |  | 2026-01-31 | 2026-01-30 | [5 empty] | 2025-11-02 |  | 2025-11-23
VNPT-EX-0218 | Site 0218 Bình | Bình Thuận | RFI Complete | VNPT 4G Phase 10 | 4G | expansion | 11.0707 | 108.1755 | 2026-03-28 | 2025-12-31 | 2025-11-09
VNPT-EX-0219 | Site 0219 Đồng | Đồng Nai | Installation Complete | VNPT 4G Phase 10 | 5G | expansion | 11.0683 | 107.1556 | 2025-12-12 | 2026-02-12 | 2025-11-04 | [5 empty] | 2026-01-07 | 2025-10-22 | 2026-01-17 | 2025-12-10 | 2025-12-09
VNPT-EX-0220 | Site 0220 Hà N | Hà Nam | Installation Complete | VNPT 4G Phase 10 | 5G | expansion | 20.0709 | 105.8021 | 2025-11-10 | 2025-11-03 | 2026-03-01 | [6 empty] | 2026-01-13 | 2025-11-10
VNPT-EX-0221 | Site 0221 Đắk | Đắk Lắk | Installation Complete | VNPT 4G Phase 10 | 5G | expansion | 12.7629 | 108.2551 |  | 2025-12-28 | 2026-03-14 | [9 empty] | 2026-02-14
VNPT-EX-0222 | Site 0222 Ninh | Ninh Bình | On Air Complete | VNPT 4G Phase 10 | 4G+5G | expansion | 19.99 | 105.9779 | 2026-01-19 | 2026-01-23
VNPT-EX-0223 | Site 0223 Hà N | Hà Nội | On Air Complete | VNPT 4G Phase 10 | 4G+5G | expansion | 20.6097 | 105.5822 | 2025-12-21 | 2025-12-31 | 2026-01-03 | 2026-01-02 |  |  |  |  | 2025-12-20 | 2025-10-23 | 2026-03-06
VNPT-EX-0224 | Site 0224 Ninh | Ninh Bình | On Air Complete | VNPT 4G Phase 10 | 4G+5G | expansion | 20.2579 | 106.375 | 2026-03-06 | 2025-12-25
VNPT-EX-0225 | Site 0225 Than | Thanh Hóa | On Air Complete | VNPT 4G Phase 10 | 4G+5G | expansion | 19.7108 | 105.8462 | 2026-04-01 | 2026-01-06 | 2025-12-08 |  | 2025-11-05 |  |  |  |  | 2025-11-27
VNPT-EX-0226 | Site 0226 An G | An Giang | On Air Complete | VNPT 4G Phase 10 | 5G | expansion | 10.3125 | 104.6528 | 2026-04-08 | 2025-11-30 | [6 empty] | 2026-01-16 | 2026-01-25 | 2026-04-01
VNPT-EX-0227 | Site 0227 Quản | Quảng Bình | PAT Complete | VNPT 4G Phase 10 | 5G | expansion | 17.0273 | 106.2848 | 2026-03-22 | 2026-01-29 | 2025-11-04 |  |  |  |  | 2026-02-09 | 2026-02-04 | 2026-03-13
VNPT-EX-0228 | Site 0228 Hưng | Hưng Yên | PAT Complete | VNPT 4G Phase 10 | 5G | expansion | 21.1339 | 105.7542 | 2025-12-26 | 2026-02-09 | 2025-10-29 | 2026-03-12 |  |  |  |  | 2025-11-14 |  | 2025-10-28 | 2025-12-13
VNPT-EX-0229 | Site 0229 Gia | Gia Lai | Installation Complete | VNPT 4G Phase 10 | 5G | expansion | 14.1703 | 107.7119 |  | 2026-01-20 | [7 empty] | 2025-11-25
VNPT-EX-0230 | Site 0230 Kiên | Kiên Giang | On Air Complete | VNPT 4G Phase 10 | 5G | expansion | 10.1719 | 104.8705 | 2026-02-23 | 2026-04-08 | 2026-03-24 | 2026-04-02 |  |  |  |  | 2026-03-16 | 2025-12-17 | 2026-01-28 | 2026-03-18 | 2025-11-09
VNPT-EX-0231 | Site 0231 Long | Long An | Installation Complete | VNPT 4G Phase 10 | 5G | expansion | 10.9639 | 106.2479 |  | 2026-03-13 | [6 empty] | 2025-12-12 |  | 2025-12-15
VNPT-EX-0232 | Site 0232 Bình | Bình Định | On Air Complete | VNPT 4G Phase 10 | 4G | expansion | 13.8582 | 109.2128 | 2026-03-24 | 2026-02-18 | 2026-02-24 | 2025-10-28 | 2026-03-23 |  |  | 2026-02-05 |  | 2025-11-23 |  | 2025-12-18
VNPT-EX-0233 | Site 0233 Hà N | Hà Nội | PAT Complete | VNPT 4G Phase 10 | 5G | expansion | 20.8905 | 105.4516 | 2025-12-31 | 2025-11-30 | 2025-12-06 |  | 2025-11-24 |  |  |  | 2025-12-28 |  |  |  | 2025-12-08
VNPT-EX-0234 | Site 0234 Tiền | Tiền Giang | RFI Complete | VNPT 4G Phase 10 | 5G | expansion | 10.7533 | 106.1401 |  |  | 2026-02-18 | [5 empty] | 2026-03-31
VNPT-EX-0235 | Site 0235 Hải | Hải Phòng | On Air Complete | VNPT 4G Phase 10 | 5G | expansion | 20.5385 | 106.5888 | 2025-10-28 | 2025-11-25 |  | 2026-03-31 | [6 empty] | 2026-01-14 |  | 2025-10-25
VNPT-EX-0236 | Site 0236 Hải | Hải Dương | RFI Complete | VNPT 4G Phase 10 | 4G | expansion | 20.8889 | 105.8191 |  |  | 2025-10-26 | [5 empty] | 2026-02-25
VNPT-EX-0237 | Site 0237 Hải | Hải Dương | PAT Complete | VNPT 4G Phase 10 | 4G+5G | expansion | 20.7373 | 106.6359 | 2025-12-29 | 2025-11-14 | 2026-01-18 |  | 2026-01-06 | [6 empty] | 2026-03-11 | 2025-12-25
VNPT-EX-0238 | Site 0238 An G | An Giang | On Air Complete | VNPT 4G Phase 10 | 4G | expansion | 10.0156 | 105.087 | 2026-02-24 |  | 2025-11-10 | 2025-10-29 | [5 empty] | 2025-12-10 |  | 2025-12-16
VNPT-EX-0239 | Site 0239 An G | An Giang | PAT Complete | VNPT 4G Phase 10 | 4G+5G | expansion | 10.3479 | 104.6046 | 2026-03-11 | [7 empty] | 2025-11-23 | 2025-12-13 |  | 2026-02-20 | 2026-03-03
VNPT-EX-0240 | Site 0240 Tiền | Tiền Giang | On Air Complete | VNPT 4G Phase 10 | 4G | expansion | 10.3347 | 106.1343 | 2025-12-15 | 2026-03-28 | [6 empty] | 2026-04-03 | 2026-03-12 | 2026-02-09
VNPT-EX-0241 | Site 0241 Khán | Khánh Hòa | PAT Complete | VNPT 4G Phase 10 | 4G+5G | expansion | 12.5914 | 108.5735 | 2026-03-28 | 2026-03-04 | 2025-11-05 |  | 2025-11-16 | 2025-12-12 |  | 2026-03-07 | 2026-01-01 | 2025-12-14 |  |  | 2026-03-09
VNPT-EX-0242 | Site 0242 Quản | Quảng Bình | On Air Complete | VNPT 4G Phase 10 | 5G | expansion | 17.9528 | 106.7056 | 2025-11-20 |  | 2025-11-28 | 2025-12-22 |  |  |  |  | 2026-02-14
VNPT-EX-0243 | Site 0243 Hà N | Hà Nội | On Air Complete | VNPT 4G Phase 10 | 4G | expansion | 20.5401 | 105.7707 | 2026-04-02 | 2025-12-31 | 2026-03-16 | [5 empty] | 2026-02-08 | 2026-04-07 |  | 2026-01-09
VNPT-EX-0244 | Site 0244 Hồ C | Hồ Chí Minh | RFI Complete | VNPT 4G Phase 10 | 4G+5G | expansion | 10.6638 | 106.3386 |  | 2026-01-06 | [7 empty] | 2025-11-01 | 2026-01-15
VNPT-EX-0245 | Site 0245 Đà N | Đà Nẵng | On Air Complete | VNPT 4G Phase 10 | 4G | expansion | 16.1147 | 108.61 | 2026-03-28 | 2026-01-07 | 2026-03-31 | [5 empty] | 2026-02-25 |  |  |  | 2026-01-15
VNPT-EX-0246 | Site 0246 Tuyê | Tuyên Quang | PAT Complete | VNPT 4G Phase 10 | 4G | expansion | 21.6205 | 105.5979 | 2025-12-23 | 2026-03-25 | 2025-12-16 | [5 empty] | 2025-11-27 |  | 2025-11-25 |  | 2025-11-03
VNPT-EX-0247 | Site 0247 Kon | Kon Tum | RFI Complete | VNPT 4G Phase 10 | 4G+5G | expansion | 14.8979 | 107.4884 |  | 2026-01-30 | 2026-03-04
VNPT-EX-0248 | Site 0248 Hải | Hải Dương | RFI Complete | VNPT 4G Phase 10 | 4G | expansion | 21.2349 | 106.3196 | 2025-11-13 | 2025-10-27
VNPT-EX-0249 | Site 0249 Bắc | Bắc Ninh | Installation Complete | VNPT 4G Phase 10 | 4G+5G | expansion | 21.0559 | 105.7664 |  |  | 2026-02-25 | 2026-02-09 | [7 empty] | 2026-01-19
VNPT-EX-0250 | Site 0250 Ninh | Ninh Bình | On Air Complete | VNPT 4G Phase 10 | 5G | expansion | 20.5755 | 105.9336 | 2026-04-04 | 2025-12-04 | [8 empty] | 2025-11-22
VNPT-EX-0251 | Site 0251 Đồng | Đồng Nai | On Air Complete | VNPT 4G Phase 10 | 4G+5G | expansion | 10.9387 | 106.8123 | 2026-03-31 | 2025-11-20 | 2026-04-04 | [5 empty] | 2026-02-13 | 2026-03-18 | 2025-11-06 |  | 2026-01-29
VNPT-EX-0252 | Site 0252 Phú | Phú Yên | Installation Complete | VNPT 4G Phase 10 | 4G+5G | expansion | 13.2032 | 109.1116 | 2025-10-22 | 2026-03-04 | [6 empty] | 2026-01-02 | 2026-01-28 | 2026-01-22 |  | 2025-12-18
VNPT-EX-0253 | Site 0253 Khán | Khánh Hòa | Installation Complete | VNPT 4G Phase 10 | 5G | expansion | 12.2979 | 108.6436 | 2025-11-27 |  | 2025-11-10 | 2026-02-25 | [5 empty] | 2025-12-27
VNPT-EX-0254 | Site 0254 Quản | Quảng Trị | PAT Complete | VNPT 4G Phase 10 | 4G+5G | expansion | 16.7941 | 107.3399 | 2026-04-10 | 2026-01-24 |  | 2026-02-24 | 2026-03-11 |  |  |  |  | 2025-10-25
VNPT-EX-0255 | Site 0255 Gia | Gia Lai | On Air Complete | VNPT 4G Phase 10 | 4G+5G | expansion | 13.928 | 108.176 | 2026-03-11 | 2025-11-14 | 2026-02-03 | 2026-02-28 |  |  |  |  | 2026-03-27 | 2025-12-13 |  | 2026-01-08
VNPT-EX-0256 | Site 0256 An G | An Giang | Installation Complete | VNPT 4G Phase 10 | 4G | expansion | 10.5988 | 104.7671 | 2026-01-20 |  |  | 2025-11-29 |  |  |  |  | 2026-01-08 | 2025-11-13 | 2026-03-05
VNPT-EX-0257 | Site 0257 Bình | Bình Dương | On Air Complete | VNPT 4G Phase 10 | 5G | expansion | 11.4461 | 106.9125 | 2026-03-12 | 2026-03-22 | 2026-03-08 | 2025-12-18 | [5 empty] | 2026-01-21
VNPT-EX-0258 | Site 0258 Ninh | Ninh Bình | On Air Complete | VNPT 4G Phase 10 | 4G+5G | expansion | 19.7253 | 105.5302 | 2026-03-13 | 2025-12-08 |  | 2026-03-11 |  |  |  |  | 2026-03-14 | 2025-10-24 |  |  | 2026-01-23
VNPT-EX-0259 | Site 0259 Lào | Lào Cai | On Air Complete | VNPT 4G Phase 10 | 4G | expansion | 21.8908 | 104.1459 |  |  | 2026-02-28 | [8 empty] | 2025-11-13
VNPT-EX-0260 | Site 0260 Hà N | Hà Nam | PAT Complete | VNPT 4G Phase 10 | 5G | expansion | 20.8513 | 105.9747 | 2026-02-22 | 2026-03-14 | 2026-01-10 | [6 empty] | 2025-11-30 | 2026-03-13 | 2025-12-12 | 2026-03-07

## ISSUES
week | raised | closed | open
W03 | 10 | 7 | 3
W04 | 11 | 12 | 2
W05 | 15 | 7 | 10
W06 | 14 | 16 | 8
W07 | 11 | 6 | 13
W08 | 12 | 9 | 16
W09 | 8 | 16 | 8
W10 | 10 | 6 | 12
W11 | 17 | 4 | 25
W12 | 18 | 16 | 27
W13 | 16 | 10 | 33
W14 | 14 | 8 | 39
W15 | 6 | 3 | 42
W16 | 14 | 10 | 46

## RESOURCES
week | project | install | ssv | onair | mw | power | optim | total | total_plan
W03 |  | 18 |  |  | 14 | 24 | 13 | 45
W04 |  | 18 |  |  | 10 | 22 | 11 | 77
W05 |  | 18 |  |  | 19 | 15 | 6 | 63
W06 |  | 21 |  |  | 13 | 16 | 14 | 65
W07 |  | 18 |  |  | 11 | 23 | 12 | 57
W08 |  | 33 |  |  | 17 | 18 | 15 | 65
W09 |  | 26 |  |  | 15 | 22 | 12 | 72
W10 |  | 23 |  |  | 10 | 24 | 6 | 47
W11 |  | 23 |  |  | 15 | 25 | 8 | 80
W12 |  | 19 |  |  | 8 | 13 | 5 | 44
W13 |  | 30 |  |  | 18 | 10 | 7 | 64
W14 |  | 34 |  |  | 18 | 20 | 7 | 59
W15 |  | 34 |  |  | 17 | 13 | 6 | 73
W16 |  | 30 |  |  | 20 | 24 | 8 | 58

## RISKS
risk_name | priority | description | owner | resolve_date | current_status | next_steps | project