## PROJECT_LIST
id | name | active | color | region
VNPT 4G P9-2 | VNPT 4G P9-2 | TRUE | #1d4ed8 | Central

## CONFIG
key | value
project_name | VNPT 4G P9-2
client | VNPT
start_date | 46082
end_date | 46265
region | Central
pm | Dung
weekly_target | 24
target_onair | 260 sites

## DATA
site_name | province | site_type | build_type | lat | lng | RFI | TSS | TSSR | MOS | Installation | On Air | PAT
1 | HUE | 4G | new |  |  | done | done | done | done | done | done
2 | HUE | 4G | new |  |  | done | done | done | done | done | done
3 | HUE | 4G | new |  |  | done | done | done | done | done | done
4 | HUE | 4G | new |  |  | done | done | done | done | done | done
5 | HUE | 4G | new |  |  | done | done | done | done | done | done
6 | HUE | 4G | new |  |  | done | done | done | done | done | done
7 | HUE | 4G | new |  |  | done | done | done | done | done | done
8 | HUE | 4G | new |  |  | done | done | done | done | done | done
9 | HUE | 4G | new |  |  | done | done | done | done | done | done
10 | HUE | 4G | new |  |  | done | done | done | done | done | done
11 | HUE | 4G | new |  |  | done | done | done | done | done | done
12 | HUE | 4G | new |  |  | done | done | done | done | done | done
13 | HUE | 4G | new |  |  | done | done | done | done | done | done
14 | HUE | 4G | new |  |  | done | done | done | done | done | done
15 | HUE | 4G | new |  |  | done | done | done | done | done | done
16 | HUE | 4G | new |  |  | done | done | done | done | done | done
17 | HUE | 4G | new |  |  | done | done | done | done | done | done
18 | HUE | 4G | new |  |  | done | done | done | done | done | done
19 | HUE | 4G | new |  |  | done | done | done | done | done | done
20 | HUE | 4G | new |  |  | done | done | done | done | done | done
21 | HUE | 4G | new |  |  | done | done | done | done | done | done
22 | HUE | 4G | new |  |  | done | done | done | done | done | done
23 | HUE | 4G | new |  |  | done | done | done | done | done | done
24 | Quang Binh | 4G | new |  |  | done | done | done | done | done | done
25 | Quang Binh | 4G | new |  |  | done | done | done | done | done | done
26 | Quang Binh | 4G | new |  |  | done | done | done | done | done | done
27 | Quang Binh | 4G | new |  |  | done | done | done | done | done | done
28 | Quang Binh | 4G | new |  |  | done | done | done | done | done | done
29 | Quang Binh | 4G | new |  |  | done | done | done | done | done | done
30 | Quang Binh | 4G | new |  |  | done | done | done | done | done | done
31 | Quang Binh | 4G | new |  |  | done | done | done | done | done | done
32 | Quang Binh | 4G | new |  |  | done | done | done | done | done | done
33 | Quang Binh | 4G | new |  |  | done | done | done | done | done | done
34 | Quang Binh | 4G | new |  |  | done | done | done | done | done | done
35 | Quang Binh | 4G | new |  |  | done | done | done | done | done | done
36 | Quang Binh | 4G | new |  |  | done | done | done | done | done | done
37 | Quang Binh | 4G | new |  |  | done | done | done | done | done | done
38 | Quang Binh | 4G | new |  |  | done | done | done | done | done | done
39 | Quang Binh | 4G | new |  |  | done | done | done | done | done | done
40 | Quang Binh | 4G | new |  |  | done | done | done | done | done | done
41 | Quang Binh | 4G | new |  |  | done | done | done | done | done | done
42 | Quang Binh | 4G | new |  |  | done | done | done | done | done | done
43 | Quang Binh | 4G | new |  |  | done | done | done | done | done | done
44 | Quang Binh | 4G | new |  |  | done | done | done | done | done | done
45 | Quang Binh | 4G | new |  |  | done | done | done | done | done | done
46 | Quang Binh | 4G | new |  |  | done | done | done | done | done | done
47 | Quang Binh | 4G | new |  |  | done | done | done | done | done | done
48 | Quang Binh | 4G | new |  |  | done | done | done | done | done | done
49 | Quang Binh | 4G | new |  |  | done | done | done | done | done | done
50 | Quang Binh | 4G | new |  |  | done | done | done | done | done | done
51 | Quang Binh | 4G | new |  |  | done | done | done | done | done | done
52 | Quang Binh | 4G | new |  |  | done | done | done | done | done | done
53 | Quang Binh | 4G | new |  |  | done | done | done | done | done | done
54 | Quang Binh | 4G | new |  |  | done | done | done | done | done | done
55 | Quang Binh | 4G | new |  |  | done | done | done | done | done | done
56 | Quang Binh | 4G | new |  |  | done | done | done | done | done | done
57 | Quang Binh | 4G | new |  |  | done | done | done | done | done | done
58 | Quang Binh | 4G | new |  |  | done | done | done | done | done | done
59 | Quang Binh | 4G | new |  |  | done | done | done | done | done | done
60 | Quang Binh | 4G | new |  |  | done | done | done | done | done | done
61 | Quang Binh | 4G | new |  |  | done | done | done | done | done | done
62 | Quang Binh | 4G | new |  |  | done | done | done | done | done | done
63 | Quang Binh | 4G | new |  |  | done | done | done | done | done | done
64 | Quang Binh | 4G | new |  |  | done | done | done | done | done | done
65 | Quang Binh | 4G | new |  |  | done | done | done | done | done | done
66 | Quang Binh | 4G | new |  |  | done | done | done | done | done | done
67 | Quang Binh | 4G | new |  |  | done | done | done | done | done | done
68 | Quang Binh | 4G | new |  |  | done | done | done | done | done | done
69 | Quang Nam | 4G | new |  |  | done | done | done | done | done | done
70 | Quang Nam | 4G | new |  |  | done | done | done | done | done | done
71 | Quang Nam | 4G | new |  |  | done | done | done | done | done | done
72 | Quang Nam | 4G | new |  |  | done | done | done | done | done | done
73 | Quang Nam | 4G | new |  |  | done | done | done | done | done | done
74 | Quang Nam | 4G | new |  |  | done | done | done | done | done | done
75 | Quang Nam | 4G | new |  |  | done | done | done | done | done | done
76 | Quang Nam | 4G | new |  |  | done | done | done | done | done | done
77 | Quang Nam | 4G | new |  |  | done | done | done | done | done | done
78 | Quang Nam | 4G | new |  |  | done | done | done | done | done | done
79 | Quang Nam | 4G | new |  |  | done | done | done | done | done | done
80 | Quang Nam | 4G | new |  |  | done | done | done | done | done | done
81 | Quang Nam | 4G | new |  |  | done | done | done | done | done | done
82 | Quang Nam | 4G | new |  |  | done | done | done | done | done | done
83 | Quang Nam | 4G | new |  |  | done | done | done | done | done | done
84 | Quang Nam | 4G | new |  |  | done | done | done | done | done | done
85 | Quang Nam | 4G | new |  |  | done | done | done | done | done | done
86 | Quang Nam | 4G | new |  |  | done | done | done | done | done | done
87 | Quang Nam | 4G | new |  |  | done | done | done | done | done | done
88 | Quang Nam | 4G | new |  |  | done | done | done | done | done | done
89 | Quang Tri | 4G | new |  |  | done | done | done | done | done | done
90 | Quang Tri | 4G | new |  |  | done | done | done | done | done | done
91 | Quang Tri | 4G | new |  |  | done | done | done | done | done | done
92 | Quang Tri | 4G | new |  |  | done | done | done | done | done | done
93 | Quang Tri | 4G | new |  |  | done | done | done | done | done | done
94 | Quang Tri | 4G | new |  |  | done | done | done | done | done | done
95 | Quang Tri | 4G | new |  |  | done | done | done | done | done | done
96 | Quang Tri | 4G | new |  |  | done | done | done | done | done | done
97 | Quang Tri | 4G | new |  |  | done | done | done | done | done | done
98 | Quang Tri | 4G | new |  |  | done | done | done | done | done | done
99 | Quang Tri | 4G | new |  |  | done | done | done | done | done | done
100 | Quang Tri | 4G | new |  |  | done | done | done | done | done | done
101 | Quang Tri | 4G | new |  |  | done | done | done | done | done | done
102 | Quang Tri | 4G | new |  |  | done | done | done | done | done | done
103 | Quang Tri | 4G | new |  |  | done | done | done | done | done | done
104 | Quang Tri | 4G | new |  |  | done | done | done | done | done | done
105 | Quang Tri | 4G | new |  |  | done | done | done | done | done | done
106 | Quang Tri | 4G | new |  |  | done | done | done | done | done | done
107 | Quang Tri | 4G | new |  |  | done | done | done | done | done | done
108 | Quang Tri | 4G | new |  |  | done | done | done | done | done | done
109 | Quang Tri | 4G | new |  |  | done | done | done | done | done | done
110 | Quang Tri | 4G | new |  |  | done | done | done | done | done | done
111 | Quang Tri | 4G | new |  |  | done | done | done | done | done | done
112 | Quang Tri | 4G | new |  |  | done | done | done | done | done | done
113 | Quang Tri | 4G | new |  |  | done | done | done | done | done | done
114 | Quang Tri | 4G | new |  |  | done | done | done | done | done | done
115 | Quang Tri | 4G | new |  |  | done | done | done | done | done | done
116 | Quang Tri | 4G | new |  |  | done | done | done | done | done | done
117 | Quang Tri | 4G | new |  |  | done | done | done | done | done | done
118 | Quang Tri | 4G | new |  |  | done | done | done | done | done | done
119 | Quang Tri | 4G | new |  |  | done | done | done | done | done | done
120 | Quang Tri | 4G | new |  |  | done | done | done | done | done | done
121 | Quang Tri | 4G | new |  |  | done | done | done | done | done | done
122 | Quang Tri | 4G | new |  |  | done | done | done | done | done | done
123 | Quang Tri | 4G | new |  |  | done | done | done | done | done | done
124 | Quang Tri | 4G | new |  |  | done | done | done | done | done | done
125 | Quang Tri | 4G | new |  |  | done | done | done | done | done | done
126 | Quang Tri | 4G | new |  |  | done | done | done | done | done | done
127 | Quang Tri | 4G | new |  |  | done | done | done | done | done | done
128 | Quang Tri | 4G | new |  |  | done | done | done | done | done | done
129 | Quang Tri | 4G | new |  |  | done | done | done | done | done | done
130 | Quang Tri | 4G | new |  |  | done | done | done | done | done | done
131 | Quang Tri | 4G | new |  |  | done | done | done | done | done | done
132 | Quang Tri | 4G | new |  |  | done | done | done | done | done | done
133 | Quang Tri | 4G | new |  |  | done | done | done | done | done | done
134 | Quang Tri | 4G | new |  |  | done | done | done | done | done | done
135 | Quang Tri | 4G | new |  |  | done | done | done | done | done | done
136 | Quang Tri | 4G | new |  |  | done | done | done | done | done | done
137 | Quang Tri | 4G | new |  |  | done | done | done | done | done | done
138 | Quang Tri | 4G | new |  |  | done | done | done | done | done | done
139 | Quang Tri | 4G | new |  |  | done | done | done | done | done | done
140 | Quang Tri | 4G | new |  |  | done | done | done | done | done | done
141 | Quang Tri | 4G | new |  |  | done | done | done | done | done | done
142 | Quang Tri | 4G | new |  |  | done | done | done | done | done | done
143 | Quang Tri | 4G | new |  |  | done | done | done | done | done | done
144 | Quang Tri | 4G | new |  |  | done | done | done | done | done | done
145 | Quang Tri | 4G | new |  |  | done | done | done | done | done | done
146 | Quang Tri | 4G | new |  |  | done | done | done | done | done | done
147 | Quang Tri | 4G | new |  |  | done | done | done | done | done | done
148 | Quang Tri | 4G | new |  |  | done | done | done | done | done | done
149 | Quang Tri | 4G | new |  |  | done | done | done | done | done | done
150 | Quang Tri | 4G | new |  |  | done | done | done | done | done | done
151 | Quang Tri | 4G | new |  |  | done | done | done | done | done | done
152 | Quang Tri | 4G | new |  |  | done | done | done | done | done | done
153 | Quang Tri | 4G | new |  |  | done | done | done | done | done | done
154 | Da Nang | 4G | new |  |  | done | done | done | done | done | done
155 | Da Nang | 4G | new |  |  | done | done | done | done | done | done
156 | Da Nang | 4G | new |  |  | done | done | done | done | done | done
157 | Da Nang | 4G | new |  |  | done | done | done | done | done | done
158 | Da Nang | 4G | new |  |  | done | done | done | done | done | done
159 | Da Nang | 4G | new |  |  | done | done | done | done | done | done
160 | Da Nang | 4G | new |  |  | done | done | done | done | done | done
161 | Da Nang | 4G | new
162 | Da Nang | 4G | new
163 | Da Nang | 4G | new
164 | Da Nang | 4G | new
165 | Da Nang | 4G | new
166 | Da Nang | 4G | new
167 | Da Nang | 4G | new
168 | Da Nang | 4G | new
169 | Da Nang | 4G | new
170 | Da Nang | 4G | new
171 | Da Nang | 4G | new
172 | Da Nang | 4G | new
173 | Da Nang | 4G | new
174 | Da Nang | 4G | new
175 | Da Nang | 4G | new
176 | Da Nang | 4G | new
177 | Da Nang | 4G | new
178 | Da Nang | 4G | new
179 | Da Nang | 4G | new
180 | Da Nang | 4G | new
181 | Da Nang | 4G | new
182 | Da Nang | 4G | new
183 | Da Nang | 4G | new
184 | Da Nang | 4G | new
185 | Da Nang | 4G | new
186 | Da Nang | 4G | new
187 | Da Nang | 4G | new
188 | Da Nang | 4G | new
189 | Da Nang | 4G | new
190 | Da Nang | 4G | new
191 | Da Nang | 4G | new
192 | Da Nang | 4G | new
193 | Da Nang | 4G | new
194 | Da Nang | 4G | new
195 | Da Nang | 4G | new
196 | Da Nang | 4G | new
197 | Da Nang | 4G | new
198 | Da Nang | 4G | new
199 | Da Nang | 4G | new
200 | Da Nang | 4G | new
201 | Da Nang | 4G | expansion
202 | Da Nang | 4G | expansion
203 | Da Nang | 4G | expansion
204 | Da Nang | 4G | expansion
205 | Da Nang | 4G | expansion
206 | Da Nang | 4G | expansion
207 | Da Nang | 4G | expansion
208 | Da Nang | 4G | expansion
209 | Da Nang | 4G | expansion
210 | Da Nang | 4G | expansion
211 | Da Nang | 4G | expansion
212 | Da Nang | 4G | expansion
213 | Da Nang | 4G | expansion
214 | Da Nang | 4G | expansion
215 | Da Nang | 4G | expansion
216 | Da Nang | 4G | expansion
217 | Da Nang | 4G | expansion
218 | Da Nang | 4G | expansion
219 | Da Nang | 4G | expansion
220 | Da Nang | 4G | expansion
221 | Da Nang | 4G | expansion
222 | Da Nang | 4G | expansion
223 | Da Nang | 4G | expansion
224 | Da Nang | 4G | expansion
225 | Da Nang | 4G | expansion
226 | Da Nang | 4G | expansion
227 | Da Nang | 4G | expansion
228 | Da Nang | 4G | expansion
229 | Da Nang | 4G | expansion
230 | Da Nang | 4G | expansion
231 | Da Nang | 4G | expansion
232 | Da Nang | 4G | expansion
233 | Da Nang | 4G | expansion
234 | Da Nang | 4G | expansion
235 | Da Nang | 4G | expansion
236 | Da Nang | 4G | expansion
237 | Da Nang | 4G | expansion
238 | Da Nang | 4G | expansion
239 | Da Nang | 4G | expansion
240 | Da Nang | 4G | expansion
241 | Da Nang | 4G | expansion
242 | Da Nang | 4G | expansion
243 | Da Nang | 4G | expansion
244 | Da Nang | 4G | expansion
245 | Da Nang | 4G | expansion
246 | Da Nang | 4G | expansion
247 | Da Nang | 4G | expansion
248 | Da Nang | 4G | expansion
249 | Da Nang | 4G | expansion
250 | Da Nang | 4G | expansion
251 | Da Nang | 4G | expansion
252 | Da Nang | 4G | expansion
253 | Da Nang | 4G | expansion
254 | Da Nang | 4G | expansion
255 | Da Nang | 4G | expansion
256 | Da Nang | 4G | expansion
257 | Da Nang | 4G | expansion
258 | Da Nang | 4G | expansion
259 | Da Nang | 4G | expansion
260 | Da Nang | 4G | expansion

## ISSUES
week | raised | closed | open
W01 | 5 | 3 | 2
W02 | 5 | 3 | 2
W03 | 5 | 3 | 2
W04 | 5 | 3 | 2
W05 | 5 | 3 | 2
W06 | 5 | 3 | 2
W07 | 5 | 3 | 2
W08 | 5 | 3 | 2
W09 | 5 | 3 | 2
W10 | 5 | 3 | 2
W11 | 5 | 3 | 2
W12 | 5 | 3 | 2
W13 | 5 | 3 | 2
W14 | 5 | 3 | 2
W15 | 5 | 3 | 2
W16 | 5 | 3 | 2
W17 | 5 | 3 | 2
W18 | 6 | 3 | 3
W19
W20
W21
W22
W23
W24

## RESOURCES
week | TSSR | install | ssv | onair | optim | total | total_plan
W01 | 10 | 0 | 0 | 0 | 0 | 0 | 10
W02 | 10 | 5 | 3 | 3 | 3 | 14 | 10
W03 | 10 | 5 | 3 | 3 | 3 | 14 | 10
W04 | 10 | 7 | 3 | 3 | 3 | 16 | 10
W05 | 10 | 7 | 3 | 3 | 3 | 16 | 10
W06 | 10 | 7 | 3 | 3 | 3 | 16 | 10
W07 |  | 7 | 3 | 3 | 3 | 16 | 12
W08 |  | 7 | 3 | 3 | 3 | 16 | 12
W09 |  | 7 | 3 | 3 | 3 | 16 | 12
W10 |  | 7 | 3 | 3 | 3 | 16 | 12
W11 |  | 7 | 3 | 3 | 3 | 16 | 12
W12 |  | 7 | 3 | 3 | 3 | 16 | 12
W13 |  | 7 | 3 | 3 | 3 | 16 | 12
W14 |  | 7 | 3 | 3 | 3 | 16 | 12
W15 |  | 7 | 3 | 3 | 3 | 16 | 12
W16 |  | 7 | 3 | 3 | 3 | 16 | 12
W17 |  | 7 | 3 | 3 | 3 | 16 | 12
W18 |  | 7 | 3 | 3 | 3 | 16 | 12
W19 | [5 empty] | 0 | 14
W20 | [5 empty] | 0 | 14
W21 | [5 empty] | 0 | 14
W22 | [5 empty] | 0 | 14
W23 | [5 empty] | 0 | 14
W24 | [5 empty] | 0

## RISKS
risk_name | priority | description | owner | resolve_date | current_status | next_steps

## VNPT 4G P9-3_ROLLING_PLAN
week | tss_plan | tssr_plan | rfi_plan | install_plan | onair_plan | ssv_plan | pat_plan
W01 | 30
W02 | 80 | 30
W03 | 130 | 80
W04 | 180 | 130
W05 | 230 | 180
W06 | 260 | 230 | 180
W07 |  | 260 | 230
W08 |  |  | 260 | 30
W09 |  |  |  | 60 | 30
W10 |  |  |  | 90 | 60 | 30
W11 |  |  |  | 120 | 90 | 60 | 30
W12 |  |  |  | 150 | 120 | 90 | 60
W13 |  |  |  | 180 | 150 | 120 | 90
W14 |  |  |  | 230 | 180 | 150 | 120
W15 |  |  |  | 260 | 230 | 180 | 150
W16 |  |  |  |  | 260 | 230 | 180
W17 | [5 empty] | 260 | 230
W18 | [6 empty] | 260
W19
W20
W21
W22
W23
W24