## PROJECT_LIST
id | name | active | color | region
VNPT 4G P9-3 | VNPT 4G P9-3 | TRUE | #1d4ed8 | Central

## CONFIG
key | value
project_name | VNPT 4G P9-3
client | VNPT
start_date | 46082
end_date | 46265
region | Central
pm | Duy Dung
weekly_target | 24
target_onair | 260 sites

## DATA
site_name | province | site_type | build_type | Total sites | RFI | TSS | MOS | Installation | On Air | PAT
1 | HUE | 4G | new | 60 | 30 | 30 | 30 | 30 | 30 | 15
2 | Quang Binh | 4G | new | 40 | 20 | 20 | 20 | 20 | 20 | 15
3 | Quang Nam | 4G | new | 20 | 10 | 10 | 10 | 10 | 10 | 6
4 | Quang Tri | 4G | new | 30 | 20 | 20 | 20 | 20 | 20 | 10
5 | Da Nang | 4G | new | 50 | 20 | 20 | 20 | 20 | 20 | 10
6 | Da Nang | 4G | expansion | 60 | 60 | 60 | 60 | 60 | 60 | 30

## ISSUES
week | raised | closed | open
W01 | 5 | 3 | 2
W02 | 5 | 3 | 2
W03 | 5 | 3 | 2
W04 | 5 | 3 | 2
W05 | 5 | 3 | 2
W06 | 5 | 3 | 2
W07 | 5 | 3 | 2
W08 | 5 | 3 | 2
W09 | 5 | 3 | 2
W10 | 5 | 3 | 2
W11 | 5 | 3 | 2
W12 | 5 | 3 | 2
W13 | 5 | 3 | 2
W14 | 5 | 3 | 2
W15 | 5 | 3 | 2
W16 | 5 | 3 | 2
W17 | 5 | 3 | 2
W18 | 7 | 3 | 4
W19
W20
W21
W22
W23
W24

## RESOURCES
week | install | ssv | onair | optim | total | total_plan
W01 | 0 | 0 | 0 | 0 | 0 | 10
W02 | 5 | 3 | 3 | 3 | 14 | 10
W03 | 5 | 3 | 3 | 3 | 14 | 10
W04 | 7 | 3 | 3 | 3 | 16 | 10
W05 | 7 | 3 | 3 | 3 | 16 | 10
W06 | 7 | 3 | 3 | 3 | 16 | 10
W07 | 7 | 3 | 3 | 3 | 16 | 12
W08 | 7 | 3 | 3 | 3 | 16 | 12
W09 | 7 | 3 | 3 | 3 | 16 | 12
W10 | 7 | 3 | 3 | 3 | 16 | 12
W11 | 7 | 3 | 3 | 3 | 16 | 12
W12 | 7 | 3 | 3 | 3 | 16 | 12
W13 | 7 | 3 | 3 | 3 | 16 | 12
W14 | 7 | 3 | 3 | 3 | 16 | 12
W15 | 7 | 3 | 3 | 3 | 16 | 12
W16 | 7 | 3 | 3 | 3 | 16 | 12
W17 | 7 | 3 | 3 | 3 | 16 | 12
W18 | 7 | 3 | 3 | 3 | 16 | 12
W19 |  |  |  |  | 0 | 14
W20 |  |  |  |  | 0 | 14
W21 |  |  |  |  | 0 | 14
W22 |  |  |  |  | 0 | 14
W23 |  |  |  |  | 0 | 14
W24 |  |  |  |  | 0

## RISKS
risk_name | priority | description | owner | resolve_date | current_status | next_steps
Site RFI | HIGH | 100 sites RFI progress get stuck | VNPT NET3 | 2026-05-31 | Delay | push VNPT to finish all sites RFI
Site Transmission | Medium | some site transmission lacking | VNPT NOC3 | 5/31/2026 | Delay | push to finish tranmission line
Manpower | Low | After 100 site RFI finished, project need speed up by increaing more manpower | ZTE Project | 2026-10-06 | Normal | Prepare for the resource to speed up site on air

## VNPT 4G P9-3_ROLLING_PLAN
week | tss_plan | rfi_plan | install_plan | onair_plan | ssv_plan | pat_plan
W01 | 30
W02 | 80
W03 | 130
W04 | 180
W05 | 230
W06 | 260 | 180
W07 | 260 | 230
W08 | 260 | 260 | 30
W09 | 260 | 260 | 60 | 30
W10 | 260 | 260 | 90 | 60 | 30
W11 | 260 | 260 | 120 | 90 | 60 | 30
W12 | 260 | 260 | 150 | 120 | 90 | 60
W13 | 260 | 260 | 180 | 150 | 120 | 90
W14 | 260 | 260 | 230 | 180 | 150 | 120
W15 | 260 | 260 | 260 | 230 | 180 | 150
W16 | 260 | 260 | 260 | 260 | 230 | 180
W17 | 260 | 260 | 260 | 260 | 260 | 230
W18 | 260 | 260 | 260 | 260 | 260 | 260
W19 | 260 | 260 | 260 | 260 | 260 | 260
W20 | 260 | 260 | 260 | 260 | 260 | 260
W21 | 260 | 260 | 260 | 260 | 260 | 260
W22 | 260 | 260 | 260 | 260 | 260 | 260
W23 | 260 | 260 | 260 | 260 | 260 | 260
W24 | 260 | 260 | 260 | 260 | 260 | 260