## PROJECT_LIST
id | name | active | color | region
VNPT 5G PO2 | VNPT 5G PO2 | TRUE | #0f766e | Central

## CONFIG
project_name | VNPT 5G PO2
client | VNPT
start_date | 2026-06-01
end_date | 2026-12-30
required_complete_date | 2026-12-30
region | Central
pm | Dung
weekly_target | 24
po_no | PO-1-2026

## DATA
site_id | site_name | province | status | project | site_type | build_type | lat | lng | ms_TSS | ms_TSSR | ms_RFI | ms_BTS_MOS | ms_BTS_On_Air | ms_PAT | ms_PAC | ms_SSV | ms_MW_On_Air | ms_Power_On_Air | ms_TX_Readiness | ms_BTS_HI | ms_BTS_Integration | ms_Dismantle | ms_OSS_KPI | ms_FAC
DNG-0001 | DNG Ward 19 — 5G NR n78 Rooftop | Da Nang | PAT Complete | VNPT 5G PO2 | 5G Expansion n78 | new |  |  | done | done | done | done | done | done
DNG-0002 | DNG Ward 37 — 5G Expansion n2 | Da Nang | PAT Complete | VNPT 5G PO2 | 5G NR n78 Macro | expansion |  |  | done | done | done | done | done | done
DNG-0003 | DNG Ward 15 — 5G NR n2 Rural | Da Nang | PAT Complete | VNPT 5G PO2 | 5G Expansion n78 | expansion |  |  | done | done | done | done | done | done
DNG-0004 | DNG Ward 33 — 5G NR n78 Rooftop | Da Nang | PAT Complete | VNPT 5G PO2 | 5G NR n2 Rural | new |  |  | done | done | done | done | done | done
DNG-0005 | DNG Ward 11 — 5G Expansion n78 | Da Nang | PAT Complete | VNPT 5G PO2 | 5G NR n78 Rooftop | new |  |  | done | done | done | done | done | done
DNG-0006 | DNG Ward 29 — 5G Expansion n2 | Da Nang | PAT Complete | VNPT 5G PO2 | 5G NR n78 Rooftop | expansion |  |  | done | done | done | done | done | done
DNG-0007 | DNG Ward 07 — 5G NR n2 Rural | Da Nang | PAT Complete | VNPT 5G PO2 | 5G NR n78 Q-Cell | expansion |  |  | done | done | done | done | done | done
DNG-0008 | DNG Ward 25 — 5G NR n78 Rooftop | Da Nang | PAT Complete | VNPT 5G PO2 | 5G Expansion n2 | expansion |  |  | done | done | done | done | done | done
DNG-0009 | DNG Ward 03 — 5G NR n78 Rooftop | Da Nang | PAT Complete | VNPT 5G PO2 | 5G NR n78 Q-Cell | expansion |  |  | done | done | done | done | done | done
DNG-0010 | DNG Ward 21 — 5G NR n78 Rooftop | Da Nang | PAT Complete | VNPT 5G PO2 | 5G NR n2 Rural | new |  |  | done | done | done | done | done | done
DNG-0011 | DNG Ward 39 — 5G NR n2 Rural | Da Nang | PAT Complete | VNPT 5G PO2 | 5G NR n78 Rooftop | new |  |  | done | done | done | done | done | done
DNG-0012 | DNG Ward 17 — 5G Expansion n2 | Da Nang | PAT Complete | VNPT 5G PO2 | 5G NR n2 Rural | new |  |  | done | done | done | done | done | done
DNG-0013 | DNG Ward 35 — 5G NR n78 Macro | Da Nang | PAT Complete | VNPT 5G PO2 | 5G Expansion n78 | new |  |  | done | done | done | done | done | done
DNG-0014 | DNG Ward 13 — 5G NR n78 Q-Cell | Da Nang | PAT Complete | VNPT 5G PO2 | 5G NR n78 Macro | expansion |  |  | done | done | done | done | done | done
DNG-0015 | DNG Ward 31 — 5G Expansion n2 | Da Nang | PAT Complete | VNPT 5G PO2 | 5G NR n78 Macro | new |  |  | done | done | done | done | done | done
DNG-0016 | DNG Ward 09 — 5G Expansion n78 | Da Nang | PAT Complete | VNPT 5G PO2 | 5G NR n78 Rooftop | new |  |  | done | done | done | done | done | done
DNG-0017 | DNG Ward 27 — 5G NR n78 Macro | Da Nang | PAT Complete | VNPT 5G PO2 | 5G NR n78 Macro | expansion |  |  | done | done | done | done | done | done
DNG-0018 | DNG Ward 05 — 5G Expansion n78 | Da Nang | PAT Complete | VNPT 5G PO2 | 5G NR n78 Q-Cell | new |  |  | done | done | done | done | done | done
DNG-0019 | DNG Ward 23 — 5G NR n78 Macro | Da Nang | PAT Complete | VNPT 5G PO2 | 5G NR n78 Macro | new |  |  | done | done | done | done | done | done
DNG-0020 | DNG Ward 01 — 5G Expansion n2 | Da Nang | PAT Complete | VNPT 5G PO2 | 5G NR n78 Macro | new |  |  | done | done | done | done | done | done
DNG-0021 | DNG Ward 19 — 5G NR n78 Macro | Da Nang | PAT Complete | VNPT 5G PO2 | 5G Expansion n78 | new |  |  | done | done | done | done | done | done
DNG-0022 | DNG Ward 37 — 5G Expansion n78 | Da Nang | PAT Complete | VNPT 5G PO2 | 5G NR n78 Q-Cell | new |  |  | done | done | done | done | done | done
DNG-0023 | DNG Ward 15 — 5G NR n78 Macro | Da Nang | PAT Complete | VNPT 5G PO2 | 5G NR n78 Rooftop | new |  |  | done | done | done | done | done | done
DNG-0024 | DNG Ward 33 — 5G Expansion n2 | Da Nang | PAT Complete | VNPT 5G PO2 | 5G NR n78 Q-Cell | new |  |  | done | done | done | done | done | done
DNG-0025 | DNG Ward 11 — 5G Expansion n2 | Da Nang | PAT Complete | VNPT 5G PO2 | 5G Expansion n2 | expansion |  |  | done | done | done | done | done | done
DNG-0026 | DNG Ward 29 — 5G NR n78 Rooftop | Da Nang | PAT Complete | VNPT 5G PO2 | 5G Expansion n2 | new |  |  | done | done | done | done | done | done
DNG-0027 | DNG Ward 07 — 5G Expansion n78 | Da Nang | PAT Complete | VNPT 5G PO2 | 5G NR n78 Rooftop | new |  |  | done | done | done | done | done | done
DNG-0028 | DNG Ward 25 — 5G Expansion n78 | Da Nang | PAT Complete | VNPT 5G PO2 | 5G NR n78 Q-Cell | new |  |  | done | done | done | done | done | done
DNG-0029 | DNG Ward 03 — 5G NR n2 Rural | Da Nang | PAT Complete | VNPT 5G PO2 | 5G NR n78 Q-Cell | new |  |  | done | done | done | done | done | done
DNG-0030 | DNG Ward 21 — 5G NR n78 Macro | Da Nang | PAT Complete | VNPT 5G PO2 | 5G Expansion n2 | expansion |  |  | done | done | done | done | done | done
DNG-0031 | DNG Ward 39 — 5G Expansion n2 | Da Nang | PAT Complete | VNPT 5G PO2 | 5G NR n2 Rural | expansion |  |  | done | done | done | done | done | done
DNG-0032 | DNG Ward 17 — 5G NR n78 Rooftop | Da Nang | PAT Complete | VNPT 5G PO2 | 5G NR n78 Rooftop | new |  |  | done | done | done | done | done | done
DNG-0033 | DNG Ward 35 — 5G NR n78 Q-Cell | Da Nang | PAT Complete | VNPT 5G PO2 | 5G NR n78 Rooftop | new |  |  | done | done | done | done | done | done
DNG-0034 | DNG Ward 13 — 5G NR n78 Macro | Da Nang | PAT Complete | VNPT 5G PO2 | 5G NR n2 Rural | new |  |  | done | done | done | done | done | done
DNG-0035 | DNG Ward 31 — 5G NR n78 Macro | Da Nang | PAT Complete | VNPT 5G PO2 | 5G Expansion n78 | new |  |  | done | done | done | done | done | done
DNG-0036 | DNG Ward 09 — 5G NR n78 Macro | Da Nang | PAT Complete | VNPT 5G PO2 | 5G Expansion n78 | new |  |  | done | done | done | done | done | done
DNG-0037 | DNG Ward 27 — 5G NR n78 Q-Cell | Da Nang | PAT Complete | VNPT 5G PO2 | 5G NR n78 Q-Cell | new |  |  | done | done | done | done | done | done
DNG-0038 | DNG Ward 05 — 5G NR n78 Q-Cell | Da Nang | PAT Complete | VNPT 5G PO2 | 5G NR n78 Macro | expansion |  |  | done | done | done | done | done | done
DNG-0039 | DNG Ward 23 — 5G Expansion n2 | Da Nang | PAT Complete | VNPT 5G PO2 | 5G NR n78 Rooftop | new |  |  | done | done | done | done | done | done
DNG-0040 | DNG Ward 01 — 5G NR n78 Rooftop | Da Nang | PAT Complete | VNPT 5G PO2 | 5G NR n78 Macro | new |  |  | done | done | done | done | done | done
DNG-0041 | DNG Ward 19 — 5G Expansion n78 | Da Nang | PAT Complete | VNPT 5G PO2 | 5G NR n78 Rooftop | new |  |  | done | done | done | done | done | done
DNG-0042 | DNG Ward 37 — 5G NR n78 Macro | Da Nang | PAT Complete | VNPT 5G PO2 | 5G Expansion n78 | new |  |  | done | done | done | done | done | done
DNG-0043 | DNG Ward 15 — 5G NR n78 Macro | Da Nang | PAT Complete | VNPT 5G PO2 | 5G NR n2 Rural | new |  |  | done | done | done | done | done | done
DNG-0044 | DNG Ward 33 — 5G NR n78 Macro | Da Nang | PAT Complete | VNPT 5G PO2 | 5G Expansion n2 | new |  |  | done | done | done | done | done | done
DNG-0045 | DNG Ward 11 — 5G Expansion n2 | Da Nang | PAT Complete | VNPT 5G PO2 | 5G Expansion n78 | new |  |  | done | done | done | done | done | done
DNG-0046 | DNG Ward 29 — 5G NR n78 Macro | Da Nang | PAT Complete | VNPT 5G PO2 | 5G NR n78 Q-Cell | new |  |  | done | done | done | done | done | done
DNG-0047 | DNG Ward 07 — 5G NR n78 Q-Cell | Da Nang | PAT Complete | VNPT 5G PO2 | 5G NR n78 Macro | new |  |  | done | done | done | done | done | done
DNG-0048 | DNG Ward 25 — 5G NR n2 Rural | Da Nang | PAT Complete | VNPT 5G PO2 | 5G NR n78 Rooftop | new |  |  | done | done | done | done | done | done
DNG-0049 | DNG Ward 03 — 5G NR n78 Q-Cell | Da Nang | PAT Complete | VNPT 5G PO2 | 5G NR n78 Macro | new |  |  | done | done | done | done | done | done
DNG-0050 | DNG Ward 21 — 5G NR n78 Rooftop | Da Nang | PAT Complete | VNPT 5G PO2 | 5G NR n78 Q-Cell | new |  |  | done | done | done | done | done | done
DNG-0051 | DNG Ward 39 — 5G Expansion n2 | Da Nang | PAT Complete | VNPT 5G PO2 | 5G NR n2 Rural | expansion |  |  | done | done | done | done | done | done
DNG-0052 | DNG Ward 17 — 5G NR n78 Macro | Da Nang | PAT Complete | VNPT 5G PO2 | 5G NR n78 Macro | new |  |  | done | done | done | done | done | done
DNG-0053 | DNG Ward 35 — 5G NR n78 Q-Cell | Da Nang | PAT Complete | VNPT 5G PO2 | 5G Expansion n2 | new |  |  | done | done | done | done | done | done
DNG-0054 | DNG Ward 13 — 5G NR n78 Q-Cell | Da Nang | PAT Complete | VNPT 5G PO2 | 5G NR n78 Rooftop | expansion |  |  | done | done | done | done | done | done
DNG-0055 | DNG Ward 31 — 5G Expansion n2 | Da Nang | PAT Complete | VNPT 5G PO2 | 5G NR n78 Macro | expansion |  |  | done | done | done | done | done | done
DNG-0056 | DNG Ward 09 — 5G NR n78 Q-Cell | Da Nang | PAT Complete | VNPT 5G PO2 | 5G Expansion n2 | expansion |  |  | done | done | done | done | done | done
DNG-0057 | DNG Ward 27 — 5G NR n2 Rural | Da Nang | On Air Complete | VNPT 5G PO2 | 5G NR n78 Q-Cell | expansion |  |  | done | done | done | done | done | done
DNG-0058 | DNG Ward 05 — 5G NR n78 Q-Cell | Da Nang | PAT Complete | VNPT 5G PO2 | 5G Expansion n78 | expansion |  |  | done | done | done | done | done | done
DNG-0059 | DNG Ward 23 — 5G NR n2 Rural | Da Nang | PAT Complete | VNPT 5G PO2 | 5G NR n78 Macro | expansion |  |  | done | done | done | done | done | done
DNG-0060 | DNG Ward 01 — 5G NR n78 Macro | Da Nang | PAT Complete | VNPT 5G PO2 | 5G NR n78 Rooftop | new |  |  | done | done | done | done | done | done
DNG-0061 | DNG Ward 19 — 5G NR n78 Rooftop | Da Nang | PAT Complete | VNPT 5G PO2 | 5G Expansion n2 | expansion |  |  | done | done | done | done | done | done
DNG-0062 | DNG Ward 37 — 5G NR n2 Rural | Da Nang | PAT Complete | VNPT 5G PO2 | 5G Expansion n78 | new |  |  | done | done | done | done | done | done
DNG-0063 | DNG Ward 15 — 5G NR n78 Rooftop | Da Nang | PAT Complete | VNPT 5G PO2 | 5G NR n78 Macro | new |  |  | done | done | done | done | done | done
DNG-0064 | DNG Ward 33 — 5G NR n2 Rural | Da Nang | PAT Complete | VNPT 5G PO2 | 5G Expansion n78 | new |  |  | done | done | done | done | done | done
DNG-0065 | DNG Ward 11 — 5G NR n2 Rural | Da Nang | PAT Complete | VNPT 5G PO2 | 5G Expansion n2 | expansion |  |  | done | done | done | done | done | done
DNG-0066 | DNG Ward 29 — 5G NR n78 Macro | Da Nang | On Air Complete | VNPT 5G PO2 | 5G NR n78 Rooftop | new |  |  | done | done | done | done | done | done
DNG-0067 | DNG Ward 07 — 5G Expansion n2 | Da Nang | PAT Complete | VNPT 5G PO2 | 5G NR n78 Rooftop | new |  |  | done | done | done | done | done | done
DNG-0068 | DNG Ward 25 — 5G Expansion n2 | Da Nang | On Air Complete | VNPT 5G PO2 | 5G NR n78 Rooftop | new |  |  | done | done | done | done | done | done
DNG-0069 | DNG Ward 03 — 5G NR n2 Rural | Da Nang | On Air Complete | VNPT 5G PO2 | 5G NR n78 Rooftop | new |  |  | done | done | done | done | done | done
DNG-0070 | DNG Ward 21 — 5G NR n78 Macro | Da Nang | PAT Complete | VNPT 5G PO2 | 5G NR n2 Rural | expansion |  |  | done | done | done | done | done | done
DNG-0071 | DNG Ward 39 — 5G NR n78 Rooftop | Da Nang | PAT Complete | VNPT 5G PO2 | 5G NR n78 Macro | new |  |  | done | done | done | done | done | done
DNG-0072 | DNG Ward 17 — 5G NR n2 Rural | Da Nang | PAT Complete | VNPT 5G PO2 | 5G NR n78 Q-Cell | new |  |  | done | done | done | done | done | done
DNG-0073 | DNG Ward 35 — 5G NR n78 Macro | Da Nang | PAT Complete | VNPT 5G PO2 | 5G NR n78 Q-Cell | expansion |  |  | done | done | done | done | done | done
DNG-0074 | DNG Ward 13 — 5G NR n78 Macro | Da Nang | PAT Complete | VNPT 5G PO2 | 5G NR n2 Rural | new |  |  | done | done | done | done | done | done
DNG-0075 | DNG Ward 31 — 5G NR n2 Rural | Da Nang | PAT Complete | VNPT 5G PO2 | 5G NR n78 Rooftop | new |  |  | done | done | done | done | done | done
DNG-0076 | DNG Ward 09 — 5G Expansion n2 | Da Nang | PAT Complete | VNPT 5G PO2 | 5G NR n78 Macro | expansion |  |  | done | done | done | done | done | done
DNG-0077 | DNG Ward 27 — 5G NR n2 Rural | Da Nang | PAT Complete | VNPT 5G PO2 | 5G NR n2 Rural | expansion |  |  | done | done | done | done | done | done
DNG-0078 | DNG Ward 05 — 5G NR n78 Rooftop | Da Nang | PAT Complete | VNPT 5G PO2 | 5G NR n78 Q-Cell | expansion |  |  | done | done | done | done | done | done
DNG-0079 | DNG Ward 23 — 5G Expansion n78 | Da Nang | PAT Complete | VNPT 5G PO2 | 5G NR n78 Rooftop | new |  |  | done | done | done | done | done | done
DNG-0080 | DNG Ward 01 — 5G NR n78 Macro | Da Nang | PAT Complete | VNPT 5G PO2 | 5G NR n78 Rooftop | new |  |  | done | done | done | done | done | done
DNG-0081 | DNG Ward 19 — 5G Expansion n2 | Da Nang | PAT Complete | VNPT 5G PO2 | 5G Expansion n2 | new |  |  | done | done | done | done | done | done
DNG-0082 | DNG Ward 37 — 5G Expansion n78 | Da Nang | PAT Complete | VNPT 5G PO2 | 5G NR n78 Macro | new |  |  | done | done | done | done | done | done
DNG-0083 | DNG Ward 15 — 5G Expansion n78 | Da Nang | PAT Complete | VNPT 5G PO2 | 5G NR n78 Macro | new |  |  | done | done | done | done | done | done
DNG-0084 | DNG Ward 33 — 5G NR n78 Macro | Da Nang | PAT Complete | VNPT 5G PO2 | 5G NR n78 Q-Cell | new |  |  | done | done | done | done | done | done
DNG-0085 | DNG Ward 11 — 5G NR n78 Macro | Da Nang | PAT Complete | VNPT 5G PO2 | 5G Expansion n2 | new |  |  | done | done | done | done | done | done
DNG-0086 | DNG Ward 29 — 5G Expansion n2 | Da Nang | PAT Complete | VNPT 5G PO2 | 5G NR n78 Rooftop | expansion |  |  | done | done | done | done | done | done
DNG-0087 | DNG Ward 07 — 5G Expansion n78 | Da Nang | On Air Complete | VNPT 5G PO2 | 5G NR n78 Macro | new |  |  | done | done | done | done | done | done
DNG-0088 | DNG Ward 25 — 5G Expansion n2 | Da Nang | PAT Complete | VNPT 5G PO2 | 5G Expansion n2 | new |  |  | done | done | done | done | done | done
DNG-0089 | DNG Ward 03 — 5G Expansion n2 | Da Nang | PAT Complete | VNPT 5G PO2 | 5G NR n78 Q-Cell | expansion |  |  | done | done | done | done | done | done
DNG-0090 | DNG Ward 21 — 5G NR n78 Rooftop | Da Nang | PAT Complete | VNPT 5G PO2 | 5G NR n78 Macro | expansion |  |  | done | done | done | done | done | done
DNG-0091 | DNG Ward 39 — 5G NR n78 Macro | Da Nang | PAT Complete | VNPT 5G PO2 | 5G Expansion n78 | expansion |  |  | done | done | done | done | done | done
DNG-0092 | DNG Ward 17 — 5G NR n78 Macro | Da Nang | PAT Complete | VNPT 5G PO2 | 5G NR n78 Macro | expansion |  |  | done | done | done | done | done | done
DNG-0093 | DNG Ward 35 — 5G NR n78 Rooftop | Da Nang | PAT Complete | VNPT 5G PO2 | 5G NR n78 Macro | new |  |  | done | done | done | done | done | done
DNG-0094 | DNG Ward 13 — 5G NR n2 Rural | Da Nang | PAT Complete | VNPT 5G PO2 | 5G Expansion n2 | new |  |  | done | done | done | done | done | done
DNG-0095 | DNG Ward 31 — 5G NR n78 Q-Cell | Da Nang | PAT Complete | VNPT 5G PO2 | 5G NR n2 Rural | new |  |  | done | done | done | done | done | done
DNG-0096 | DNG Ward 09 — 5G Expansion n2 | Da Nang | On Air Complete | VNPT 5G PO2 | 5G Expansion n78 | expansion |  |  | done | done | done | done | done | done
DNG-0097 | DNG Ward 27 — 5G NR n78 Rooftop | Da Nang | PAT Complete | VNPT 5G PO2 | 5G NR n78 Q-Cell | expansion |  |  | done | done | done | done | done | done
DNG-0098 | DNG Ward 05 — 5G Expansion n2 | Da Nang | PAT Complete | VNPT 5G PO2 | 5G NR n78 Macro | new |  |  | done | done | done | done | done | done
DNG-0099 | DNG Ward 23 — 5G NR n78 Macro | Da Nang | PAT Complete | VNPT 5G PO2 | 5G NR n2 Rural | expansion |  |  | done | done | done | done | done | done
DNG-0100 | DNG Ward 01 — 5G Expansion n78 | Da Nang | PAT Complete | VNPT 5G PO2 | 5G Expansion n78 | new |  |  | done | done | done | done | done | done
DNG-0101 | DNG Ward 19 — 5G NR n2 Rural | Da Nang | PAT Complete | VNPT 5G PO2 | 5G Expansion n78 | new |  |  | done | done | done | done | done | done
DNG-0102 | DNG Ward 37 — 5G NR n78 Rooftop | Da Nang | PAT Complete | VNPT 5G PO2 | 5G Expansion n78 | new |  |  | done | done | done | done | done | done
DNG-0103 | DNG Ward 15 — 5G Expansion n2 | Da Nang | PAT Complete | VNPT 5G PO2 | 5G Expansion n2 | new |  |  | done | done | done | done | done | done
DNG-0104 | DNG Ward 33 — 5G NR n78 Macro | Da Nang | PAT Complete | VNPT 5G PO2 | 5G NR n78 Macro | expansion |  |  | done | done | done | done | done | done
DNG-0105 | DNG Ward 11 — 5G NR n2 Rural | Da Nang | PAT Complete | VNPT 5G PO2 | 5G Expansion n2 | expansion |  |  | done | done | done | done | done | done
DNG-0106 | DNG Ward 29 — 5G NR n2 Rural | Da Nang | PAT Complete | VNPT 5G PO2 | 5G NR n78 Q-Cell | new |  |  | done | done | done | done | done | done
DNG-0107 | DNG Ward 07 — 5G NR n78 Q-Cell | Da Nang | PAT Complete | VNPT 5G PO2 | 5G Expansion n2 | expansion |  |  | done | done | done | done | done | done
DNG-0108 | DNG Ward 25 — 5G Expansion n78 | Da Nang | PAT Complete | VNPT 5G PO2 | 5G NR n78 Rooftop | new |  |  | done | done | done | done | done | done
DNG-0109 | DNG Ward 03 — 5G NR n78 Macro | Da Nang | PAT Complete | VNPT 5G PO2 | 5G NR n78 Rooftop | new |  |  | done | done | done | done | done | done
DNG-0110 | DNG Ward 21 — 5G NR n78 Macro | Da Nang | PAT Complete | VNPT 5G PO2 | 5G NR n78 Rooftop | new |  |  | done | done | done | done | done | done
DNG-0111 | DNG Ward 39 — 5G NR n78 Macro | Da Nang | PAT Complete | VNPT 5G PO2 | 5G Expansion n78 | expansion |  |  | done | done | done | done | done | done
DNG-0112 | DNG Ward 17 — 5G Expansion n78 | Da Nang | PAT Complete | VNPT 5G PO2 | 5G Expansion n78 | new |  |  | done | done | done | done | done | done
QNM-0001 | QNM Ward 11 — 5G NR n78 Q-Cell | Quang Nam | PAT Complete | VNPT 5G PO2 | 5G NR n2 Rural | expansion | 15.8213 | 107.7755 | 2026-01-08 | 2026-01-14 | 2026-01-22 | 2026-02-07 | 2026-02-23 | 2026-03-07
QNM-0002 | QNM Ward 29 — 5G NR n78 Rooftop | Quang Nam | PAT Complete | VNPT 5G PO2 | 5G Expansion n2 | new | 15.8095 | 108.1258 | 2026-01-27 | 2026-02-02 | 2026-02-10 | 2026-02-26 | 2026-03-14 | 2026-03-26
QNM-0003 | QNM Ward 07 — 5G NR n78 Macro | Quang Nam | PAT Complete | VNPT 5G PO2 | 5G NR n78 Rooftop | new | 15.3763 | 107.8963 | 2026-02-07 | 2026-02-13 | 2026-02-21 | 2026-03-09 | 2026-03-25 | 2026-04-06
QNM-0004 | QNM Ward 25 — 5G Expansion n2 | Quang Nam | PAT Complete | VNPT 5G PO2 | 5G NR n78 Q-Cell | new | 15.3697 | 107.9814 | 2026-01-09 | 2026-01-15 | 2026-01-23 | 2026-02-08 | 2026-02-24 | 2026-03-08
QNM-0005 | QNM Ward 03 — 5G NR n2 Rural | Quang Nam | PAT Complete | VNPT 5G PO2 | 5G Expansion n78 | expansion | 15.758 | 107.7703 | 2026-01-27 | 2026-02-02 | 2026-02-10 | 2026-02-26 | 2026-03-14 | 2026-03-26
QNM-0006 | QNM Ward 21 — 5G Expansion n78 | Quang Nam | PAT Complete | VNPT 5G PO2 | 5G NR n78 Rooftop | new | 15.7163 | 107.8951 | 2026-01-22 | 2026-01-28 | 2026-02-05 | 2026-02-21 | 2026-03-09 | 2026-03-21
QNM-0007 | QNM Ward 39 — 5G Expansion n78 | Quang Nam | PAT Complete | VNPT 5G PO2 | 5G NR n78 Q-Cell | new | 15.8225 | 107.919 | 2026-01-16 | 2026-01-22 | 2026-01-30 | 2026-02-15 | 2026-03-03 | 2026-03-15
QNM-0008 | QNM Ward 17 — 5G NR n78 Macro | Quang Nam | PAT Complete | VNPT 5G PO2 | 5G NR n78 Q-Cell | new | 15.3325 | 107.9102 | 2026-01-31 | 2026-02-06 | 2026-02-14 | 2026-03-02 | 2026-03-18 | 2026-03-30
QNM-0009 | QNM Ward 35 — 5G NR n78 Macro | Quang Nam | PAT Complete | VNPT 5G PO2 | 5G NR n78 Q-Cell | expansion | 15.627 | 107.8546 | 2026-02-15 | 2026-02-21 | 2026-03-01 | 2026-03-17 | 2026-04-02 | 2026-04-14
QNM-0010 | QNM Ward 13 — 5G NR n2 Rural | Quang Nam | PAT Complete | VNPT 5G PO2 | 5G Expansion n78 | new | 15.511 | 108.3283 | 2026-02-20 | 2026-02-26 | 2026-03-06 | 2026-03-22 | 2026-04-07 | 2026-04-19
QNM-0011 | QNM Ward 31 — 5G Expansion n78 | Quang Nam | PAT Complete | VNPT 5G PO2 | 5G NR n78 Rooftop | expansion | 15.4967 | 107.7145 | 2026-01-20 | 2026-01-26 | 2026-02-03 | 2026-02-19 | 2026-03-07 | 2026-03-19
QNM-0012 | QNM Ward 09 — 5G NR n78 Q-Cell | Quang Nam | On Air Complete | VNPT 5G PO2 | 5G NR n78 Macro | expansion | 15.7759 | 107.783 | 2026-01-21 | 2026-01-27 | 2026-02-04 | 2026-02-20 | 2026-03-08
QNM-0013 | QNM Ward 27 — 5G NR n2 Rural | Quang Nam | PAT Complete | VNPT 5G PO2 | 5G NR n78 Rooftop | expansion | 15.315 | 108.1356 | 2026-01-15 | 2026-01-21 | 2026-01-29 | 2026-02-14 | 2026-03-02 | 2026-03-14
QNM-0014 | QNM Ward 05 — 5G NR n78 Rooftop | Quang Nam | PAT Complete | VNPT 5G PO2 | 5G NR n78 Macro | new | 15.4303 | 107.8038 | 2026-01-16 | 2026-01-22 | 2026-01-30 | 2026-02-15 | 2026-03-03 | 2026-03-15
QNM-0015 | QNM Ward 23 — 5G NR n78 Q-Cell | Quang Nam | PAT Complete | VNPT 5G PO2 | 5G NR n2 Rural | new | 15.4469 | 107.9193 | 2026-02-07 | 2026-02-13 | 2026-02-21 | 2026-03-09 | 2026-03-25 | 2026-04-06
QNM-0016 | QNM Ward 01 — 5G NR n78 Rooftop | Quang Nam | PAT Complete | VNPT 5G PO2 | 5G NR n78 Rooftop | expansion | 15.4703 | 108.1226 | 2026-02-14 | 2026-02-20 | 2026-02-28 | 2026-03-16 | 2026-04-01 | 2026-04-13
QNM-0017 | QNM Ward 19 — 5G NR n2 Rural | Quang Nam | PAT Complete | VNPT 5G PO2 | 5G NR n78 Macro | new | 15.4638 | 107.9796 | 2026-01-12 | 2026-01-18 | 2026-01-26 | 2026-02-11 | 2026-02-27 | 2026-03-11
QNM-0018 | QNM Ward 37 — 5G NR n78 Rooftop | Quang Nam | PAT Complete | VNPT 5G PO2 | 5G NR n78 Macro | expansion | 15.4043 | 107.7838 | 2026-01-28 | 2026-02-03 | 2026-02-11 | 2026-02-27 | 2026-03-15 | 2026-03-27
QNM-0019 | QNM Ward 15 — 5G NR n78 Q-Cell | Quang Nam | PAT Complete | VNPT 5G PO2 | 5G Expansion n2 | expansion | 15.5842 | 107.8557 | 2026-01-15 | 2026-01-21 | 2026-01-29 | 2026-02-14 | 2026-03-02 | 2026-03-14
QNM-0020 | QNM Ward 33 — 5G NR n78 Rooftop | Quang Nam | PAT Complete | VNPT 5G PO2 | 5G NR n78 Rooftop | new | 15.7584 | 107.7283 | 2026-01-07 | 2026-01-13 | 2026-01-21 | 2026-02-06 | 2026-02-22 | 2026-03-06
QNM-0021 | QNM Ward 11 — 5G NR n78 Rooftop | Quang Nam | PAT Complete | VNPT 5G PO2 | 5G Expansion n2 | expansion | 15.4703 | 108.1063 | 2026-01-07 | 2026-01-13 | 2026-01-21 | 2026-02-06 | 2026-02-22 | 2026-03-06
QNM-0022 | QNM Ward 29 — 5G Expansion n78 | Quang Nam | PAT Complete | VNPT 5G PO2 | 5G Expansion n78 | new | 15.713 | 107.9482 | 2026-02-13 | 2026-02-19 | 2026-02-27 | 2026-03-15 | 2026-03-31 | 2026-04-12
QNM-0023 | QNM Ward 07 — 5G NR n2 Rural | Quang Nam | PAT Complete | VNPT 5G PO2 | 5G Expansion n78 | new | 15.435 | 108.3255 | 2026-01-14 | 2026-01-20 | 2026-01-28 | 2026-02-13 | 2026-03-01 | 2026-03-13
QNM-0024 | QNM Ward 25 — 5G NR n78 Rooftop | Quang Nam | PAT Complete | VNPT 5G PO2 | 5G NR n78 Macro | expansion | 15.2914 | 107.7018 | 2026-02-15 | 2026-02-21 | 2026-03-01 | 2026-03-17 | 2026-04-02 | 2026-04-14
QNM-0025 | QNM Ward 03 — 5G NR n78 Macro | Quang Nam | PAT Complete | VNPT 5G PO2 | 5G NR n2 Rural | expansion | 15.5411 | 107.909 | 2026-02-19 | 2026-02-25 | 2026-03-05 | 2026-03-21 | 2026-04-06 | 2026-04-18
QNM-0026 | QNM Ward 21 — 5G Expansion n78 | Quang Nam | PAT Complete | VNPT 5G PO2 | 5G Expansion n78 | new | 15.526 | 107.7097 | 2026-01-03 | 2026-01-09 | 2026-01-17 | 2026-02-02 | 2026-02-18 | 2026-03-02
QNM-0027 | QNM Ward 39 — 5G NR n78 Macro | Quang Nam | PAT Complete | VNPT 5G PO2 | 5G NR n2 Rural | expansion | 15.6736 | 108.1745 | 2026-01-13 | 2026-01-19 | 2026-01-27 | 2026-02-12 | 2026-02-28 | 2026-03-12
QNM-0028 | QNM Ward 17 — 5G Expansion n78 | Quang Nam | PAT Complete | VNPT 5G PO2 | 5G Expansion n2 | new | 15.4253 | 107.7636 | 2026-02-03 | 2026-02-09 | 2026-02-17 | 2026-03-05 | 2026-03-21 | 2026-04-02
QNM-0029 | QNM Ward 35 — 5G NR n78 Rooftop | Quang Nam | PAT Complete | VNPT 5G PO2 | 5G NR n78 Q-Cell | expansion | 15.5796 | 107.9759 | 2026-02-16 | 2026-02-22 | 2026-03-02 | 2026-03-18 | 2026-04-03 | 2026-04-15
QNM-0030 | QNM Ward 13 — 5G Expansion n78 | Quang Nam | PAT Complete | VNPT 5G PO2 | 5G NR n78 Rooftop | expansion | 15.7052 | 107.9227 | 2026-02-22 | 2026-02-28 | 2026-03-08 | 2026-03-24 | 2026-04-09 | 2026-04-21
QNM-0031 | QNM Ward 31 — 5G NR n78 Rooftop | Quang Nam | PAT Complete | VNPT 5G PO2 | 5G NR n78 Q-Cell | new | 15.4365 | 107.8465 | 2026-01-12 | 2026-01-18 | 2026-01-26 | 2026-02-11 | 2026-02-27 | 2026-03-11
QNM-0032 | QNM Ward 09 — 5G NR n78 Macro | Quang Nam | PAT Complete | VNPT 5G PO2 | 5G Expansion n78 | expansion | 15.2751 | 107.9031 | 2026-01-12 | 2026-01-18 | 2026-01-26 | 2026-02-11 | 2026-02-27 | 2026-03-11
QNM-0033 | QNM Ward 27 — 5G Expansion n2 | Quang Nam | PAT Complete | VNPT 5G PO2 | 5G NR n78 Rooftop | new | 15.4131 | 108.11 | 2026-01-25 | 2026-01-31 | 2026-02-08 | 2026-02-24 | 2026-03-12 | 2026-03-24
QNM-0034 | QNM Ward 05 — 5G NR n78 Macro | Quang Nam | PAT Complete | VNPT 5G PO2 | 5G Expansion n2 | new | 15.7654 | 107.9595 | 2026-02-10 | 2026-02-16 | 2026-02-24 | 2026-03-12 | 2026-03-28 | 2026-04-09
QNM-0035 | QNM Ward 23 — 5G NR n78 Macro | Quang Nam | PAT Complete | VNPT 5G PO2 | 5G NR n78 Macro | new | 15.7615 | 107.8963 | 2026-01-29 | 2026-02-04 | 2026-02-12 | 2026-02-28 | 2026-03-16 | 2026-03-28
QNM-0036 | QNM Ward 01 — 5G Expansion n78 | Quang Nam | PAT Complete | VNPT 5G PO2 | 5G NR n2 Rural | new | 15.7361 | 108.1002 | 2026-01-05 | 2026-01-11 | 2026-01-19 | 2026-02-04 | 2026-02-20 | 2026-03-04
QNM-0037 | QNM Ward 19 — 5G Expansion n78 | Quang Nam | PAT Complete | VNPT 5G PO2 | 5G NR n78 Q-Cell | new | 15.4222 | 107.9507 | 2026-02-18 | 2026-02-24 | 2026-03-04 | 2026-03-20 | 2026-04-05 | 2026-04-17
QNM-0038 | QNM Ward 37 — 5G NR n78 Rooftop | Quang Nam | PAT Complete | VNPT 5G PO2 | 5G Expansion n2 | new | 15.3368 | 107.9947 | 2026-02-14 | 2026-02-20 | 2026-02-28 | 2026-03-16 | 2026-04-01 | 2026-04-13
QNM-0039 | QNM Ward 15 — 5G Expansion n2 | Quang Nam | PAT Complete | VNPT 5G PO2 | 5G Expansion n2 | new | 15.4552 | 107.8395 | 2026-01-21 | 2026-01-27 | 2026-02-04 | 2026-02-20 | 2026-03-08 | 2026-03-20
QNM-0040 | QNM Ward 33 — 5G Expansion n2 | Quang Nam | PAT Complete | VNPT 5G PO2 | 5G Expansion n78 | new | 15.7268 | 108.0104 | 2026-01-30 | 2026-02-05 | 2026-02-13 | 2026-03-01 | 2026-03-17 | 2026-03-29
QNM-0041 | QNM Ward 11 — 5G NR n78 Q-Cell | Quang Nam | PAT Complete | VNPT 5G PO2 | 5G NR n2 Rural | new | 15.7985 | 108.2741 | 2026-02-28 | 2026-03-06 | 2026-03-14 | 2026-03-30 | 2026-04-15 | 2026-04-27
QNM-0042 | QNM Ward 29 — 5G NR n78 Q-Cell | Quang Nam | PAT Complete | VNPT 5G PO2 | 5G Expansion n78 | new | 15.7771 | 108.3199 | 2026-01-02 | 2026-01-08 | 2026-01-16 | 2026-02-01 | 2026-02-17 | 2026-03-01
QNM-0043 | QNM Ward 07 — 5G NR n2 Rural | Quang Nam | PAT Complete | VNPT 5G PO2 | 5G NR n2 Rural | new | 15.4103 | 107.9535 | 2026-02-12 | 2026-02-18 | 2026-02-26 | 2026-03-14 | 2026-03-30 | 2026-04-11
QNM-0044 | QNM Ward 25 — 5G NR n78 Q-Cell | Quang Nam | PAT Complete | VNPT 5G PO2 | 5G NR n2 Rural | new | 15.2976 | 108.0317 | 2026-02-23 | 2026-03-01 | 2026-03-09 | 2026-03-25 | 2026-04-10 | 2026-04-22
QNM-0045 | QNM Ward 03 — 5G NR n78 Rooftop | Quang Nam | PAT Complete | VNPT 5G PO2 | 5G NR n2 Rural | expansion | 15.6527 | 107.8716 | 2026-02-20 | 2026-02-26 | 2026-03-06 | 2026-03-22 | 2026-04-07 | 2026-04-19
QNM-0046 | QNM Ward 21 — 5G Expansion n2 | Quang Nam | PAT Complete | VNPT 5G PO2 | 5G NR n78 Q-Cell | expansion | 15.3185 | 108.1007 | 2026-02-16 | 2026-02-22 | 2026-03-02 | 2026-03-18 | 2026-04-03 | 2026-04-15
QNM-0047 | QNM Ward 39 — 5G Expansion n2 | Quang Nam | PAT Complete | VNPT 5G PO2 | 5G NR n78 Macro | new | 15.4577 | 107.8162 | 2026-01-21 | 2026-01-27 | 2026-02-04 | 2026-02-20 | 2026-03-08 | 2026-03-20
QNM-0048 | QNM Ward 17 — 5G NR n78 Q-Cell | Quang Nam | PAT Complete | VNPT 5G PO2 | 5G NR n78 Q-Cell | new | 15.3146 | 107.8576 | 2026-02-20 | 2026-02-26 | 2026-03-06 | 2026-03-22 | 2026-04-07 | 2026-04-19
QNM-0049 | QNM Ward 35 — 5G NR n78 Q-Cell | Quang Nam | PAT Complete | VNPT 5G PO2 | 5G Expansion n78 | new | 15.828 | 107.7466 | 2026-01-31 | 2026-02-06 | 2026-02-14 | 2026-03-02 | 2026-03-18 | 2026-03-30
QNM-0050 | QNM Ward 13 — 5G NR n78 Macro | Quang Nam | On Air Complete | VNPT 5G PO2 | 5G NR n78 Q-Cell | new | 15.3905 | 108.3295 | 2026-02-05 | 2026-02-11 | 2026-02-19 | 2026-03-07 | 2026-03-23
QNM-0051 | QNM Ward 31 — 5G NR n78 Rooftop | Quang Nam | PAT Complete | VNPT 5G PO2 | 5G Expansion n2 | expansion | 15.452 | 108.0394 | 2026-02-09 | 2026-02-15 | 2026-02-23 | 2026-03-11 | 2026-03-27 | 2026-04-08
QNM-0052 | QNM Ward 09 — 5G Expansion n2 | Quang Nam | PAT Complete | VNPT 5G PO2 | 5G NR n78 Macro | new | 15.7879 | 108.0378 | 2026-01-31 | 2026-02-06 | 2026-02-14 | 2026-03-02 | 2026-03-18 | 2026-03-30
QNM-0053 | QNM Ward 27 — 5G NR n2 Rural | Quang Nam | PAT Complete | VNPT 5G PO2 | 5G Expansion n78 | new | 15.3051 | 108.0947 | 2026-02-04 | 2026-02-10 | 2026-02-18 | 2026-03-06 | 2026-03-22 | 2026-04-03
QNM-0054 | QNM Ward 05 — 5G NR n78 Q-Cell | Quang Nam | PAT Complete | VNPT 5G PO2 | 5G NR n78 Rooftop | new | 15.5812 | 107.8567 | 2026-02-08 | 2026-02-14 | 2026-02-22 | 2026-03-10 | 2026-03-26 | 2026-04-07
QNM-0055 | QNM Ward 23 — 5G Expansion n78 | Quang Nam | PAT Complete | VNPT 5G PO2 | 5G Expansion n2 | expansion | 15.4471 | 108.224 | 2026-01-08 | 2026-01-14 | 2026-01-22 | 2026-02-07 | 2026-02-23 | 2026-03-07
QNM-0056 | QNM Ward 01 — 5G NR n78 Macro | Quang Nam | PAT Complete | VNPT 5G PO2 | 5G NR n78 Macro | new | 15.3611 | 107.8294 | 2026-02-14 | 2026-02-20 | 2026-02-28 | 2026-03-16 | 2026-04-01 | 2026-04-13
QNM-0057 | QNM Ward 19 — 5G NR n2 Rural | Quang Nam | PAT Complete | VNPT 5G PO2 | 5G Expansion n2 | expansion | 15.368 | 108.2511 | 2026-01-27 | 2026-02-02 | 2026-02-10 | 2026-02-26 | 2026-03-14 | 2026-03-26
QNM-0058 | QNM Ward 37 — 5G NR n78 Rooftop | Quang Nam | PAT Complete | VNPT 5G PO2 | 5G NR n78 Rooftop | new | 15.6882 | 108.1457 | 2026-01-24 | 2026-01-30 | 2026-02-07 | 2026-02-23 | 2026-03-11 | 2026-03-23
QNM-0059 | QNM Ward 15 — 5G Expansion n2 | Quang Nam | On Air Complete | VNPT 5G PO2 | 5G NR n78 Q-Cell | new | 15.2836 | 107.8541 | 2026-02-11 | 2026-02-17 | 2026-02-25 | 2026-03-13 | 2026-03-29 | 2026-04-30
QNM-0060 | QNM Ward 33 — 5G NR n78 Macro | Quang Nam | PAT Complete | VNPT 5G PO2 | 5G NR n78 Q-Cell | new | 15.7855 | 107.7437 | 2026-01-16 | 2026-01-22 | 2026-01-30 | 2026-02-15 | 2026-03-03 | 2026-03-15
QNM-0061 | QNM Ward 11 — 5G NR n78 Macro | Quang Nam | PAT Complete | VNPT 5G PO2 | 5G NR n78 Rooftop | new | 15.3472 | 107.9587 | 2026-01-31 | 2026-02-06 | 2026-02-14 | 2026-03-02 | 2026-03-18 | 2026-03-30
QNM-0062 | QNM Ward 29 — 5G NR n2 Rural | Quang Nam | PAT Complete | VNPT 5G PO2 | 5G NR n78 Q-Cell | new | 15.702 | 108.1393 | 2026-02-10 | 2026-02-16 | 2026-02-24 | 2026-03-12 | 2026-03-28 | 2026-04-09
QNM-0063 | QNM Ward 07 — 5G Expansion n78 | Quang Nam | PAT Complete | VNPT 5G PO2 | 5G NR n2 Rural | new | 15.3394 | 107.964 | 2026-01-23 | 2026-01-29 | 2026-02-06 | 2026-02-22 | 2026-03-10 | 2026-03-22
QNM-0064 | QNM Ward 25 — 5G NR n78 Q-Cell | Quang Nam | PAT Complete | VNPT 5G PO2 | 5G NR n2 Rural | expansion | 15.4775 | 108.2742 | 2026-01-24 | 2026-01-30 | 2026-02-07 | 2026-02-23 | 2026-03-11 | 2026-03-23
QNM-0065 | QNM Ward 03 — 5G NR n78 Macro | Quang Nam | PAT Complete | VNPT 5G PO2 | 5G NR n78 Q-Cell | expansion | 15.5334 | 107.8353 | 2026-01-06 | 2026-01-12 | 2026-01-20 | 2026-02-05 | 2026-02-21 | 2026-03-05
QNM-0066 | QNM Ward 21 — 5G NR n78 Q-Cell | Quang Nam | PAT Complete | VNPT 5G PO2 | 5G NR n2 Rural | new | 15.6233 | 108.0263 | 2026-02-01 | 2026-02-07 | 2026-02-15 | 2026-03-03 | 2026-03-19 | 2026-03-31
QNM-0067 | QNM Ward 39 — 5G NR n78 Rooftop | Quang Nam | PAT Complete | VNPT 5G PO2 | 5G NR n78 Macro | new | 15.8251 | 108.2186 | 2026-02-22 | 2026-02-28 | 2026-03-08 | 2026-03-24 | 2026-04-09 | 2026-04-21
QNM-0068 | QNM Ward 17 — 5G NR n78 Q-Cell | Quang Nam | PAT Complete | VNPT 5G PO2 | 5G Expansion n2 | new | 15.5315 | 107.7818 | 2026-01-28 | 2026-02-03 | 2026-02-11 | 2026-02-27 | 2026-03-15 | 2026-03-27
QNM-0069 | QNM Ward 35 — 5G NR n78 Rooftop | Quang Nam | PAT Complete | VNPT 5G PO2 | 5G Expansion n2 | expansion | 15.7616 | 107.744 | 2026-02-17 | 2026-02-23 | 2026-03-03 | 2026-03-19 | 2026-04-04 | 2026-04-16
QNM-0070 | QNM Ward 13 — 5G NR n78 Macro | Quang Nam | PAT Complete | VNPT 5G PO2 | 5G Expansion n2 | expansion | 15.4513 | 107.7258 | 2026-01-16 | 2026-01-22 | 2026-01-30 | 2026-02-15 | 2026-03-03 | 2026-03-15
QNM-0071 | QNM Ward 31 — 5G NR n2 Rural | Quang Nam | PAT Complete | VNPT 5G PO2 | 5G NR n78 Macro | new | 15.3024 | 107.9909 | 2026-02-11 | 2026-02-17 | 2026-02-25 | 2026-03-13 | 2026-03-29 | 2026-04-10
QNM-0072 | QNM Ward 09 — 5G NR n78 Rooftop | Quang Nam | PAT Complete | VNPT 5G PO2 | 5G NR n78 Macro | new | 15.6313 | 107.908 | 2026-02-15 | 2026-02-21 | 2026-03-01 | 2026-03-17 | 2026-04-02 | 2026-04-14
QNM-0073 | QNM Ward 27 — 5G NR n78 Q-Cell | Quang Nam | PAT Complete | VNPT 5G PO2 | 5G Expansion n2 | new | 15.7727 | 108.0656 | 2026-02-17 | 2026-02-23 | 2026-03-03 | 2026-03-19 | 2026-04-04 | 2026-04-16
QNM-0074 | QNM Ward 05 — 5G NR n2 Rural | Quang Nam | PAT Complete | VNPT 5G PO2 | 5G NR n78 Rooftop | new | 15.6977 | 107.8439 | 2026-01-18 | 2026-01-24 | 2026-02-01 | 2026-02-17 | 2026-03-05 | 2026-03-17
QNM-0075 | QNM Ward 23 — 5G NR n78 Rooftop | Quang Nam | PAT Complete | VNPT 5G PO2 | 5G NR n78 Rooftop | new | 15.537 | 108.1134 | 2026-02-08 | 2026-02-14 | 2026-02-22 | 2026-03-10 | 2026-03-26 | 2026-04-07
QNM-0076 | QNM Ward 01 — 5G NR n78 Q-Cell | Quang Nam | PAT Complete | VNPT 5G PO2 | 5G Expansion n78 | expansion | 15.7182 | 108.1936 | 2026-02-08 | 2026-02-14 | 2026-02-22 | 2026-03-10 | 2026-03-26 | 2026-04-07
QNM-0077 | QNM Ward 19 — 5G NR n78 Rooftop | Quang Nam | PAT Complete | VNPT 5G PO2 | 5G NR n2 Rural | expansion | 15.544 | 107.8111 | 2026-02-02 | 2026-02-08 | 2026-02-16 | 2026-03-04 | 2026-03-20 | 2026-04-01
QNM-0078 | QNM Ward 37 — 5G Expansion n2 | Quang Nam | On Air Complete | VNPT 5G PO2 | 5G NR n78 Macro | expansion | 15.794 | 107.9837 | 2026-01-16 | 2026-01-22 | 2026-01-30 | 2026-02-15 | 2026-03-03
QNM-0079 | QNM Ward 15 — 5G NR n78 Q-Cell | Quang Nam | PAT Complete | VNPT 5G PO2 | 5G NR n78 Q-Cell | new | 15.5806 | 107.7099 | 2026-01-06 | 2026-01-12 | 2026-01-20 | 2026-02-05 | 2026-02-21 | 2026-03-05
QNM-0080 | QNM Ward 33 — 5G NR n78 Rooftop | Quang Nam | PAT Complete | VNPT 5G PO2 | 5G NR n78 Macro | expansion | 15.4103 | 107.7622 | 2026-01-17 | 2026-01-23 | 2026-01-31 | 2026-02-16 | 2026-03-04 | 2026-03-16
QNM-0081 | QNM Ward 11 — 5G NR n78 Q-Cell | Quang Nam | PAT Complete | VNPT 5G PO2 | 5G Expansion n78 | new | 15.4807 | 108.3192 | 2026-01-08 | 2026-01-14 | 2026-01-22 | 2026-02-07 | 2026-02-23 | 2026-03-07
QNM-0082 | QNM Ward 29 — 5G NR n78 Rooftop | Quang Nam | On Air Complete | VNPT 5G PO2 | 5G NR n78 Rooftop | new | 15.5335 | 107.8658 | 2026-01-22 | 2026-01-28 | 2026-02-05 | 2026-02-21 | 2026-03-09 | 2026-04-29
QNM-0083 | QNM Ward 07 — 5G Expansion n2 | Quang Nam | PAT Complete | VNPT 5G PO2 | 5G Expansion n78 | expansion | 15.3073 | 107.7032 | 2026-02-28 | 2026-03-06 | 2026-03-14 | 2026-03-30 | 2026-04-15 | 2026-04-27
QNM-0084 | QNM Ward 25 — 5G NR n2 Rural | Quang Nam | PAT Complete | VNPT 5G PO2 | 5G Expansion n2 | expansion | 15.415 | 107.8538 | 2026-02-04 | 2026-02-10 | 2026-02-18 | 2026-03-06 | 2026-03-22 | 2026-04-03
QNM-0085 | QNM Ward 03 — 5G NR n78 Macro | Quang Nam | PAT Complete | VNPT 5G PO2 | 5G NR n78 Macro | new | 15.7742 | 108.1186 | 2026-01-08 | 2026-01-14 | 2026-01-22 | 2026-02-07 | 2026-02-23 | 2026-03-07
QNM-0086 | QNM Ward 21 — 5G NR n2 Rural | Quang Nam | PAT Complete | VNPT 5G PO2 | 5G NR n78 Q-Cell | new | 15.6147 | 108.0058 | 2026-01-08 | 2026-01-14 | 2026-01-22 | 2026-02-07 | 2026-02-23 | 2026-03-07
QNM-0087 | QNM Ward 39 — 5G NR n78 Q-Cell | Quang Nam | PAT Complete | VNPT 5G PO2 | 5G Expansion n78 | new | 15.5101 | 108.3159 | 2026-01-01 | 2026-01-07 | 2026-01-15 | 2026-01-31 | 2026-02-16 | 2026-02-28
QNM-0088 | QNM Ward 17 — 5G NR n78 Rooftop | Quang Nam | PAT Complete | VNPT 5G PO2 | 5G Expansion n2 | new | 15.7698 | 108.0295 | 2026-01-16 | 2026-01-22 | 2026-01-30 | 2026-02-15 | 2026-03-03 | 2026-03-15
QNM-0089 | QNM Ward 35 — 5G NR n78 Macro | Quang Nam | PAT Complete | VNPT 5G PO2 | 5G NR n78 Q-Cell | expansion | 15.6864 | 108.2083 | 2026-02-17 | 2026-02-23 | 2026-03-03 | 2026-03-19 | 2026-04-04 | 2026-04-16
QNM-0090 | QNM Ward 13 — 5G Expansion n2 | Quang Nam | PAT Complete | VNPT 5G PO2 | 5G NR n2 Rural | new | 15.687 | 108.0999 | 2026-01-30 | 2026-02-05 | 2026-02-13 | 2026-03-01 | 2026-03-17 | 2026-03-29
QNM-0091 | QNM Ward 31 — 5G Expansion n78 | Quang Nam | PAT Complete | VNPT 5G PO2 | 5G NR n78 Q-Cell | new | 15.4965 | 107.7503 | 2026-02-03 | 2026-02-09 | 2026-02-17 | 2026-03-05 | 2026-03-21 | 2026-04-02
QNM-0092 | QNM Ward 09 — 5G Expansion n78 | Quang Nam | PAT Complete | VNPT 5G PO2 | 5G NR n78 Q-Cell | new | 15.6387 | 107.9043 | 2026-02-05 | 2026-02-11 | 2026-02-19 | 2026-03-07 | 2026-03-23 | 2026-04-04
QNM-0093 | QNM Ward 27 — 5G NR n78 Macro | Quang Nam | PAT Complete | VNPT 5G PO2 | 5G Expansion n2 | new | 15.6865 | 108.274 | 2026-02-05 | 2026-02-11 | 2026-02-19 | 2026-03-07 | 2026-03-23 | 2026-04-04
QNM-0094 | QNM Ward 05 — 5G Expansion n2 | Quang Nam | PAT Complete | VNPT 5G PO2 | 5G NR n2 Rural | new | 15.5627 | 108.3232 | 2026-02-05 | 2026-02-11 | 2026-02-19 | 2026-03-07 | 2026-03-23 | 2026-04-04
QNM-0095 | QNM Ward 23 — 5G Expansion n78 | Quang Nam | PAT Complete | VNPT 5G PO2 | 5G NR n78 Q-Cell | new | 15.7813 | 108.074 | 2026-02-16 | 2026-02-22 | 2026-03-02 | 2026-03-18 | 2026-04-03 | 2026-04-15
QNM-0096 | QNM Ward 01 — 5G Expansion n2 | Quang Nam | On Air Complete | VNPT 5G PO2 | 5G NR n78 Rooftop | new | 15.7071 | 108.1596 | 2026-01-29 | 2026-02-04 | 2026-02-12 | 2026-02-28 | 2026-03-16
QNM-0097 | QNM Ward 19 — 5G NR n78 Rooftop | Quang Nam | PAT Complete | VNPT 5G PO2 | 5G Expansion n2 | expansion | 15.6354 | 107.9261 | 2026-02-16 | 2026-02-22 | 2026-03-02 | 2026-03-18 | 2026-04-03 | 2026-04-15
QNM-0098 | QNM Ward 37 — 5G NR n2 Rural | Quang Nam | PAT Complete | VNPT 5G PO2 | 5G NR n78 Macro | expansion | 15.7213 | 108.2424 | 2026-01-24 | 2026-01-30 | 2026-02-07 | 2026-02-23 | 2026-03-11 | 2026-03-23
QNM-0099 | QNM Ward 15 — 5G Expansion n2 | Quang Nam | PAT Complete | VNPT 5G PO2 | 5G NR n78 Rooftop | new | 15.7585 | 108.2896 | 2026-01-13 | 2026-01-19 | 2026-01-27 | 2026-02-12 | 2026-02-28 | 2026-03-12
QNM-0100 | QNM Ward 33 — 5G NR n78 Q-Cell | Quang Nam | PAT Complete | VNPT 5G PO2 | 5G NR n2 Rural | expansion | 15.4371 | 107.9535 | 2026-01-01 | 2026-01-07 | 2026-01-15 | 2026-01-31 | 2026-02-16 | 2026-02-28
QNM-0101 | QNM Ward 11 — 5G Expansion n2 | Quang Nam | PAT Complete | VNPT 5G PO2 | 5G Expansion n2 | expansion | 15.4381 | 107.8933 | 2026-01-08 | 2026-01-14 | 2026-01-22 | 2026-02-07 | 2026-02-23 | 2026-03-07
QNM-0102 | QNM Ward 29 — 5G NR n2 Rural | Quang Nam | PAT Complete | VNPT 5G PO2 | 5G NR n78 Rooftop | new | 15.3046 | 107.7999 | 2026-01-09 | 2026-01-15 | 2026-01-23 | 2026-02-08 | 2026-02-24 | 2026-03-08
QNM-0103 | QNM Ward 07 — 5G NR n78 Macro | Quang Nam | PAT Complete | VNPT 5G PO2 | 5G NR n78 Rooftop | new | 15.4858 | 107.9661 | 2026-02-21 | 2026-02-27 | 2026-03-07 | 2026-03-23 | 2026-04-08 | 2026-04-20
QNM-0104 | QNM Ward 25 — 5G NR n78 Q-Cell | Quang Nam | PAT Complete | VNPT 5G PO2 | 5G NR n78 Q-Cell | new | 15.72 | 107.8096 | 2026-02-12 | 2026-02-18 | 2026-02-26 | 2026-03-14 | 2026-03-30 | 2026-04-11
QNM-0105 | QNM Ward 03 — 5G NR n2 Rural | Quang Nam | On Air Complete | VNPT 5G PO2 | 5G Expansion n2 | new | 15.7315 | 108.3005 | 2026-01-02 | 2026-01-08 | 2026-01-16 | 2026-02-01 | 2026-02-17
QNM-0106 | QNM Ward 21 — 5G Expansion n78 | Quang Nam | PAT Complete | VNPT 5G PO2 | 5G NR n78 Rooftop | new | 15.3244 | 107.925 | 2026-01-24 | 2026-01-30 | 2026-02-07 | 2026-02-23 | 2026-03-11 | 2026-03-23
QNM-0107 | QNM Ward 39 — 5G NR n78 Rooftop | Quang Nam | PAT Complete | VNPT 5G PO2 | 5G NR n78 Q-Cell | new | 15.3222 | 107.8312 | 2026-02-03 | 2026-02-09 | 2026-02-17 | 2026-03-05 | 2026-03-21 | 2026-04-02
QNM-0108 | QNM Ward 17 — 5G NR n78 Q-Cell | Quang Nam | PAT Complete | VNPT 5G PO2 | 5G NR n78 Macro | expansion | 15.7517 | 108.3279 | 2026-01-02 | 2026-01-08 | 2026-01-16 | 2026-02-01 | 2026-02-17 | 2026-03-01
QNM-0109 | QNM Ward 35 — 5G NR n2 Rural | Quang Nam | PAT Complete | VNPT 5G PO2 | 5G NR n78 Macro | new | 15.3225 | 108.26 | 2026-01-26 | 2026-02-01 | 2026-02-09 | 2026-02-25 | 2026-03-13 | 2026-03-25
QNM-0110 | QNM Ward 13 — 5G Expansion n2 | Quang Nam | PAT Complete | VNPT 5G PO2 | 5G Expansion n2 | new | 15.7331 | 107.8086 | 2026-01-31 | 2026-02-06 | 2026-02-14 | 2026-03-02 | 2026-03-18 | 2026-03-30
QNM-0111 | QNM Ward 31 — 5G NR n2 Rural | Quang Nam | PAT Complete | VNPT 5G PO2 | 5G NR n2 Rural | new | 15.5882 | 108.2031 | 2026-02-16 | 2026-02-22 | 2026-03-02 | 2026-03-18 | 2026-04-03 | 2026-04-15
QNM-0112 | QNM Ward 09 — 5G NR n78 Rooftop | Quang Nam | PAT Complete | VNPT 5G PO2 | 5G NR n2 Rural | new | 15.8229 | 107.7475 | 2026-02-21 | 2026-02-27 | 2026-03-07 | 2026-03-23 | 2026-04-08 | 2026-04-20
QNM-0113 | QNM Ward 27 — 5G NR n78 Macro | Quang Nam | PAT Complete | VNPT 5G PO2 | 5G NR n78 Q-Cell | new | 15.8172 | 108.0172 | 2026-02-20 | 2026-02-26 | 2026-03-06 | 2026-03-22 | 2026-04-07 | 2026-04-19
QNM-0114 | QNM Ward 05 — 5G Expansion n2 | Quang Nam | PAT Complete | VNPT 5G PO2 | 5G NR n78 Rooftop | new | 15.6327 | 107.7848 | 2026-02-14 | 2026-02-20 | 2026-02-28 | 2026-03-16 | 2026-04-01 | 2026-04-13
QNM-0115 | QNM Ward 23 — 5G NR n78 Q-Cell | Quang Nam | On Air Complete | VNPT 5G PO2 | 5G NR n78 Rooftop | new | 15.6815 | 108.1049 | 2026-02-01 | 2026-02-07 | 2026-02-15 | 2026-03-03 | 2026-03-19 | 2026-04-30
QNM-0116 | QNM Ward 01 — 5G NR n2 Rural | Quang Nam | PAT Complete | VNPT 5G PO2 | 5G NR n2 Rural | new | 15.3124 | 107.97 | 2026-01-28 | 2026-02-03 | 2026-02-11 | 2026-02-27 | 2026-03-15 | 2026-03-27
QNM-0117 | QNM Ward 19 — 5G NR n78 Rooftop | Quang Nam | PAT Complete | VNPT 5G PO2 | 5G NR n78 Macro | new | 15.5416 | 108.2228 | 2026-02-07 | 2026-02-13 | 2026-02-21 | 2026-03-09 | 2026-03-25 | 2026-04-06
QNM-0118 | QNM Ward 37 — 5G NR n2 Rural | Quang Nam | On Air Complete | VNPT 5G PO2 | 5G NR n78 Macro | new | 15.7622 | 107.919 | 2026-02-05 | 2026-02-11 | 2026-02-19 | 2026-03-07 | 2026-03-23
QNM-0119 | QNM Ward 15 — 5G NR n78 Macro | Quang Nam | PAT Complete | VNPT 5G PO2 | 5G NR n78 Rooftop | expansion | 15.3014 | 108.1991 | 2026-01-16 | 2026-01-22 | 2026-01-30 | 2026-02-15 | 2026-03-03 | 2026-03-15
QNM-0120 | QNM Ward 33 — 5G NR n2 Rural | Quang Nam | PAT Complete | VNPT 5G PO2 | 5G NR n78 Q-Cell | new | 15.6384 | 108.2024 | 2026-01-02 | 2026-01-08 | 2026-01-16 | 2026-02-01 | 2026-02-17 | 2026-03-01
QNM-0121 | QNM Ward 11 — 5G NR n78 Rooftop | Quang Nam | PAT Complete | VNPT 5G PO2 | 5G NR n2 Rural | new | 15.3613 | 107.7344 | 2026-02-22 | 2026-02-28 | 2026-03-08 | 2026-03-24 | 2026-04-09 | 2026-04-21
QNM-0122 | QNM Ward 29 — 5G Expansion n2 | Quang Nam | PAT Complete | VNPT 5G PO2 | 5G NR n2 Rural | expansion | 15.412 | 107.9127 | 2026-02-15 | 2026-02-21 | 2026-03-01 | 2026-03-17 | 2026-04-02 | 2026-04-14
QNM-0123 | QNM Ward 07 — 5G Expansion n2 | Quang Nam | PAT Complete | VNPT 5G PO2 | 5G NR n78 Rooftop | expansion | 15.7454 | 108.0072 | 2026-02-11 | 2026-02-17 | 2026-02-25 | 2026-03-13 | 2026-03-29 | 2026-04-10
QNM-0124 | QNM Ward 25 — 5G NR n2 Rural | Quang Nam | PAT Complete | VNPT 5G PO2 | 5G Expansion n78 | new | 15.4755 | 107.8977 | 2026-02-01 | 2026-02-07 | 2026-02-15 | 2026-03-03 | 2026-03-19 | 2026-03-31
QNM-0125 | QNM Ward 03 — 5G NR n78 Macro | Quang Nam | PAT Complete | VNPT 5G PO2 | 5G Expansion n78 | new | 15.7027 | 108.3057 | 2026-01-01 | 2026-01-07 | 2026-01-15 | 2026-01-31 | 2026-02-16 | 2026-02-28
QNM-0126 | QNM Ward 21 — 5G NR n78 Q-Cell | Quang Nam | PAT Complete | VNPT 5G PO2 | 5G NR n78 Q-Cell | new | 15.6123 | 108.2958 | 2026-02-17 | 2026-02-23 | 2026-03-03 | 2026-03-19 | 2026-04-04 | 2026-04-16
QNM-0127 | QNM Ward 39 — 5G NR n2 Rural | Quang Nam | PAT Complete | VNPT 5G PO2 | 5G NR n2 Rural | new | 15.2988 | 108.2095 | 2026-02-08 | 2026-02-14 | 2026-02-22 | 2026-03-10 | 2026-03-26 | 2026-04-07
QNM-0128 | QNM Ward 17 — 5G Expansion n78 | Quang Nam | PAT Complete | VNPT 5G PO2 | 5G Expansion n2 | new | 15.3677 | 108.1994 | 2026-01-10 | 2026-01-16 | 2026-01-24 | 2026-02-09 | 2026-02-25 | 2026-03-09
QNM-0129 | QNM Ward 35 — 5G Expansion n2 | Quang Nam | PAT Complete | VNPT 5G PO2 | 5G Expansion n78 | expansion | 15.7111 | 108.0888 | 2026-02-18 | 2026-02-24 | 2026-03-04 | 2026-03-20 | 2026-04-05 | 2026-04-17
QNM-0130 | QNM Ward 13 — 5G Expansion n2 | Quang Nam | PAT Complete | VNPT 5G PO2 | 5G Expansion n2 | new | 15.4329 | 108.231 | 2026-02-02 | 2026-02-08 | 2026-02-16 | 2026-03-04 | 2026-03-20 | 2026-04-01
QNM-0131 | QNM Ward 31 — 5G NR n78 Macro | Quang Nam | PAT Complete | VNPT 5G PO2 | 5G NR n78 Q-Cell | expansion | 15.3959 | 107.9058 | 2026-01-15 | 2026-01-21 | 2026-01-29 | 2026-02-14 | 2026-03-02 | 2026-03-14
QNM-0132 | QNM Ward 09 — 5G NR n2 Rural | Quang Nam | PAT Complete | VNPT 5G PO2 | 5G NR n78 Q-Cell | expansion | 15.292 | 108.0774 | 2026-02-23 | 2026-03-01 | 2026-03-09 | 2026-03-25 | 2026-04-10 | 2026-04-22
QNM-0133 | QNM Ward 27 — 5G NR n2 Rural | Quang Nam | PAT Complete | VNPT 5G PO2 | 5G Expansion n78 | new | 15.6722 | 108.0353 | 2026-01-18 | 2026-01-24 | 2026-02-01 | 2026-02-17 | 2026-03-05 | 2026-03-17
QNM-0134 | QNM Ward 05 — 5G Expansion n2 | Quang Nam | PAT Complete | VNPT 5G PO2 | 5G NR n2 Rural | expansion | 15.6835 | 108.0248 | 2026-01-01 | 2026-01-07 | 2026-01-15 | 2026-01-31 | 2026-02-16 | 2026-02-28
QNM-0135 | QNM Ward 23 — 5G NR n78 Q-Cell | Quang Nam | PAT Complete | VNPT 5G PO2 | 5G NR n78 Macro | new | 15.6466 | 108.1531 | 2026-02-10 | 2026-02-16 | 2026-02-24 | 2026-03-12 | 2026-03-28 | 2026-04-09
QNM-0136 | QNM Ward 01 — 5G NR n78 Rooftop | Quang Nam | PAT Complete | VNPT 5G PO2 | 5G Expansion n78 | new | 15.3777 | 107.7025 | 2026-01-03 | 2026-01-09 | 2026-01-17 | 2026-02-02 | 2026-02-18 | 2026-03-02
QNM-0137 | QNM Ward 19 — 5G NR n78 Q-Cell | Quang Nam | PAT Complete | VNPT 5G PO2 | 5G Expansion n78 | expansion | 15.285 | 108.3238 | 2026-02-25 | 2026-03-03 | 2026-03-11 | 2026-03-27 | 2026-04-12 | 2026-04-24
QNM-0138 | QNM Ward 37 — 5G NR n78 Q-Cell | Quang Nam | PAT Complete | VNPT 5G PO2 | 5G NR n78 Q-Cell | new | 15.7194 | 108.1707 | 2026-01-06 | 2026-01-12 | 2026-01-20 | 2026-02-05 | 2026-02-21 | 2026-03-05
QNI-0001 | QNI Ward 29 — 5G NR n2 Rural | Quang Ngai | PAT Complete | VNPT 5G PO2 | 5G NR n2 Rural | new | 14.9087 | 108.6985 | 2026-01-11 | 2026-01-17 | 2026-01-25 | 2026-02-10 | 2026-02-26 | 2026-03-10
QNI-0002 | QNI Ward 07 — 5G NR n78 Q-Cell | Quang Ngai | PAT Complete | VNPT 5G PO2 | 5G NR n2 Rural | expansion | 15.2121 | 108.6649 | 2026-01-14 | 2026-01-20 | 2026-01-28 | 2026-02-13 | 2026-03-01 | 2026-03-13
QNI-0003 | QNI Ward 25 — 5G Expansion n78 | Quang Ngai | On Air Complete | VNPT 5G PO2 | 5G NR n78 Macro | expansion | 15.325 | 109.1041 | 2026-02-20 | 2026-02-26 | 2026-03-06 | 2026-03-22 | 2026-04-07 | 2026-04-28
QNI-0004 | QNI Ward 03 — 5G NR n78 Q-Cell | Quang Ngai | PAT Complete | VNPT 5G PO2 | 5G NR n78 Macro | new | 14.9823 | 108.5939 | 2026-02-05 | 2026-02-11 | 2026-02-19 | 2026-03-07 | 2026-03-23 | 2026-04-04
QNI-0005 | QNI Ward 21 — 5G Expansion n78 | Quang Ngai | PAT Complete | VNPT 5G PO2 | 5G NR n2 Rural | new | 14.862 | 108.6742 | 2026-01-03 | 2026-01-09 | 2026-01-17 | 2026-02-02 | 2026-02-18 | 2026-03-02
QNI-0006 | QNI Ward 39 — 5G NR n78 Macro | Quang Ngai | PAT Complete | VNPT 5G PO2 | 5G Expansion n78 | new | 15.134 | 108.875 | 2026-02-03 | 2026-02-09 | 2026-02-17 | 2026-03-05 | 2026-03-21 | 2026-04-02
QNI-0007 | QNI Ward 17 — 5G NR n78 Rooftop | Quang Ngai | PAT Complete | VNPT 5G PO2 | 5G NR n2 Rural | expansion | 15.039 | 108.9232 | 2026-02-15 | 2026-02-21 | 2026-03-01 | 2026-03-17 | 2026-04-02 | 2026-04-14
QNI-0008 | QNI Ward 35 — 5G NR n78 Rooftop | Quang Ngai | PAT Complete | VNPT 5G PO2 | 5G NR n78 Q-Cell | new | 15.001 | 108.916 | 2026-01-06 | 2026-01-12 | 2026-01-20 | 2026-02-05 | 2026-02-21 | 2026-03-05
QNI-0009 | QNI Ward 13 — 5G NR n78 Rooftop | Quang Ngai | PAT Complete | VNPT 5G PO2 | 5G NR n78 Macro | new | 14.9148 | 109.1128 | 2026-01-24 | 2026-01-30 | 2026-02-07 | 2026-02-23 | 2026-03-11 | 2026-03-23
QNI-0010 | QNI Ward 31 — 5G NR n78 Macro | Quang Ngai | PAT Complete | VNPT 5G PO2 | 5G NR n78 Macro | new | 15.1859 | 108.7893 | 2026-01-04 | 2026-01-10 | 2026-01-18 | 2026-02-03 | 2026-02-19 | 2026-03-03
QNI-0011 | QNI Ward 09 — 5G NR n2 Rural | Quang Ngai | PAT Complete | VNPT 5G PO2 | 5G NR n78 Macro | expansion | 15.2774 | 108.9301 | 2026-01-25 | 2026-01-31 | 2026-02-08 | 2026-02-24 | 2026-03-12 | 2026-03-24
QNI-0012 | QNI Ward 27 — 5G Expansion n78 | Quang Ngai | PAT Complete | VNPT 5G PO2 | 5G Expansion n78 | new | 15.1215 | 108.797 | 2026-01-22 | 2026-01-28 | 2026-02-05 | 2026-02-21 | 2026-03-09 | 2026-03-21
QNI-0013 | QNI Ward 05 — 5G NR n2 Rural | Quang Ngai | PAT Complete | VNPT 5G PO2 | 5G NR n2 Rural | new | 14.9766 | 108.6992 | 2026-01-06 | 2026-01-12 | 2026-01-20 | 2026-02-05 | 2026-02-21 | 2026-03-05
QNI-0014 | QNI Ward 23 — 5G NR n78 Q-Cell | Quang Ngai | PAT Complete | VNPT 5G PO2 | 5G NR n78 Q-Cell | expansion | 14.8993 | 108.9968 | 2026-01-28 | 2026-02-03 | 2026-02-11 | 2026-02-27 | 2026-03-15 | 2026-03-27
QNI-0015 | QNI Ward 01 — 5G Expansion n2 | Quang Ngai | PAT Complete | VNPT 5G PO2 | 5G Expansion n78 | new | 15.2455 | 109.0335 | 2026-01-04 | 2026-01-10 | 2026-01-18 | 2026-02-03 | 2026-02-19 | 2026-03-03
QNI-0016 | QNI Ward 19 — 5G Expansion n2 | Quang Ngai | PAT Complete | VNPT 5G PO2 | 5G Expansion n2 | new | 15.3316 | 108.7774 | 2026-01-05 | 2026-01-11 | 2026-01-19 | 2026-02-04 | 2026-02-20 | 2026-03-04
QNI-0017 | QNI Ward 37 — 5G NR n2 Rural | Quang Ngai | PAT Complete | VNPT 5G PO2 | 5G NR n78 Rooftop | new | 15.3992 | 108.9748 | 2026-01-24 | 2026-01-30 | 2026-02-07 | 2026-02-23 | 2026-03-11 | 2026-03-23
QNI-0018 | QNI Ward 15 — 5G NR n78 Q-Cell | Quang Ngai | PAT Complete | VNPT 5G PO2 | 5G Expansion n78 | new | 15.2306 | 109.0195 | 2026-01-15 | 2026-01-21 | 2026-01-29 | 2026-02-14 | 2026-03-02 | 2026-03-14
QNI-0019 | QNI Ward 33 — 5G Expansion n2 | Quang Ngai | PAT Complete | VNPT 5G PO2 | 5G NR n78 Macro | new | 15.0397 | 109.0654 | 2026-02-08 | 2026-02-14 | 2026-02-22 | 2026-03-10 | 2026-03-26 | 2026-04-07
QNI-0020 | QNI Ward 11 — 5G NR n78 Rooftop | Quang Ngai | PAT Complete | VNPT 5G PO2 | 5G Expansion n2 | expansion | 15.0729 | 108.873 | 2026-02-11 | 2026-02-17 | 2026-02-25 | 2026-03-13 | 2026-03-29 | 2026-04-10
QNI-0021 | QNI Ward 29 — 5G Expansion n78 | Quang Ngai | PAT Complete | VNPT 5G PO2 | 5G NR n78 Q-Cell | expansion | 15.0063 | 108.616 | 2026-02-12 | 2026-02-18 | 2026-02-26 | 2026-03-14 | 2026-03-30 | 2026-04-11
QNI-0022 | QNI Ward 07 — 5G Expansion n2 | Quang Ngai | PAT Complete | VNPT 5G PO2 | 5G NR n2 Rural | new | 14.8647 | 108.6119 | 2026-01-19 | 2026-01-25 | 2026-02-02 | 2026-02-18 | 2026-03-06 | 2026-03-18
QNI-0023 | QNI Ward 25 — 5G Expansion n2 | Quang Ngai | On Air Complete | VNPT 5G PO2 | 5G NR n78 Q-Cell | new | 15.2315 | 109.0194 | 2026-01-10 | 2026-01-16 | 2026-01-24 | 2026-02-09 | 2026-02-25
QNI-0024 | QNI Ward 03 — 5G NR n78 Q-Cell | Quang Ngai | PAT Complete | VNPT 5G PO2 | 5G Expansion n2 | expansion | 15.0992 | 108.8949 | 2026-01-01 | 2026-01-07 | 2026-01-15 | 2026-01-31 | 2026-02-16 | 2026-02-28
QNI-0025 | QNI Ward 21 — 5G NR n78 Rooftop | Quang Ngai | PAT Complete | VNPT 5G PO2 | 5G Expansion n2 | new | 15.3561 | 108.8919 | 2026-01-26 | 2026-02-01 | 2026-02-09 | 2026-02-25 | 2026-03-13 | 2026-03-25
QNI-0026 | QNI Ward 39 — 5G NR n78 Rooftop | Quang Ngai | PAT Complete | VNPT 5G PO2 | 5G Expansion n78 | expansion | 15.2339 | 108.8271 | 2026-02-03 | 2026-02-09 | 2026-02-17 | 2026-03-05 | 2026-03-21 | 2026-04-02
QNI-0027 | QNI Ward 17 — 5G NR n2 Rural | Quang Ngai | PAT Complete | VNPT 5G PO2 | 5G NR n78 Rooftop | new | 15.0963 | 108.8758 | 2026-02-02 | 2026-02-08 | 2026-02-16 | 2026-03-04 | 2026-03-20 | 2026-04-01
QNI-0028 | QNI Ward 35 — 5G Expansion n2 | Quang Ngai | PAT Complete | VNPT 5G PO2 | 5G NR n78 Q-Cell | expansion | 14.9552 | 108.5344 | 2026-01-08 | 2026-01-14 | 2026-01-22 | 2026-02-07 | 2026-02-23 | 2026-03-07
QNI-0029 | QNI Ward 13 — 5G NR n78 Q-Cell | Quang Ngai | PAT Complete | VNPT 5G PO2 | 5G Expansion n78 | new | 14.9211 | 109.0564 | 2026-01-13 | 2026-01-19 | 2026-01-27 | 2026-02-12 | 2026-02-28 | 2026-03-12
QNI-0030 | QNI Ward 31 — 5G NR n78 Macro | Quang Ngai | PAT Complete | VNPT 5G PO2 | 5G NR n78 Macro | expansion | 15.361 | 108.8667 | 2026-01-06 | 2026-01-12 | 2026-01-20 | 2026-02-05 | 2026-02-21 | 2026-03-05
QNI-0031 | QNI Ward 09 — 5G NR n2 Rural | Quang Ngai | PAT Complete | VNPT 5G PO2 | 5G Expansion n2 | new | 15.1443 | 108.7388 | 2026-02-04 | 2026-02-10 | 2026-02-18 | 2026-03-06 | 2026-03-22 | 2026-04-03
QNI-0032 | QNI Ward 27 — 5G NR n78 Q-Cell | Quang Ngai | PAT Complete | VNPT 5G PO2 | 5G Expansion n78 | expansion | 15.225 | 108.5604 | 2026-01-07 | 2026-01-13 | 2026-01-21 | 2026-02-06 | 2026-02-22 | 2026-03-06
QNI-0033 | QNI Ward 05 — 5G Expansion n78 | Quang Ngai | PAT Complete | VNPT 5G PO2 | 5G NR n78 Rooftop | new | 14.9249 | 109.0037 | 2026-01-15 | 2026-01-21 | 2026-01-29 | 2026-02-14 | 2026-03-02 | 2026-03-14
QNI-0034 | QNI Ward 23 — 5G NR n78 Macro | Quang Ngai | PAT Complete | VNPT 5G PO2 | 5G NR n78 Q-Cell | new | 14.9924 | 108.7569 | 2026-01-17 | 2026-01-23 | 2026-01-31 | 2026-02-16 | 2026-03-04 | 2026-03-16
QNI-0035 | QNI Ward 01 — 5G NR n78 Macro | Quang Ngai | PAT Complete | VNPT 5G PO2 | 5G NR n2 Rural | new | 15.004 | 108.9916 | 2026-02-17 | 2026-02-23 | 2026-03-03 | 2026-03-19 | 2026-04-04 | 2026-04-16
QNI-0036 | QNI Ward 19 — 5G NR n78 Rooftop | Quang Ngai | PAT Complete | VNPT 5G PO2 | 5G NR n2 Rural | new | 15.0888 | 108.7643 | 2026-02-15 | 2026-02-21 | 2026-03-01 | 2026-03-17 | 2026-04-02 | 2026-04-14
QNI-0037 | QNI Ward 37 — 5G NR n2 Rural | Quang Ngai | PAT Complete | VNPT 5G PO2 | 5G Expansion n78 | expansion | 15.3795 | 108.8762 | 2026-01-05 | 2026-01-11 | 2026-01-19 | 2026-02-04 | 2026-02-20 | 2026-03-04
QNI-0038 | QNI Ward 15 — 5G Expansion n2 | Quang Ngai | PAT Complete | VNPT 5G PO2 | 5G NR n78 Rooftop | new | 15.0273 | 108.5751 | 2026-01-02 | 2026-01-08 | 2026-01-16 | 2026-02-01 | 2026-02-17 | 2026-03-01
QNI-0039 | QNI Ward 33 — 5G NR n78 Macro | Quang Ngai | PAT Complete | VNPT 5G PO2 | 5G Expansion n2 | expansion | 15.0958 | 109.0719 | 2026-02-08 | 2026-02-14 | 2026-02-22 | 2026-03-10 | 2026-03-26 | 2026-04-07
QNI-0040 | QNI Ward 11 — 5G NR n78 Macro | Quang Ngai | PAT Complete | VNPT 5G PO2 | 5G NR n78 Macro | new | 15.0022 | 108.6512 | 2026-02-03 | 2026-02-09 | 2026-02-17 | 2026-03-05 | 2026-03-21 | 2026-04-02
QNI-0041 | QNI Ward 29 — 5G NR n78 Rooftop | Quang Ngai | PAT Complete | VNPT 5G PO2 | 5G Expansion n78 | new | 14.9276 | 108.5926 | 2026-02-04 | 2026-02-10 | 2026-02-18 | 2026-03-06 | 2026-03-22 | 2026-04-03
QNI-0042 | QNI Ward 07 — 5G Expansion n2 | Quang Ngai | PAT Complete | VNPT 5G PO2 | 5G NR n78 Rooftop | expansion | 15.0707 | 108.999 | 2026-01-14 | 2026-01-20 | 2026-01-28 | 2026-02-13 | 2026-03-01 | 2026-03-13
QNI-0043 | QNI Ward 25 — 5G NR n78 Q-Cell | Quang Ngai | PAT Complete | VNPT 5G PO2 | 5G NR n78 Macro | expansion | 15.3047 | 108.8074 | 2026-02-06 | 2026-02-12 | 2026-02-20 | 2026-03-08 | 2026-03-24 | 2026-04-05
QNI-0044 | QNI Ward 03 — 5G Expansion n2 | Quang Ngai | PAT Complete | VNPT 5G PO2 | 5G NR n78 Q-Cell | new | 14.9942 | 108.9942 | 2026-01-22 | 2026-01-28 | 2026-02-05 | 2026-02-21 | 2026-03-09 | 2026-03-21
QNI-0045 | QNI Ward 21 — 5G Expansion n2 | Quang Ngai | PAT Complete | VNPT 5G PO2 | 5G Expansion n2 | new | 15.0736 | 108.677 | 2026-01-20 | 2026-01-26 | 2026-02-03 | 2026-02-19 | 2026-03-07 | 2026-03-19
QNI-0046 | QNI Ward 39 — 5G NR n2 Rural | Quang Ngai | PAT Complete | VNPT 5G PO2 | 5G Expansion n2 | new | 15.1811 | 108.6417 | 2026-02-15 | 2026-02-21 | 2026-03-01 | 2026-03-17 | 2026-04-02 | 2026-04-14
QNI-0047 | QNI Ward 17 — 5G NR n78 Q-Cell | Quang Ngai | PAT Complete | VNPT 5G PO2 | 5G NR n78 Q-Cell | new | 15.0539 | 109.028 | 2026-01-20 | 2026-01-26 | 2026-02-03 | 2026-02-19 | 2026-03-07 | 2026-03-19
QNI-0048 | QNI Ward 35 — 5G Expansion n78 | Quang Ngai | PAT Complete | VNPT 5G PO2 | 5G NR n78 Q-Cell | new | 15.2015 | 108.8988 | 2026-02-15 | 2026-02-21 | 2026-03-01 | 2026-03-17 | 2026-04-02 | 2026-04-14
QNI-0049 | QNI Ward 13 — 5G NR n78 Macro | Quang Ngai | PAT Complete | VNPT 5G PO2 | 5G NR n2 Rural | expansion | 15.2339 | 109.0199 | 2026-01-22 | 2026-01-28 | 2026-02-05 | 2026-02-21 | 2026-03-09 | 2026-03-21
QNI-0050 | QNI Ward 31 — 5G NR n78 Macro | Quang Ngai | PAT Complete | VNPT 5G PO2 | 5G NR n78 Rooftop | expansion | 15.1781 | 108.6372 | 2026-02-03 | 2026-02-09 | 2026-02-17 | 2026-03-05 | 2026-03-21 | 2026-04-02
QNI-0051 | QNI Ward 09 — 5G Expansion n2 | Quang Ngai | On Air Complete | VNPT 5G PO2 | 5G NR n78 Rooftop | new | 14.9804 | 108.8093 | 2026-01-06 | 2026-01-12 | 2026-01-20 | 2026-02-05 | 2026-02-21
QNI-0052 | QNI Ward 27 — 5G Expansion n78 | Quang Ngai | PAT Complete | VNPT 5G PO2 | 5G Expansion n78 | expansion | 15.2782 | 109.0075 | 2026-01-21 | 2026-01-27 | 2026-02-04 | 2026-02-20 | 2026-03-08 | 2026-03-20
QNI-0053 | QNI Ward 05 — 5G NR n2 Rural | Quang Ngai | PAT Complete | VNPT 5G PO2 | 5G NR n78 Rooftop | new | 14.956 | 108.78 | 2026-01-07 | 2026-01-13 | 2026-01-21 | 2026-02-06 | 2026-02-22 | 2026-03-06
QNI-0054 | QNI Ward 23 — 5G NR n78 Macro | Quang Ngai | PAT Complete | VNPT 5G PO2 | 5G NR n2 Rural | new | 15.2669 | 108.8584 | 2026-01-13 | 2026-01-19 | 2026-01-27 | 2026-02-12 | 2026-02-28 | 2026-03-12
QNI-0055 | QNI Ward 01 — 5G NR n2 Rural | Quang Ngai | PAT Complete | VNPT 5G PO2 | 5G Expansion n78 | new | 14.9234 | 108.9922 | 2026-02-18 | 2026-02-24 | 2026-03-04 | 2026-03-20 | 2026-04-05 | 2026-04-17
QNI-0056 | QNI Ward 19 — 5G NR n2 Rural | Quang Ngai | PAT Complete | VNPT 5G PO2 | 5G NR n78 Q-Cell | new | 15.2954 | 108.7498 | 2026-02-14 | 2026-02-20 | 2026-02-28 | 2026-03-16 | 2026-04-01 | 2026-04-13
QNI-0057 | QNI Ward 37 — 5G NR n2 Rural | Quang Ngai | PAT Complete | VNPT 5G PO2 | 5G NR n78 Macro | expansion | 14.9157 | 108.6676 | 2026-02-15 | 2026-02-21 | 2026-03-01 | 2026-03-17 | 2026-04-02 | 2026-04-14
QNI-0058 | QNI Ward 15 — 5G Expansion n78 | Quang Ngai | PAT Complete | VNPT 5G PO2 | 5G NR n78 Q-Cell | new | 14.9497 | 108.7669 | 2026-02-02 | 2026-02-08 | 2026-02-16 | 2026-03-04 | 2026-03-20 | 2026-04-01
QNI-0059 | QNI Ward 33 — 5G Expansion n78 | Quang Ngai | PAT Complete | VNPT 5G PO2 | 5G Expansion n2 | new | 15.1784 | 108.6316 | 2026-01-10 | 2026-01-16 | 2026-01-24 | 2026-02-09 | 2026-02-25 | 2026-03-09
QNI-0060 | QNI Ward 11 — 5G Expansion n2 | Quang Ngai | On Air Complete | VNPT 5G PO2 | 5G NR n78 Rooftop | expansion | 15.2411 | 108.8451 | 2026-01-24 | 2026-01-30 | 2026-02-07 | 2026-02-23 | 2026-03-11
QNI-0061 | QNI Ward 29 — 5G NR n78 Macro | Quang Ngai | PAT Complete | VNPT 5G PO2 | 5G Expansion n2 | expansion | 15.2684 | 109.018 | 2026-02-16 | 2026-02-22 | 2026-03-02 | 2026-03-18 | 2026-04-03 | 2026-04-15
QNI-0062 | QNI Ward 07 — 5G NR n78 Q-Cell | Quang Ngai | On Air Complete | VNPT 5G PO2 | 5G Expansion n78 | expansion | 14.9572 | 108.6534 | 2026-02-09 | 2026-02-15 | 2026-02-23 | 2026-03-11 | 2026-03-27
QNI-0063 | QNI Ward 25 — 5G NR n2 Rural | Quang Ngai | PAT Complete | VNPT 5G PO2 | 5G NR n78 Rooftop | new | 14.8733 | 109.1168 | 2026-02-13 | 2026-02-19 | 2026-02-27 | 2026-03-15 | 2026-03-31 | 2026-04-12
QNI-0064 | QNI Ward 03 — 5G NR n78 Q-Cell | Quang Ngai | PAT Complete | VNPT 5G PO2 | 5G NR n78 Q-Cell | new | 15.3824 | 108.8118 | 2026-02-06 | 2026-02-12 | 2026-02-20 | 2026-03-08 | 2026-03-24 | 2026-04-05
QNI-0065 | QNI Ward 21 — 5G Expansion n2 | Quang Ngai | PAT Complete | VNPT 5G PO2 | 5G NR n78 Rooftop | expansion | 15.3199 | 109.112 | 2026-02-17 | 2026-02-23 | 2026-03-03 | 2026-03-19 | 2026-04-04 | 2026-04-16
QNI-0066 | QNI Ward 39 — 5G NR n2 Rural | Quang Ngai | PAT Complete | VNPT 5G PO2 | 5G NR n78 Q-Cell | new | 15.0532 | 108.6243 | 2026-01-26 | 2026-02-01 | 2026-02-09 | 2026-02-25 | 2026-03-13 | 2026-03-25
QNI-0067 | QNI Ward 17 — 5G Expansion n2 | Quang Ngai | PAT Complete | VNPT 5G PO2 | 5G Expansion n2 | new | 15.1088 | 108.7331 | 2026-01-22 | 2026-01-28 | 2026-02-05 | 2026-02-21 | 2026-03-09 | 2026-03-21
QNI-0068 | QNI Ward 35 — 5G Expansion n78 | Quang Ngai | PAT Complete | VNPT 5G PO2 | 5G Expansion n78 | expansion | 15.3097 | 109.0795 | 2026-01-08 | 2026-01-14 | 2026-01-22 | 2026-02-07 | 2026-02-23 | 2026-03-07
QNI-0069 | QNI Ward 13 — 5G Expansion n78 | Quang Ngai | PAT Complete | VNPT 5G PO2 | 5G NR n78 Rooftop | expansion | 14.8496 | 108.6697 | 2026-01-26 | 2026-02-01 | 2026-02-09 | 2026-02-25 | 2026-03-13 | 2026-03-25
QNI-0070 | QNI Ward 31 — 5G NR n78 Rooftop | Quang Ngai | PAT Complete | VNPT 5G PO2 | 5G NR n78 Q-Cell | new | 15.3174 | 108.7674 | 2026-02-20 | 2026-02-26 | 2026-03-06 | 2026-03-22 | 2026-04-07 | 2026-04-19
QNI-0071 | QNI Ward 09 — 5G Expansion n2 | Quang Ngai | PAT Complete | VNPT 5G PO2 | 5G NR n78 Q-Cell | expansion | 15.2077 | 108.8138 | 2026-02-21 | 2026-02-27 | 2026-03-07 | 2026-03-23 | 2026-04-08 | 2026-04-20
QNI-0072 | QNI Ward 27 — 5G Expansion n78 | Quang Ngai | PAT Complete | VNPT 5G PO2 | 5G NR n2 Rural | expansion | 14.9148 | 108.9901 | 2026-01-20 | 2026-01-26 | 2026-02-03 | 2026-02-19 | 2026-03-07 | 2026-03-19
QNI-0073 | QNI Ward 05 — 5G Expansion n78 | Quang Ngai | PAT Complete | VNPT 5G PO2 | 5G NR n2 Rural | new | 15.1599 | 108.955 | 2026-02-02 | 2026-02-08 | 2026-02-16 | 2026-03-04 | 2026-03-20 | 2026-04-01
QNI-0074 | QNI Ward 23 — 5G NR n78 Macro | Quang Ngai | On Air Complete | VNPT 5G PO2 | 5G NR n2 Rural | expansion | 15.0215 | 108.7828 | 2026-01-18 | 2026-01-24 | 2026-02-01 | 2026-02-17 | 2026-03-05
QNI-0075 | QNI Ward 01 — 5G NR n78 Rooftop | Quang Ngai | PAT Complete | VNPT 5G PO2 | 5G NR n2 Rural | expansion | 15.2153 | 108.7974 | 2026-02-06 | 2026-02-12 | 2026-02-20 | 2026-03-08 | 2026-03-24 | 2026-04-05
QNI-0076 | QNI Ward 19 — 5G NR n78 Rooftop | Quang Ngai | PAT Complete | VNPT 5G PO2 | 5G Expansion n2 | expansion | 15.1269 | 108.5069 | 2026-02-09 | 2026-02-15 | 2026-02-23 | 2026-03-11 | 2026-03-27 | 2026-04-08
QNI-0077 | QNI Ward 37 — 5G NR n78 Rooftop | Quang Ngai | PAT Complete | VNPT 5G PO2 | 5G Expansion n2 | new | 15.2179 | 109.0154 | 2026-01-18 | 2026-01-24 | 2026-02-01 | 2026-02-17 | 2026-03-05 | 2026-03-17
QNI-0078 | QNI Ward 15 — 5G Expansion n2 | Quang Ngai | PAT Complete | VNPT 5G PO2 | 5G NR n2 Rural | new | 14.8583 | 109.0112 | 2026-02-17 | 2026-02-23 | 2026-03-03 | 2026-03-19 | 2026-04-04 | 2026-04-16
QNI-0079 | QNI Ward 33 — 5G NR n78 Rooftop | Quang Ngai | PAT Complete | VNPT 5G PO2 | 5G NR n78 Q-Cell | new | 15.252 | 108.4963 | 2026-01-10 | 2026-01-16 | 2026-01-24 | 2026-02-09 | 2026-02-25 | 2026-03-09
QNI-0080 | QNI Ward 11 — 5G NR n78 Rooftop | Quang Ngai | PAT Complete | VNPT 5G PO2 | 5G Expansion n2 | new | 14.8984 | 108.618 | 2026-02-15 | 2026-02-21 | 2026-03-01 | 2026-03-17 | 2026-04-02 | 2026-04-14
QNI-0081 | QNI Ward 29 — 5G Expansion n2 | Quang Ngai | PAT Complete | VNPT 5G PO2 | 5G NR n78 Q-Cell | expansion | 15.0367 | 108.6629 | 2026-01-11 | 2026-01-17 | 2026-01-25 | 2026-02-10 | 2026-02-26 | 2026-03-10
QNI-0082 | QNI Ward 07 — 5G Expansion n78 | Quang Ngai | PAT Complete | VNPT 5G PO2 | 5G Expansion n2 | expansion | 15.0044 | 108.5996 | 2026-02-15 | 2026-02-21 | 2026-03-01 | 2026-03-17 | 2026-04-02 | 2026-04-14
QNI-0083 | QNI Ward 25 — 5G Expansion n78 | Quang Ngai | PAT Complete | VNPT 5G PO2 | 5G NR n2 Rural | expansion | 14.9634 | 108.9113 | 2026-02-05 | 2026-02-11 | 2026-02-19 | 2026-03-07 | 2026-03-23 | 2026-04-04
QNI-0084 | QNI Ward 03 — 5G NR n78 Macro | Quang Ngai | PAT Complete | VNPT 5G PO2 | 5G NR n78 Rooftop | new | 15.2807 | 108.6205 | 2026-02-17 | 2026-02-23 | 2026-03-03 | 2026-03-19 | 2026-04-04 | 2026-04-16
QNI-0085 | QNI Ward 21 — 5G NR n78 Q-Cell | Quang Ngai | PAT Complete | VNPT 5G PO2 | 5G Expansion n78 | expansion | 14.8881 | 108.7095 | 2026-02-12 | 2026-02-18 | 2026-02-26 | 2026-03-14 | 2026-03-30 | 2026-04-11
QNI-0086 | QNI Ward 39 — 5G NR n78 Macro | Quang Ngai | PAT Complete | VNPT 5G PO2 | 5G NR n78 Q-Cell | expansion | 15.0932 | 108.7497 | 2026-01-25 | 2026-01-31 | 2026-02-08 | 2026-02-24 | 2026-03-12 | 2026-03-24
QNI-0087 | QNI Ward 17 — 5G NR n78 Macro | Quang Ngai | PAT Complete | VNPT 5G PO2 | 5G Expansion n2 | expansion | 14.9841 | 108.5663 | 2026-01-08 | 2026-01-14 | 2026-01-22 | 2026-02-07 | 2026-02-23 | 2026-03-07
QNI-0088 | QNI Ward 35 — 5G NR n2 Rural | Quang Ngai | PAT Complete | VNPT 5G PO2 | 5G Expansion n78 | new | 14.9742 | 108.9507 | 2026-02-11 | 2026-02-17 | 2026-02-25 | 2026-03-13 | 2026-03-29 | 2026-04-10
QNI-0089 | QNI Ward 13 — 5G NR n2 Rural | Quang Ngai | PAT Complete | VNPT 5G PO2 | 5G Expansion n2 | expansion | 15.2534 | 108.5759 | 2026-02-14 | 2026-02-20 | 2026-02-28 | 2026-03-16 | 2026-04-01 | 2026-04-13
QNI-0090 | QNI Ward 31 — 5G NR n78 Macro | Quang Ngai | PAT Complete | VNPT 5G PO2 | 5G Expansion n2 | expansion | 14.9736 | 108.8889 | 2026-01-19 | 2026-01-25 | 2026-02-02 | 2026-02-18 | 2026-03-06 | 2026-03-18
QNI-0091 | QNI Ward 09 — 5G NR n78 Macro | Quang Ngai | PAT Complete | VNPT 5G PO2 | 5G Expansion n2 | new | 15.2767 | 108.8885 | 2026-02-12 | 2026-02-18 | 2026-02-26 | 2026-03-14 | 2026-03-30 | 2026-04-11
QNI-0092 | QNI Ward 27 — 5G NR n78 Macro | Quang Ngai | PAT Complete | VNPT 5G PO2 | 5G Expansion n2 | new | 15.2825 | 108.7977 | 2026-02-18 | 2026-02-24 | 2026-03-04 | 2026-03-20 | 2026-04-05 | 2026-04-17
QNI-0093 | QNI Ward 05 — 5G NR n78 Rooftop | Quang Ngai | PAT Complete | VNPT 5G PO2 | 5G NR n2 Rural | expansion | 15.1553 | 108.5905 | 2026-02-03 | 2026-02-09 | 2026-02-17 | 2026-03-05 | 2026-03-21 | 2026-04-02
QNI-0094 | QNI Ward 23 — 5G NR n78 Rooftop | Quang Ngai | PAT Complete | VNPT 5G PO2 | 5G NR n78 Rooftop | new | 15.1142 | 108.7316 | 2026-01-02 | 2026-01-08 | 2026-01-16 | 2026-02-01 | 2026-02-17 | 2026-03-01
QNI-0095 | QNI Ward 01 — 5G NR n78 Macro | Quang Ngai | PAT Complete | VNPT 5G PO2 | 5G NR n78 Macro | new | 15.3871 | 108.4801 | 2026-02-07 | 2026-02-13 | 2026-02-21 | 2026-03-09 | 2026-03-25 | 2026-04-06
QNI-0096 | QNI Ward 19 — 5G NR n78 Q-Cell | Quang Ngai | PAT Complete | VNPT 5G PO2 | 5G NR n2 Rural | new | 15.1045 | 108.6108 | 2026-01-22 | 2026-01-28 | 2026-02-05 | 2026-02-21 | 2026-03-09 | 2026-03-21
QNI-0097 | QNI Ward 37 — 5G NR n78 Q-Cell | Quang Ngai | PAT Complete | VNPT 5G PO2 | 5G NR n78 Q-Cell | expansion | 15.1603 | 108.6018 | 2026-02-09 | 2026-02-15 | 2026-02-23 | 2026-03-11 | 2026-03-27 | 2026-04-08
QNI-0098 | QNI Ward 15 — 5G Expansion n78 | Quang Ngai | PAT Complete | VNPT 5G PO2 | 5G NR n78 Macro | expansion | 14.8489 | 108.7397 | 2026-02-03 | 2026-02-09 | 2026-02-17 | 2026-03-05 | 2026-03-21 | 2026-04-02
QNI-0099 | QNI Ward 33 — 5G NR n78 Macro | Quang Ngai | PAT Complete | VNPT 5G PO2 | 5G Expansion n78 | new | 15.0624 | 108.9009 | 2026-01-20 | 2026-01-26 | 2026-02-03 | 2026-02-19 | 2026-03-07 | 2026-03-19
QNI-0100 | QNI Ward 11 — 5G Expansion n78 | Quang Ngai | PAT Complete | VNPT 5G PO2 | 5G NR n78 Rooftop | expansion | 15.055 | 109.1003 | 2026-01-03 | 2026-01-09 | 2026-01-17 | 2026-02-02 | 2026-02-18 | 2026-03-02
QNI-0101 | QNI Ward 29 — 5G Expansion n78 | Quang Ngai | PAT Complete | VNPT 5G PO2 | 5G NR n78 Macro | new | 14.8783 | 109.074 | 2026-02-12 | 2026-02-18 | 2026-02-26 | 2026-03-14 | 2026-03-30 | 2026-04-11
QNI-0102 | QNI Ward 07 — 5G NR n78 Q-Cell | Quang Ngai | PAT Complete | VNPT 5G PO2 | 5G Expansion n78 | new | 15.3193 | 109.0242 | 2026-02-03 | 2026-02-09 | 2026-02-17 | 2026-03-05 | 2026-03-21 | 2026-04-02
QNI-0103 | QNI Ward 25 — 5G NR n78 Q-Cell | Quang Ngai | PAT Complete | VNPT 5G PO2 | 5G NR n78 Macro | new | 15.1657 | 108.9971 | 2026-01-11 | 2026-01-17 | 2026-01-25 | 2026-02-10 | 2026-02-26 | 2026-03-10
QNI-0104 | QNI Ward 03 — 5G NR n78 Macro | Quang Ngai | PAT Complete | VNPT 5G PO2 | 5G Expansion n2 | new | 15.1244 | 108.7217 | 2026-02-15 | 2026-02-21 | 2026-03-01 | 2026-03-17 | 2026-04-02 | 2026-04-14
QNI-0105 | QNI Ward 21 — 5G NR n78 Rooftop | Quang Ngai | PAT Complete | VNPT 5G PO2 | 5G NR n78 Q-Cell | new | 15.3722 | 108.8342 | 2026-02-22 | 2026-02-28 | 2026-03-08 | 2026-03-24 | 2026-04-09 | 2026-04-21
BDI-0001 | BDI Ward 14 — 5G NR n78 Macro | Binh Dinh | PAT Complete | VNPT 5G PO2 | 5G NR n2 Rural | new | 14.0329 | 108.9659 | 2026-01-04 | 2026-01-10 | 2026-01-18 | 2026-02-03 | 2026-02-19 | 2026-03-03
BDI-0002 | BDI Ward 32 — 5G Expansion n78 | Binh Dinh | PAT Complete | VNPT 5G PO2 | 5G NR n78 Rooftop | expansion | 13.5556 | 109.4944 | 2026-01-10 | 2026-01-16 | 2026-01-24 | 2026-02-09 | 2026-02-25 | 2026-03-09
BDI-0003 | BDI Ward 10 — 5G NR n78 Macro | Binh Dinh | PAT Complete | VNPT 5G PO2 | 5G Expansion n2 | new | 13.9391 | 109.3939 | 2026-02-14 | 2026-02-20 | 2026-02-28 | 2026-03-16 | 2026-04-01 | 2026-04-13
BDI-0004 | BDI Ward 28 — 5G NR n78 Rooftop | Binh Dinh | PAT Complete | VNPT 5G PO2 | 5G Expansion n78 | new | 13.9852 | 109.027 | 2026-01-05 | 2026-01-11 | 2026-01-19 | 2026-02-04 | 2026-02-20 | 2026-03-04
BDI-0005 | BDI Ward 06 — 5G NR n2 Rural | Binh Dinh | PAT Complete | VNPT 5G PO2 | 5G NR n2 Rural | new | 14.0001 | 109.0302 | 2026-01-03 | 2026-01-09 | 2026-01-17 | 2026-02-02 | 2026-02-18 | 2026-03-02
BDI-0006 | BDI Ward 24 — 5G NR n78 Q-Cell | Binh Dinh | PAT Complete | VNPT 5G PO2 | 5G Expansion n78 | expansion | 13.7738 | 109.0584 | 2026-02-21 | 2026-02-27 | 2026-03-07 | 2026-03-23 | 2026-04-08 | 2026-04-20
BDI-0007 | BDI Ward 02 — 5G NR n2 Rural | Binh Dinh | PAT Complete | VNPT 5G PO2 | 5G NR n78 Rooftop | new | 13.8921 | 109.3543 | 2026-01-31 | 2026-02-06 | 2026-02-14 | 2026-03-02 | 2026-03-18 | 2026-03-30
BDI-0008 | BDI Ward 20 — 5G Expansion n2 | Binh Dinh | PAT Complete | VNPT 5G PO2 | 5G NR n78 Rooftop | new | 13.5634 | 109.4875 | 2026-02-11 | 2026-02-17 | 2026-02-25 | 2026-03-13 | 2026-03-29 | 2026-04-10
BDI-0009 | BDI Ward 38 — 5G NR n78 Macro | Binh Dinh | PAT Complete | VNPT 5G PO2 | 5G Expansion n2 | new | 13.9859 | 109.2296 | 2026-01-03 | 2026-01-09 | 2026-01-17 | 2026-02-02 | 2026-02-18 | 2026-03-02
BDI-0010 | BDI Ward 16 — 5G NR n78 Rooftop | Binh Dinh | PAT Complete | VNPT 5G PO2 | 5G NR n78 Q-Cell | expansion | 13.9783 | 109.2633 | 2026-01-07 | 2026-01-13 | 2026-01-21 | 2026-02-06 | 2026-02-22 | 2026-03-06
BDI-0011 | BDI Ward 34 — 5G Expansion n78 | Binh Dinh | PAT Complete | VNPT 5G PO2 | 5G NR n2 Rural | expansion | 13.742 | 109.254 | 2026-02-19 | 2026-02-25 | 2026-03-05 | 2026-03-21 | 2026-04-06 | 2026-04-18
BDI-0012 | BDI Ward 12 — 5G NR n2 Rural | Binh Dinh | PAT Complete | VNPT 5G PO2 | 5G NR n78 Macro | expansion | 13.8212 | 109.0232 | 2026-01-16 | 2026-01-22 | 2026-01-30 | 2026-02-15 | 2026-03-03 | 2026-03-15
BDI-0013 | BDI Ward 30 — 5G NR n2 Rural | Binh Dinh | PAT Complete | VNPT 5G PO2 | 5G Expansion n78 | new | 13.7169 | 109.5064 | 2026-01-04 | 2026-01-10 | 2026-01-18 | 2026-02-03 | 2026-02-19 | 2026-03-03
BDI-0014 | BDI Ward 08 — 5G NR n2 Rural | Binh Dinh | PAT Complete | VNPT 5G PO2 | 5G NR n78 Macro | expansion | 13.7546 | 109.4138 | 2026-01-07 | 2026-01-13 | 2026-01-21 | 2026-02-06 | 2026-02-22 | 2026-03-06
BDI-0015 | BDI Ward 26 — 5G NR n2 Rural | Binh Dinh | PAT Complete | VNPT 5G PO2 | 5G NR n2 Rural | expansion | 13.7167 | 108.9345 | 2026-02-03 | 2026-02-09 | 2026-02-17 | 2026-03-05 | 2026-03-21 | 2026-04-02
BDI-0016 | BDI Ward 04 — 5G NR n78 Rooftop | Binh Dinh | PAT Complete | VNPT 5G PO2 | 5G Expansion n2 | expansion | 13.8947 | 109.0269 | 2026-02-21 | 2026-02-27 | 2026-03-07 | 2026-03-23 | 2026-04-08 | 2026-04-20
BDI-0017 | BDI Ward 22 — 5G NR n78 Rooftop | Binh Dinh | PAT Complete | VNPT 5G PO2 | 5G NR n78 Q-Cell | new | 13.5897 | 108.9374 | 2026-01-13 | 2026-01-19 | 2026-01-27 | 2026-02-12 | 2026-02-28 | 2026-03-12
BDI-0018 | BDI Ward 40 — 5G NR n78 Q-Cell | Binh Dinh | PAT Complete | VNPT 5G PO2 | 5G NR n78 Macro | new | 13.6558 | 109.4148 | 2026-02-20 | 2026-02-26 | 2026-03-06 | 2026-03-22 | 2026-04-07 | 2026-04-19
BDI-0019 | BDI Ward 18 — 5G Expansion n2 | Binh Dinh | PAT Complete | VNPT 5G PO2 | 5G Expansion n78 | expansion | 13.5365 | 109.4712 | 2026-02-10 | 2026-02-16 | 2026-02-24 | 2026-03-12 | 2026-03-28 | 2026-04-09
BDI-0020 | BDI Ward 36 — 5G NR n78 Macro | Binh Dinh | PAT Complete | VNPT 5G PO2 | 5G NR n78 Q-Cell | new | 14.0378 | 108.926 | 2026-02-08 | 2026-02-14 | 2026-02-22 | 2026-03-10 | 2026-03-26 | 2026-04-07
BDI-0021 | BDI Ward 14 — 5G NR n78 Rooftop | Binh Dinh | PAT Complete | VNPT 5G PO2 | 5G NR n2 Rural | new | 13.5648 | 109.53 | 2026-02-11 | 2026-02-17 | 2026-02-25 | 2026-03-13 | 2026-03-29 | 2026-04-10
BDI-0022 | BDI Ward 32 — 5G Expansion n78 | Binh Dinh | PAT Complete | VNPT 5G PO2 | 5G NR n78 Q-Cell | expansion | 13.6685 | 109.2458 | 2026-01-11 | 2026-01-17 | 2026-01-25 | 2026-02-10 | 2026-02-26 | 2026-03-10
BDI-0023 | BDI Ward 10 — 5G NR n78 Q-Cell | Binh Dinh | PAT Complete | VNPT 5G PO2 | 5G NR n78 Q-Cell | expansion | 13.963 | 109.3313 | 2026-01-18 | 2026-01-24 | 2026-02-01 | 2026-02-17 | 2026-03-05 | 2026-03-17
BDI-0024 | BDI Ward 28 — 5G Expansion n78 | Binh Dinh | PAT Complete | VNPT 5G PO2 | 5G Expansion n2 | expansion | 13.657 | 109.1241 | 2026-02-11 | 2026-02-17 | 2026-02-25 | 2026-03-13 | 2026-03-29 | 2026-04-10
BDI-0025 | BDI Ward 06 — 5G Expansion n78 | Binh Dinh | PAT Complete | VNPT 5G PO2 | 5G NR n78 Rooftop | expansion | 13.8595 | 109.1239 | 2026-01-14 | 2026-01-20 | 2026-01-28 | 2026-02-13 | 2026-03-01 | 2026-03-13
BDI-0026 | BDI Ward 24 — 5G NR n78 Q-Cell | Binh Dinh | PAT Complete | VNPT 5G PO2 | 5G NR n78 Rooftop | new | 13.661 | 108.9072 | 2026-01-15 | 2026-01-21 | 2026-01-29 | 2026-02-14 | 2026-03-02 | 2026-03-14
BDI-0027 | BDI Ward 02 — 5G Expansion n78 | Binh Dinh | PAT Complete | VNPT 5G PO2 | 5G NR n78 Macro | expansion | 13.9143 | 109.1406 | 2026-01-22 | 2026-01-28 | 2026-02-05 | 2026-02-21 | 2026-03-09 | 2026-03-21
BDI-0028 | BDI Ward 20 — 5G NR n78 Q-Cell | Binh Dinh | PAT Complete | VNPT 5G PO2 | 5G NR n78 Macro | expansion | 13.7844 | 109.3429 | 2026-01-04 | 2026-01-10 | 2026-01-18 | 2026-02-03 | 2026-02-19 | 2026-03-03
BDI-0029 | BDI Ward 38 — 5G Expansion n2 | Binh Dinh | PAT Complete | VNPT 5G PO2 | 5G NR n78 Rooftop | expansion | 13.6178 | 109.1232 | 2026-02-01 | 2026-02-07 | 2026-02-15 | 2026-03-03 | 2026-03-19 | 2026-03-31
BDI-0030 | BDI Ward 16 — 5G NR n78 Q-Cell | Binh Dinh | PAT Complete | VNPT 5G PO2 | 5G NR n78 Rooftop | expansion | 13.9703 | 109.1989 | 2026-01-17 | 2026-01-23 | 2026-01-31 | 2026-02-16 | 2026-03-04 | 2026-03-16
BDI-0031 | BDI Ward 34 — 5G Expansion n2 | Binh Dinh | PAT Complete | VNPT 5G PO2 | 5G NR n2 Rural | new | 13.6177 | 109.2243 | 2026-01-15 | 2026-01-21 | 2026-01-29 | 2026-02-14 | 2026-03-02 | 2026-03-14
BDI-0032 | BDI Ward 12 — 5G Expansion n78 | Binh Dinh | PAT Complete | VNPT 5G PO2 | 5G Expansion n2 | new | 13.8679 | 109.3172 | 2026-02-08 | 2026-02-14 | 2026-02-22 | 2026-03-10 | 2026-03-26 | 2026-04-07
BDI-0033 | BDI Ward 30 — 5G NR n78 Macro | Binh Dinh | PAT Complete | VNPT 5G PO2 | 5G Expansion n78 | expansion | 13.8287 | 109.4462 | 2026-01-17 | 2026-01-23 | 2026-01-31 | 2026-02-16 | 2026-03-04 | 2026-03-16
BDI-0034 | BDI Ward 08 — 5G Expansion n2 | Binh Dinh | PAT Complete | VNPT 5G PO2 | 5G NR n78 Q-Cell | expansion | 13.8721 | 109.4413 | 2026-02-17 | 2026-02-23 | 2026-03-03 | 2026-03-19 | 2026-04-04 | 2026-04-16
BDI-0035 | BDI Ward 26 — 5G Expansion n78 | Binh Dinh | PAT Complete | VNPT 5G PO2 | 5G NR n78 Rooftop | new | 13.8518 | 108.9874 | 2026-01-26 | 2026-02-01 | 2026-02-09 | 2026-02-25 | 2026-03-13 | 2026-03-25
BDI-0036 | BDI Ward 04 — 5G NR n78 Rooftop | Binh Dinh | PAT Complete | VNPT 5G PO2 | 5G NR n2 Rural | expansion | 13.6712 | 109.1481 | 2026-01-07 | 2026-01-13 | 2026-01-21 | 2026-02-06 | 2026-02-22 | 2026-03-06
BDI-0037 | BDI Ward 22 — 5G NR n78 Q-Cell | Binh Dinh | PAT Complete | VNPT 5G PO2 | 5G NR n2 Rural | new | 13.7446 | 109.4955 | 2026-02-17 | 2026-02-23 | 2026-03-03 | 2026-03-19 | 2026-04-04 | 2026-04-16
BDI-0038 | BDI Ward 40 — 5G NR n2 Rural | Binh Dinh | PAT Complete | VNPT 5G PO2 | 5G NR n78 Rooftop | new | 13.5501 | 109.2567 | 2026-01-31 | 2026-02-06 | 2026-02-14 | 2026-03-02 | 2026-03-18 | 2026-03-30
BDI-0039 | BDI Ward 18 — 5G Expansion n2 | Binh Dinh | PAT Complete | VNPT 5G PO2 | 5G NR n78 Q-Cell | new | 13.6395 | 108.9592 | 2026-02-09 | 2026-02-15 | 2026-02-23 | 2026-03-11 | 2026-03-27 | 2026-04-08
BDI-0040 | BDI Ward 36 — 5G Expansion n2 | Binh Dinh | PAT Complete | VNPT 5G PO2 | 5G Expansion n78 | new | 13.7444 | 108.925 | 2026-02-07 | 2026-02-13 | 2026-02-21 | 2026-03-09 | 2026-03-25 | 2026-04-06
BDI-0041 | BDI Ward 14 — 5G Expansion n2 | Binh Dinh | PAT Complete | VNPT 5G PO2 | 5G NR n78 Macro | expansion | 13.8462 | 108.9129 | 2026-01-19 | 2026-01-25 | 2026-02-02 | 2026-02-18 | 2026-03-06 | 2026-03-18
BDI-0042 | BDI Ward 32 — 5G NR n78 Rooftop | Binh Dinh | PAT Complete | VNPT 5G PO2 | 5G NR n78 Rooftop | new | 13.5057 | 109.5336 | 2026-02-02 | 2026-02-08 | 2026-02-16 | 2026-03-04 | 2026-03-20 | 2026-04-01
BDI-0043 | BDI Ward 10 — 5G Expansion n78 | Binh Dinh | PAT Complete | VNPT 5G PO2 | 5G Expansion n78 | new | 13.9972 | 109.3008 | 2026-01-22 | 2026-01-28 | 2026-02-05 | 2026-02-21 | 2026-03-09 | 2026-03-21
BDI-0044 | BDI Ward 28 — 5G NR n78 Macro | Binh Dinh | PAT Complete | VNPT 5G PO2 | 5G Expansion n2 | expansion | 13.7147 | 109.4083 | 2026-01-14 | 2026-01-20 | 2026-01-28 | 2026-02-13 | 2026-03-01 | 2026-03-13
BDI-0045 | BDI Ward 06 — 5G Expansion n2 | Binh Dinh | PAT Complete | VNPT 5G PO2 | 5G NR n78 Macro | expansion | 13.6857 | 109.3224 | 2026-01-12 | 2026-01-18 | 2026-01-26 | 2026-02-11 | 2026-02-27 | 2026-03-11
BDI-0046 | BDI Ward 24 — 5G NR n78 Q-Cell | Binh Dinh | PAT Complete | VNPT 5G PO2 | 5G NR n78 Macro | expansion | 13.6791 | 108.9421 | 2026-01-28 | 2026-02-03 | 2026-02-11 | 2026-02-27 | 2026-03-15 | 2026-03-27
BDI-0047 | BDI Ward 02 — 5G NR n78 Rooftop | Binh Dinh | On Air Complete | VNPT 5G PO2 | 5G NR n2 Rural | new | 13.5399 | 109.2291 | 2026-02-17 | 2026-02-23 | 2026-03-03 | 2026-03-19 | 2026-04-04
BDI-0048 | BDI Ward 20 — 5G Expansion n2 | Binh Dinh | PAT Complete | VNPT 5G PO2 | 5G NR n2 Rural | expansion | 13.8724 | 109.4257 | 2026-02-18 | 2026-02-24 | 2026-03-04 | 2026-03-20 | 2026-04-05 | 2026-04-17
BDI-0049 | BDI Ward 38 — 5G NR n78 Rooftop | Binh Dinh | PAT Complete | VNPT 5G PO2 | 5G NR n78 Macro | new | 13.9031 | 108.9123 | 2026-01-13 | 2026-01-19 | 2026-01-27 | 2026-02-12 | 2026-02-28 | 2026-03-12
BDI-0050 | BDI Ward 16 — 5G NR n78 Macro | Binh Dinh | PAT Complete | VNPT 5G PO2 | 5G NR n78 Macro | new | 13.6912 | 109.378 | 2026-02-20 | 2026-02-26 | 2026-03-06 | 2026-03-22 | 2026-04-07 | 2026-04-19
BDI-0051 | BDI Ward 34 — 5G Expansion n2 | Binh Dinh | PAT Complete | VNPT 5G PO2 | 5G NR n78 Macro | expansion | 13.983 | 109.534 | 2026-01-19 | 2026-01-25 | 2026-02-02 | 2026-02-18 | 2026-03-06 | 2026-03-18
BDI-0052 | BDI Ward 12 — 5G Expansion n78 | Binh Dinh | PAT Complete | VNPT 5G PO2 | 5G NR n78 Q-Cell | new | 13.6038 | 109.1621 | 2026-02-28 | 2026-03-06 | 2026-03-14 | 2026-03-30 | 2026-04-15 | 2026-04-27
BDI-0053 | BDI Ward 30 — 5G NR n78 Macro | Binh Dinh | PAT Complete | VNPT 5G PO2 | 5G NR n78 Macro | new | 13.7802 | 109.345 | 2026-01-10 | 2026-01-16 | 2026-01-24 | 2026-02-09 | 2026-02-25 | 2026-03-09
BDI-0054 | BDI Ward 08 — 5G NR n78 Q-Cell | Binh Dinh | PAT Complete | VNPT 5G PO2 | 5G NR n2 Rural | new | 13.713 | 109.4375 | 2026-02-04 | 2026-02-10 | 2026-02-18 | 2026-03-06 | 2026-03-22 | 2026-04-03
BDI-0055 | BDI Ward 26 — 5G NR n78 Macro | Binh Dinh | PAT Complete | VNPT 5G PO2 | 5G NR n78 Q-Cell | new | 13.6813 | 109.095 | 2026-01-29 | 2026-02-04 | 2026-02-12 | 2026-02-28 | 2026-03-16 | 2026-03-28
BDI-0056 | BDI Ward 04 — 5G NR n78 Macro | Binh Dinh | PAT Complete | VNPT 5G PO2 | 5G NR n78 Rooftop | expansion | 13.6396 | 108.9067 | 2026-01-23 | 2026-01-29 | 2026-02-06 | 2026-02-22 | 2026-03-10 | 2026-03-22
BDI-0057 | BDI Ward 22 — 5G Expansion n78 | Binh Dinh | PAT Complete | VNPT 5G PO2 | 5G NR n78 Macro | new | 13.6076 | 109.5282 | 2026-02-28 | 2026-03-06 | 2026-03-14 | 2026-03-30 | 2026-04-15 | 2026-04-27
BDI-0058 | BDI Ward 40 — 5G NR n78 Rooftop | Binh Dinh | PAT Complete | VNPT 5G PO2 | 5G Expansion n78 | new | 13.6008 | 109.0857 | 2026-01-13 | 2026-01-19 | 2026-01-27 | 2026-02-12 | 2026-02-28 | 2026-03-12
BDI-0059 | BDI Ward 18 — 5G NR n78 Rooftop | Binh Dinh | PAT Complete | VNPT 5G PO2 | 5G NR n78 Rooftop | new | 13.9636 | 109.2441 | 2026-02-20 | 2026-02-26 | 2026-03-06 | 2026-03-22 | 2026-04-07 | 2026-04-19
BDI-0060 | BDI Ward 36 — 5G Expansion n78 | Binh Dinh | PAT Complete | VNPT 5G PO2 | 5G NR n78 Q-Cell | new | 13.7364 | 109.2005 | 2026-01-01 | 2026-01-07 | 2026-01-15 | 2026-01-31 | 2026-02-16 | 2026-02-28
BDI-0061 | BDI Ward 14 — 5G NR n78 Rooftop | Binh Dinh | PAT Complete | VNPT 5G PO2 | 5G NR n78 Rooftop | new | 13.995 | 109.4554 | 2026-02-13 | 2026-02-19 | 2026-02-27 | 2026-03-15 | 2026-03-31 | 2026-04-12
BDI-0062 | BDI Ward 32 — 5G NR n2 Rural | Binh Dinh | On Air Complete | VNPT 5G PO2 | 5G NR n2 Rural | expansion | 13.6677 | 109.0914 | 2026-02-01 | 2026-02-07 | 2026-02-15 | 2026-03-03 | 2026-03-19 | 2026-04-28
BDI-0063 | BDI Ward 10 — 5G NR n78 Rooftop | Binh Dinh | PAT Complete | VNPT 5G PO2 | 5G NR n78 Macro | new | 14.0318 | 109.5048 | 2026-01-10 | 2026-01-16 | 2026-01-24 | 2026-02-09 | 2026-02-25 | 2026-03-09
BDI-0064 | BDI Ward 28 — 5G NR n2 Rural | Binh Dinh | PAT Complete | VNPT 5G PO2 | 5G Expansion n78 | new | 13.6783 | 108.9288 | 2026-01-01 | 2026-01-07 | 2026-01-15 | 2026-01-31 | 2026-02-16 | 2026-02-28
BDI-0065 | BDI Ward 06 — 5G NR n78 Macro | Binh Dinh | PAT Complete | VNPT 5G PO2 | 5G NR n78 Rooftop | expansion | 13.7814 | 109.0617 | 2026-02-13 | 2026-02-19 | 2026-02-27 | 2026-03-15 | 2026-03-31 | 2026-04-12
BDI-0066 | BDI Ward 24 — 5G NR n2 Rural | Binh Dinh | PAT Complete | VNPT 5G PO2 | 5G NR n2 Rural | new | 13.5067 | 109.103 | 2026-01-04 | 2026-01-10 | 2026-01-18 | 2026-02-03 | 2026-02-19 | 2026-03-03
BDI-0067 | BDI Ward 02 — 5G Expansion n2 | Binh Dinh | PAT Complete | VNPT 5G PO2 | 5G NR n78 Q-Cell | new | 14.0148 | 109.253 | 2026-02-09 | 2026-02-15 | 2026-02-23 | 2026-03-11 | 2026-03-27 | 2026-04-08
BDI-0068 | BDI Ward 20 — 5G NR n78 Rooftop | Binh Dinh | PAT Complete | VNPT 5G PO2 | 5G NR n78 Macro | new | 13.9441 | 109.1019 | 2026-01-29 | 2026-02-04 | 2026-02-12 | 2026-02-28 | 2026-03-16 | 2026-03-28
BDI-0069 | BDI Ward 38 — 5G NR n78 Q-Cell | Binh Dinh | PAT Complete | VNPT 5G PO2 | 5G NR n2 Rural | new | 13.7181 | 109.3218 | 2026-01-27 | 2026-02-02 | 2026-02-10 | 2026-02-26 | 2026-03-14 | 2026-03-26
BDI-0070 | BDI Ward 16 — 5G NR n78 Rooftop | Binh Dinh | PAT Complete | VNPT 5G PO2 | 5G NR n78 Macro | new | 14.0087 | 109.3144 | 2026-02-01 | 2026-02-07 | 2026-02-15 | 2026-03-03 | 2026-03-19 | 2026-03-31
BDI-0071 | BDI Ward 34 — 5G Expansion n78 | Binh Dinh | PAT Complete | VNPT 5G PO2 | 5G Expansion n2 | expansion | 13.7327 | 109.4494 | 2026-02-19 | 2026-02-25 | 2026-03-05 | 2026-03-21 | 2026-04-06 | 2026-04-18
BDI-0072 | BDI Ward 12 — 5G Expansion n78 | Binh Dinh | PAT Complete | VNPT 5G PO2 | 5G NR n78 Q-Cell | new | 13.8631 | 109.0049 | 2026-02-19 | 2026-02-25 | 2026-03-05 | 2026-03-21 | 2026-04-06 | 2026-04-18
BDI-0073 | BDI Ward 30 — 5G Expansion n2 | Binh Dinh | PAT Complete | VNPT 5G PO2 | 5G NR n78 Rooftop | new | 13.9727 | 109.0398 | 2026-01-10 | 2026-01-16 | 2026-01-24 | 2026-02-09 | 2026-02-25 | 2026-03-09
BDI-0074 | BDI Ward 08 — 5G Expansion n2 | Binh Dinh | PAT Complete | VNPT 5G PO2 | 5G NR n78 Q-Cell | new | 13.878 | 109.4988 | 2026-01-15 | 2026-01-21 | 2026-01-29 | 2026-02-14 | 2026-03-02 | 2026-03-14
BDI-0075 | BDI Ward 26 — 5G NR n78 Q-Cell | Binh Dinh | PAT Complete | VNPT 5G PO2 | 5G NR n78 Rooftop | new | 13.5703 | 108.9345 | 2026-02-07 | 2026-02-13 | 2026-02-21 | 2026-03-09 | 2026-03-25 | 2026-04-06
BDI-0076 | BDI Ward 04 — 5G NR n78 Rooftop | Binh Dinh | PAT Complete | VNPT 5G PO2 | 5G Expansion n2 | new | 13.8773 | 109.0941 | 2026-01-26 | 2026-02-01 | 2026-02-09 | 2026-02-25 | 2026-03-13 | 2026-03-25
BDI-0077 | BDI Ward 22 — 5G NR n78 Rooftop | Binh Dinh | PAT Complete | VNPT 5G PO2 | 5G NR n78 Macro | expansion | 13.5906 | 108.9291 | 2026-01-30 | 2026-02-05 | 2026-02-13 | 2026-03-01 | 2026-03-17 | 2026-03-29
BDI-0078 | BDI Ward 40 — 5G NR n78 Q-Cell | Binh Dinh | PAT Complete | VNPT 5G PO2 | 5G NR n78 Macro | new | 13.927 | 109.3517 | 2026-01-05 | 2026-01-11 | 2026-01-19 | 2026-02-04 | 2026-02-20 | 2026-03-04
BDI-0079 | BDI Ward 18 — 5G Expansion n2 | Binh Dinh | PAT Complete | VNPT 5G PO2 | 5G Expansion n2 | new | 13.6548 | 109.5357 | 2026-01-31 | 2026-02-06 | 2026-02-14 | 2026-03-02 | 2026-03-18 | 2026-03-30
BDI-0080 | BDI Ward 36 — 5G NR n78 Rooftop | Binh Dinh | PAT Complete | VNPT 5G PO2 | 5G NR n78 Rooftop | new | 14.0238 | 109.1761 | 2026-02-18 | 2026-02-24 | 2026-03-04 | 2026-03-20 | 2026-04-05 | 2026-04-17
BDI-0081 | BDI Ward 14 — 5G Expansion n2 | Binh Dinh | PAT Complete | VNPT 5G PO2 | 5G NR n78 Macro | expansion | 13.5562 | 109.4979 | 2026-02-06 | 2026-02-12 | 2026-02-20 | 2026-03-08 | 2026-03-24 | 2026-04-05
BDI-0082 | BDI Ward 32 — 5G Expansion n78 | Binh Dinh | PAT Complete | VNPT 5G PO2 | 5G NR n2 Rural | expansion | 13.7407 | 109.3804 | 2026-01-09 | 2026-01-15 | 2026-01-23 | 2026-02-08 | 2026-02-24 | 2026-03-08
BDI-0083 | BDI Ward 10 — 5G NR n78 Rooftop | Binh Dinh | PAT Complete | VNPT 5G PO2 | 5G NR n78 Q-Cell | new | 13.7048 | 109.523 | 2026-01-22 | 2026-01-28 | 2026-02-05 | 2026-02-21 | 2026-03-09 | 2026-03-21
BDI-0084 | BDI Ward 28 — 5G NR n2 Rural | Binh Dinh | PAT Complete | VNPT 5G PO2 | 5G NR n78 Macro | expansion | 13.929 | 108.9318 | 2026-02-10 | 2026-02-16 | 2026-02-24 | 2026-03-12 | 2026-03-28 | 2026-04-09
BDI-0085 | BDI Ward 06 — 5G NR n78 Rooftop | Binh Dinh | PAT Complete | VNPT 5G PO2 | 5G NR n78 Macro | expansion | 13.5831 | 108.9905 | 2026-02-22 | 2026-02-28 | 2026-03-08 | 2026-03-24 | 2026-04-09 | 2026-04-21
BDI-0086 | BDI Ward 24 — 5G NR n78 Macro | Binh Dinh | PAT Complete | VNPT 5G PO2 | 5G Expansion n2 | new | 13.9715 | 109.1898 | 2026-02-20 | 2026-02-26 | 2026-03-06 | 2026-03-22 | 2026-04-07 | 2026-04-19
BDI-0087 | BDI Ward 02 — 5G NR n2 Rural | Binh Dinh | PAT Complete | VNPT 5G PO2 | 5G NR n78 Q-Cell | expansion | 13.6633 | 109.2866 | 2026-01-29 | 2026-02-04 | 2026-02-12 | 2026-02-28 | 2026-03-16 | 2026-03-28
BDI-0088 | BDI Ward 20 — 5G NR n78 Q-Cell | Binh Dinh | PAT Complete | VNPT 5G PO2 | 5G Expansion n78 | new | 13.5646 | 109.3851 | 2026-01-05 | 2026-01-11 | 2026-01-19 | 2026-02-04 | 2026-02-20 | 2026-03-04
BDI-0089 | BDI Ward 38 — 5G NR n78 Rooftop | Binh Dinh | PAT Complete | VNPT 5G PO2 | 5G NR n78 Q-Cell | expansion | 14.0311 | 109.3677 | 2026-02-16 | 2026-02-22 | 2026-03-02 | 2026-03-18 | 2026-04-03 | 2026-04-15
BDI-0090 | BDI Ward 16 — 5G NR n2 Rural | Binh Dinh | PAT Complete | VNPT 5G PO2 | 5G NR n78 Q-Cell | expansion | 13.8644 | 109.1616 | 2026-02-07 | 2026-02-13 | 2026-02-21 | 2026-03-09 | 2026-03-25 | 2026-04-06
BDI-0091 | BDI Ward 34 — 5G NR n78 Macro | Binh Dinh | PAT Complete | VNPT 5G PO2 | 5G NR n78 Macro | new | 13.6268 | 109.0647 | 2026-01-20 | 2026-01-26 | 2026-02-03 | 2026-02-19 | 2026-03-07 | 2026-03-19
BDI-0092 | BDI Ward 12 — 5G Expansion n2 | Binh Dinh | PAT Complete | VNPT 5G PO2 | 5G NR n78 Macro | expansion | 13.984 | 109.1303 | 2026-01-06 | 2026-01-12 | 2026-01-20 | 2026-02-05 | 2026-02-21 | 2026-03-05
BDI-0093 | BDI Ward 30 — 5G NR n78 Rooftop | Binh Dinh | PAT Complete | VNPT 5G PO2 | 5G Expansion n2 | new | 13.9639 | 108.9904 | 2026-01-25 | 2026-01-31 | 2026-02-08 | 2026-02-24 | 2026-03-12 | 2026-03-24
BDI-0094 | BDI Ward 08 — 5G NR n78 Rooftop | Binh Dinh | PAT Complete | VNPT 5G PO2 | 5G NR n78 Q-Cell | expansion | 13.6279 | 109.18 | 2026-01-23 | 2026-01-29 | 2026-02-06 | 2026-02-22 | 2026-03-10 | 2026-03-22
BDI-0095 | BDI Ward 26 — 5G NR n78 Q-Cell | Binh Dinh | PAT Complete | VNPT 5G PO2 | 5G NR n78 Macro | new | 13.9949 | 108.9621 | 2026-01-30 | 2026-02-05 | 2026-02-13 | 2026-03-01 | 2026-03-17 | 2026-03-29
BDI-0096 | BDI Ward 04 — 5G NR n78 Q-Cell | Binh Dinh | PAT Complete | VNPT 5G PO2 | 5G NR n2 Rural | new | 13.9046 | 109.0126 | 2026-01-09 | 2026-01-15 | 2026-01-23 | 2026-02-08 | 2026-02-24 | 2026-03-08
BDI-0097 | BDI Ward 22 — 5G Expansion n78 | Binh Dinh | PAT Complete | VNPT 5G PO2 | 5G NR n78 Macro | new | 13.8904 | 109.263 | 2026-02-08 | 2026-02-14 | 2026-02-22 | 2026-03-10 | 2026-03-26 | 2026-04-07
BDI-0098 | BDI Ward 40 — 5G Expansion n2 | Binh Dinh | PAT Complete | VNPT 5G PO2 | 5G NR n78 Rooftop | new | 13.7323 | 109.1457 | 2026-02-28 | 2026-03-06 | 2026-03-14 | 2026-03-30 | 2026-04-15 | 2026-04-27
BDI-0099 | BDI Ward 18 — 5G NR n2 Rural | Binh Dinh | PAT Complete | VNPT 5G PO2 | 5G Expansion n78 | new | 13.7411 | 109.2482 | 2026-02-21 | 2026-02-27 | 2026-03-07 | 2026-03-23 | 2026-04-08 | 2026-04-20
BDI-0100 | BDI Ward 36 — 5G NR n78 Rooftop | Binh Dinh | PAT Complete | VNPT 5G PO2 | 5G NR n78 Rooftop | new | 13.9367 | 109.18 | 2026-01-24 | 2026-01-30 | 2026-02-07 | 2026-02-23 | 2026-03-11 | 2026-03-23
BDI-0101 | BDI Ward 14 — 5G Expansion n2 | Binh Dinh | PAT Complete | VNPT 5G PO2 | 5G NR n78 Rooftop | new | 14.0587 | 109.3715 | 2026-01-12 | 2026-01-18 | 2026-01-26 | 2026-02-11 | 2026-02-27 | 2026-03-11
BDI-0102 | BDI Ward 32 — 5G NR n78 Rooftop | Binh Dinh | PAT Complete | VNPT 5G PO2 | 5G NR n78 Macro | expansion | 14.0457 | 108.986 | 2026-02-08 | 2026-02-14 | 2026-02-22 | 2026-03-10 | 2026-03-26 | 2026-04-07
BDI-0103 | BDI Ward 10 — 5G Expansion n78 | Binh Dinh | On Air Complete | VNPT 5G PO2 | 5G NR n78 Q-Cell | expansion | 13.904 | 108.9625 | 2026-02-02 | 2026-02-08 | 2026-02-16 | 2026-03-04 | 2026-03-20
BDI-0104 | BDI Ward 28 — 5G NR n78 Rooftop | Binh Dinh | PAT Complete | VNPT 5G PO2 | 5G NR n2 Rural | expansion | 13.7454 | 109.1797 | 2026-02-09 | 2026-02-15 | 2026-02-23 | 2026-03-11 | 2026-03-27 | 2026-04-08
BDI-0105 | BDI Ward 06 — 5G NR n78 Rooftop | Binh Dinh | PAT Complete | VNPT 5G PO2 | 5G NR n78 Q-Cell | expansion | 13.685 | 109.1135 | 2026-01-06 | 2026-01-12 | 2026-01-20 | 2026-02-05 | 2026-02-21 | 2026-03-05
BDI-0106 | BDI Ward 24 — 5G NR n78 Macro | Binh Dinh | PAT Complete | VNPT 5G PO2 | 5G NR n78 Q-Cell | expansion | 13.8634 | 109.002 | 2026-01-17 | 2026-01-23 | 2026-01-31 | 2026-02-16 | 2026-03-04 | 2026-03-16
BDI-0107 | BDI Ward 02 — 5G NR n2 Rural | Binh Dinh | PAT Complete | VNPT 5G PO2 | 5G Expansion n78 | expansion | 13.6322 | 109.3734 | 2026-01-11 | 2026-01-17 | 2026-01-25 | 2026-02-10 | 2026-02-26 | 2026-03-10
BDI-0108 | BDI Ward 20 — 5G NR n2 Rural | Binh Dinh | PAT Complete | VNPT 5G PO2 | 5G NR n2 Rural | expansion | 14.0323 | 109.412 | 2026-01-06 | 2026-01-12 | 2026-01-20 | 2026-02-05 | 2026-02-21 | 2026-03-05
BDI-0109 | BDI Ward 38 — 5G Expansion n78 | Binh Dinh | PAT Complete | VNPT 5G PO2 | 5G NR n78 Macro | new | 13.726 | 109.3864 | 2026-01-13 | 2026-01-19 | 2026-01-27 | 2026-02-12 | 2026-02-28 | 2026-03-12
BDI-0110 | BDI Ward 16 — 5G NR n78 Rooftop | Binh Dinh | PAT Complete | VNPT 5G PO2 | 5G NR n78 Rooftop | expansion | 13.5512 | 109.4052 | 2026-01-22 | 2026-01-28 | 2026-02-05 | 2026-02-21 | 2026-03-09 | 2026-03-21
BDI-0111 | BDI Ward 34 — 5G NR n78 Rooftop | Binh Dinh | On Air Complete | VNPT 5G PO2 | 5G NR n78 Macro | expansion | 13.7179 | 109.3085 | 2026-02-13 | 2026-02-19 | 2026-02-27 | 2026-03-15 | 2026-03-31
BDI-0112 | BDI Ward 12 — 5G NR n2 Rural | Binh Dinh | PAT Complete | VNPT 5G PO2 | 5G NR n78 Q-Cell | new | 14.0377 | 109.4015 | 2026-01-22 | 2026-01-28 | 2026-02-05 | 2026-02-21 | 2026-03-09 | 2026-03-21
BDI-0113 | BDI Ward 30 — 5G NR n78 Rooftop | Binh Dinh | PAT Complete | VNPT 5G PO2 | 5G NR n78 Q-Cell | expansion | 14.0027 | 109.2289 | 2026-02-06 | 2026-02-12 | 2026-02-20 | 2026-03-08 | 2026-03-24 | 2026-04-05
BDI-0114 | BDI Ward 08 — 5G Expansion n2 | Binh Dinh | PAT Complete | VNPT 5G PO2 | 5G Expansion n2 | new | 13.5283 | 109.0424 | 2026-02-01 | 2026-02-07 | 2026-02-15 | 2026-03-03 | 2026-03-19 | 2026-03-31
BDI-0115 | BDI Ward 26 — 5G NR n78 Q-Cell | Binh Dinh | PAT Complete | VNPT 5G PO2 | 5G NR n78 Q-Cell | new | 13.521 | 109.4584 | 2026-02-19 | 2026-02-25 | 2026-03-05 | 2026-03-21 | 2026-04-06 | 2026-04-18
BDI-0116 | BDI Ward 04 — 5G NR n78 Rooftop | Binh Dinh | PAT Complete | VNPT 5G PO2 | 5G Expansion n78 | new | 13.7703 | 109.4102 | 2026-02-07 | 2026-02-13 | 2026-02-21 | 2026-03-09 | 2026-03-25 | 2026-04-06
BDI-0117 | BDI Ward 22 — 5G Expansion n2 | Binh Dinh | PAT Complete | VNPT 5G PO2 | 5G NR n78 Q-Cell | new | 13.5798 | 108.9021 | 2026-01-25 | 2026-01-31 | 2026-02-08 | 2026-02-24 | 2026-03-12 | 2026-03-24
BDI-0118 | BDI Ward 40 — 5G NR n78 Rooftop | Binh Dinh | PAT Complete | VNPT 5G PO2 | 5G NR n78 Macro | new | 13.9395 | 109.5372 | 2026-01-10 | 2026-01-16 | 2026-01-24 | 2026-02-09 | 2026-02-25 | 2026-03-09
BDI-0119 | BDI Ward 18 — 5G Expansion n2 | Binh Dinh | PAT Complete | VNPT 5G PO2 | 5G Expansion n78 | new | 13.8547 | 109.1366 | 2026-01-26 | 2026-02-01 | 2026-02-09 | 2026-02-25 | 2026-03-13 | 2026-03-25
BDI-0120 | BDI Ward 36 — 5G NR n78 Q-Cell | Binh Dinh | PAT Complete | VNPT 5G PO2 | 5G NR n78 Rooftop | new | 13.9881 | 109.5173 | 2026-01-04 | 2026-01-10 | 2026-01-18 | 2026-02-03 | 2026-02-19 | 2026-03-03
BDI-0121 | BDI Ward 14 — 5G Expansion n78 | Binh Dinh | PAT Complete | VNPT 5G PO2 | 5G NR n78 Q-Cell | new | 13.9007 | 109.2797 | 2026-02-10 | 2026-02-16 | 2026-02-24 | 2026-03-12 | 2026-03-28 | 2026-04-09
BDI-0122 | BDI Ward 32 — 5G Expansion n78 | Binh Dinh | PAT Complete | VNPT 5G PO2 | 5G Expansion n2 | new | 13.615 | 109.5025 | 2026-01-20 | 2026-01-26 | 2026-02-03 | 2026-02-19 | 2026-03-07 | 2026-03-19
BDI-0123 | BDI Ward 10 — 5G NR n78 Rooftop | Binh Dinh | On Air Complete | VNPT 5G PO2 | 5G NR n78 Q-Cell | expansion | 13.7231 | 109.291 | 2026-01-28 | 2026-02-03 | 2026-02-11 | 2026-02-27 | 2026-03-15
BDI-0124 | BDI Ward 28 — 5G NR n2 Rural | Binh Dinh | PAT Complete | VNPT 5G PO2 | 5G NR n2 Rural | new | 13.5835 | 109.0403 | 2026-01-07 | 2026-01-13 | 2026-01-21 | 2026-02-06 | 2026-02-22 | 2026-03-06
BDI-0125 | BDI Ward 06 — 5G Expansion n2 | Binh Dinh | PAT Complete | VNPT 5G PO2 | 5G NR n2 Rural | new | 14.0343 | 108.9373 | 2026-01-21 | 2026-01-27 | 2026-02-04 | 2026-02-20 | 2026-03-08 | 2026-03-20
BDI-0126 | BDI Ward 24 — 5G NR n78 Macro | Binh Dinh | PAT Complete | VNPT 5G PO2 | 5G NR n78 Q-Cell | expansion | 13.5766 | 109.2322 | 2026-01-22 | 2026-01-28 | 2026-02-05 | 2026-02-21 | 2026-03-09 | 2026-03-21
BDI-0127 | BDI Ward 02 — 5G NR n78 Rooftop | Binh Dinh | PAT Complete | VNPT 5G PO2 | 5G NR n78 Rooftop | new | 13.6387 | 109.3039 | 2026-01-06 | 2026-01-12 | 2026-01-20 | 2026-02-05 | 2026-02-21 | 2026-03-05
PHY-0001 | PHY Ward 21 — 5G NR n78 Rooftop | Phu Yen | PAT Complete | VNPT 5G PO2 | 5G NR n78 Q-Cell | new | 13.1428 | 109.0547 | 2026-02-16 | 2026-02-22 | 2026-03-02 | 2026-03-18 | 2026-04-03 | 2026-04-15
PHY-0002 | PHY Ward 39 — 5G Expansion n78 | Phu Yen | PAT Complete | VNPT 5G PO2 | 5G NR n78 Macro | expansion | 13.0084 | 109.2462 | 2026-01-03 | 2026-01-09 | 2026-01-17 | 2026-02-02 | 2026-02-18 | 2026-03-02
PHY-0003 | PHY Ward 17 — 5G NR n78 Q-Cell | Phu Yen | PAT Complete | VNPT 5G PO2 | 5G NR n78 Rooftop | new | 13.3577 | 109.085 | 2026-01-20 | 2026-01-26 | 2026-02-03 | 2026-02-19 | 2026-03-07 | 2026-03-19
PHY-0004 | PHY Ward 35 — 5G NR n78 Macro | Phu Yen | PAT Complete | VNPT 5G PO2 | 5G Expansion n2 | new | 13.2274 | 109.267 | 2026-02-22 | 2026-02-28 | 2026-03-08 | 2026-03-24 | 2026-04-09 | 2026-04-21
PHY-0005 | PHY Ward 13 — 5G NR n2 Rural | Phu Yen | PAT Complete | VNPT 5G PO2 | 5G NR n78 Macro | new | 12.8494 | 109.047 | 2026-02-01 | 2026-02-07 | 2026-02-15 | 2026-03-03 | 2026-03-19 | 2026-03-31
PHY-0006 | PHY Ward 31 — 5G Expansion n2 | Phu Yen | PAT Complete | VNPT 5G PO2 | 5G NR n78 Rooftop | expansion | 13.2134 | 109.4586 | 2026-02-24 | 2026-03-02 | 2026-03-10 | 2026-03-26 | 2026-04-11 | 2026-04-23
PHY-0007 | PHY Ward 09 — 5G NR n2 Rural | Phu Yen | PAT Complete | VNPT 5G PO2 | 5G NR n2 Rural | new | 13.1185 | 109.1098 | 2026-01-02 | 2026-01-08 | 2026-01-16 | 2026-02-01 | 2026-02-17 | 2026-03-01
PHY-0008 | PHY Ward 27 — 5G Expansion n78 | Phu Yen | PAT Complete | VNPT 5G PO2 | 5G NR n78 Rooftop | new | 13.1729 | 109.4388 | 2026-01-03 | 2026-01-09 | 2026-01-17 | 2026-02-02 | 2026-02-18 | 2026-03-02
PHY-0009 | PHY Ward 05 — 5G NR n78 Q-Cell | Phu Yen | PAT Complete | VNPT 5G PO2 | 5G Expansion n2 | expansion | 12.9408 | 109.3003 | 2026-01-30 | 2026-02-05 | 2026-02-13 | 2026-03-01 | 2026-03-17 | 2026-03-29
PHY-0010 | PHY Ward 23 — 5G Expansion n78 | Phu Yen | PAT Complete | VNPT 5G PO2 | 5G NR n78 Rooftop | new | 13.1501 | 109.1967 | 2026-01-27 | 2026-02-02 | 2026-02-10 | 2026-02-26 | 2026-03-14 | 2026-03-26
PHY-0011 | PHY Ward 01 — 5G NR n78 Q-Cell | Phu Yen | PAT Complete | VNPT 5G PO2 | 5G NR n78 Rooftop | new | 12.9217 | 109.026 | 2026-01-29 | 2026-02-04 | 2026-02-12 | 2026-02-28 | 2026-03-16 | 2026-03-28
PHY-0012 | PHY Ward 19 — 5G NR n78 Macro | Phu Yen | PAT Complete | VNPT 5G PO2 | 5G Expansion n78 | expansion | 12.9029 | 109.3625 | 2026-01-25 | 2026-01-31 | 2026-02-08 | 2026-02-24 | 2026-03-12 | 2026-03-24
PHY-0013 | PHY Ward 37 — 5G NR n78 Rooftop | Phu Yen | PAT Complete | VNPT 5G PO2 | 5G NR n78 Q-Cell | expansion | 13.1357 | 109.5619 | 2026-01-20 | 2026-01-26 | 2026-02-03 | 2026-02-19 | 2026-03-07 | 2026-03-19
PHY-0014 | PHY Ward 15 — 5G NR n78 Q-Cell | Phu Yen | PAT Complete | VNPT 5G PO2 | 5G Expansion n78 | new | 13.1382 | 109.3017 | 2026-01-04 | 2026-01-10 | 2026-01-18 | 2026-02-03 | 2026-02-19 | 2026-03-03
PHY-0015 | PHY Ward 33 — 5G Expansion n2 | Phu Yen | On Air Complete | VNPT 5G PO2 | 5G NR n78 Macro | expansion | 13.1852 | 109.5191 | 2026-02-22 | 2026-02-28 | 2026-03-08 | 2026-03-24 | 2026-04-09
PHY-0016 | PHY Ward 11 — 5G NR n2 Rural | Phu Yen | PAT Complete | VNPT 5G PO2 | 5G Expansion n78 | new | 13.1202 | 109.0904 | 2026-02-08 | 2026-02-14 | 2026-02-22 | 2026-03-10 | 2026-03-26 | 2026-04-07
PHY-0017 | PHY Ward 29 — 5G NR n2 Rural | Phu Yen | PAT Complete | VNPT 5G PO2 | 5G NR n78 Rooftop | expansion | 13.1119 | 109.5003 | 2026-01-26 | 2026-02-01 | 2026-02-09 | 2026-02-25 | 2026-03-13 | 2026-03-25
PHY-0018 | PHY Ward 07 — 5G NR n78 Macro | Phu Yen | PAT Complete | VNPT 5G PO2 | 5G NR n78 Q-Cell | new | 12.8551 | 109.318 | 2026-02-16 | 2026-02-22 | 2026-03-02 | 2026-03-18 | 2026-04-03 | 2026-04-15
PHY-0019 | PHY Ward 25 — 5G NR n78 Macro | Phu Yen | PAT Complete | VNPT 5G PO2 | 5G NR n78 Q-Cell | new | 12.8848 | 109.0377 | 2026-02-22 | 2026-02-28 | 2026-03-08 | 2026-03-24 | 2026-04-09 | 2026-04-21
PHY-0020 | PHY Ward 03 — 5G Expansion n78 | Phu Yen | PAT Complete | VNPT 5G PO2 | 5G NR n78 Q-Cell | expansion | 12.9741 | 109.3281 | 2026-01-30 | 2026-02-05 | 2026-02-13 | 2026-03-01 | 2026-03-17 | 2026-03-29
PHY-0021 | PHY Ward 21 — 5G NR n2 Rural | Phu Yen | On Air Complete | VNPT 5G PO2 | 5G NR n78 Q-Cell | new | 13.1049 | 109.5712 | 2026-02-22 | 2026-02-28 | 2026-03-08 | 2026-03-24 | 2026-04-09
PHY-0022 | PHY Ward 39 — 5G NR n78 Q-Cell | Phu Yen | PAT Complete | VNPT 5G PO2 | 5G NR n2 Rural | new | 13.3542 | 109.4656 | 2026-02-07 | 2026-02-13 | 2026-02-21 | 2026-03-09 | 2026-03-25 | 2026-04-06
PHY-0023 | PHY Ward 17 — 5G NR n78 Macro | Phu Yen | PAT Complete | VNPT 5G PO2 | 5G Expansion n78 | expansion | 12.9119 | 109.6041 | 2026-01-27 | 2026-02-02 | 2026-02-10 | 2026-02-26 | 2026-03-14 | 2026-03-26
PHY-0024 | PHY Ward 35 — 5G Expansion n78 | Phu Yen | PAT Complete | VNPT 5G PO2 | 5G NR n78 Q-Cell | new | 13.1439 | 109.1967 | 2026-02-01 | 2026-02-07 | 2026-02-15 | 2026-03-03 | 2026-03-19 | 2026-03-31
PHY-0025 | PHY Ward 13 — 5G NR n78 Q-Cell | Phu Yen | PAT Complete | VNPT 5G PO2 | 5G NR n78 Macro | expansion | 13.1949 | 109.4836 | 2026-02-02 | 2026-02-08 | 2026-02-16 | 2026-03-04 | 2026-03-20 | 2026-04-01
PHY-0026 | PHY Ward 31 — 5G NR n78 Q-Cell | Phu Yen | PAT Complete | VNPT 5G PO2 | 5G NR n78 Q-Cell | expansion | 13.1076 | 109.4414 | 2026-02-16 | 2026-02-22 | 2026-03-02 | 2026-03-18 | 2026-04-03 | 2026-04-15
PHY-0027 | PHY Ward 09 — 5G NR n78 Q-Cell | Phu Yen | PAT Complete | VNPT 5G PO2 | 5G NR n78 Rooftop | expansion | 13.0803 | 109.2537 | 2026-02-15 | 2026-02-21 | 2026-03-01 | 2026-03-17 | 2026-04-02 | 2026-04-14
PHY-0028 | PHY Ward 27 — 5G Expansion n2 | Phu Yen | PAT Complete | VNPT 5G PO2 | 5G Expansion n2 | new | 13.3629 | 109.307 | 2026-02-28 | 2026-03-06 | 2026-03-14 | 2026-03-30 | 2026-04-15 | 2026-04-27
PHY-0029 | PHY Ward 05 — 5G NR n78 Macro | Phu Yen | PAT Complete | VNPT 5G PO2 | 5G NR n78 Rooftop | new | 13.2113 | 109.1605 | 2026-02-12 | 2026-02-18 | 2026-02-26 | 2026-03-14 | 2026-03-30 | 2026-04-11
PHY-0030 | PHY Ward 23 — 5G NR n2 Rural | Phu Yen | PAT Complete | VNPT 5G PO2 | 5G NR n78 Rooftop | expansion | 13.055 | 109.2594 | 2026-01-31 | 2026-02-06 | 2026-02-14 | 2026-03-02 | 2026-03-18 | 2026-03-30
PHY-0031 | PHY Ward 01 — 5G NR n2 Rural | Phu Yen | PAT Complete | VNPT 5G PO2 | 5G NR n78 Q-Cell | new | 12.9919 | 109.015 | 2026-02-01 | 2026-02-07 | 2026-02-15 | 2026-03-03 | 2026-03-19 | 2026-03-31
PHY-0032 | PHY Ward 19 — 5G NR n78 Rooftop | Phu Yen | PAT Complete | VNPT 5G PO2 | 5G NR n2 Rural | new | 13.1818 | 109.1782 | 2026-02-12 | 2026-02-18 | 2026-02-26 | 2026-03-14 | 2026-03-30 | 2026-04-11
PHY-0033 | PHY Ward 37 — 5G NR n78 Rooftop | Phu Yen | PAT Complete | VNPT 5G PO2 | 5G Expansion n2 | new | 12.859 | 109.4217 | 2026-02-13 | 2026-02-19 | 2026-02-27 | 2026-03-15 | 2026-03-31 | 2026-04-12
PHY-0034 | PHY Ward 15 — 5G Expansion n2 | Phu Yen | PAT Complete | VNPT 5G PO2 | 5G NR n2 Rural | new | 12.8691 | 109.3995 | 2026-01-06 | 2026-01-12 | 2026-01-20 | 2026-02-05 | 2026-02-21 | 2026-03-05
PHY-0035 | PHY Ward 33 — 5G NR n78 Q-Cell | Phu Yen | PAT Complete | VNPT 5G PO2 | 5G NR n2 Rural | new | 13.2703 | 109.347 | 2026-02-28 | 2026-03-06 | 2026-03-14 | 2026-03-30 | 2026-04-15 | 2026-04-27
PHY-0036 | PHY Ward 11 — 5G NR n78 Q-Cell | Phu Yen | PAT Complete | VNPT 5G PO2 | 5G Expansion n2 | new | 13.2089 | 109.2628 | 2026-01-17 | 2026-01-23 | 2026-01-31 | 2026-02-16 | 2026-03-04 | 2026-03-16
PHY-0037 | PHY Ward 29 — 5G NR n2 Rural | Phu Yen | PAT Complete | VNPT 5G PO2 | 5G NR n78 Rooftop | new | 13.1496 | 109.617 | 2026-02-16 | 2026-02-22 | 2026-03-02 | 2026-03-18 | 2026-04-03 | 2026-04-15
PHY-0038 | PHY Ward 07 — 5G NR n2 Rural | Phu Yen | PAT Complete | VNPT 5G PO2 | 5G Expansion n78 | expansion | 12.8206 | 109.0973 | 2026-01-02 | 2026-01-08 | 2026-01-16 | 2026-02-01 | 2026-02-17 | 2026-03-01
PHY-0039 | PHY Ward 25 — 5G NR n78 Macro | Phu Yen | PAT Complete | VNPT 5G PO2 | 5G Expansion n78 | new | 12.8383 | 109.1518 | 2026-02-15 | 2026-02-21 | 2026-03-01 | 2026-03-17 | 2026-04-02 | 2026-04-14
PHY-0040 | PHY Ward 03 — 5G NR n78 Macro | Phu Yen | PAT Complete | VNPT 5G PO2 | 5G NR n78 Q-Cell | expansion | 12.8787 | 109.3952 | 2026-02-02 | 2026-02-08 | 2026-02-16 | 2026-03-04 | 2026-03-20 | 2026-04-01
PHY-0041 | PHY Ward 21 — 5G NR n2 Rural | Phu Yen | PAT Complete | VNPT 5G PO2 | 5G Expansion n2 | expansion | 13.1363 | 109.5752 | 2026-02-18 | 2026-02-24 | 2026-03-04 | 2026-03-20 | 2026-04-05 | 2026-04-17
PHY-0042 | PHY Ward 39 — 5G Expansion n78 | Phu Yen | PAT Complete | VNPT 5G PO2 | 5G NR n78 Q-Cell | new | 13.2737 | 109.125 | 2026-02-21 | 2026-02-27 | 2026-03-07 | 2026-03-23 | 2026-04-08 | 2026-04-20
PHY-0043 | PHY Ward 17 — 5G NR n2 Rural | Phu Yen | PAT Complete | VNPT 5G PO2 | 5G NR n2 Rural | expansion | 13.1446 | 109.3748 | 2026-01-08 | 2026-01-14 | 2026-01-22 | 2026-02-07 | 2026-02-23 | 2026-03-07
PHY-0044 | PHY Ward 35 — 5G Expansion n78 | Phu Yen | PAT Complete | VNPT 5G PO2 | 5G NR n78 Macro | new | 13.3292 | 109.4542 | 2026-02-02 | 2026-02-08 | 2026-02-16 | 2026-03-04 | 2026-03-20 | 2026-04-01
PHY-0045 | PHY Ward 13 — 5G NR n78 Q-Cell | Phu Yen | PAT Complete | VNPT 5G PO2 | 5G Expansion n78 | expansion | 13.1899 | 109.606 | 2026-01-28 | 2026-02-03 | 2026-02-11 | 2026-02-27 | 2026-03-15 | 2026-03-27
PHY-0046 | PHY Ward 31 — 5G NR n78 Q-Cell | Phu Yen | PAT Complete | VNPT 5G PO2 | 5G NR n2 Rural | new | 12.9928 | 109.5007 | 2026-02-03 | 2026-02-09 | 2026-02-17 | 2026-03-05 | 2026-03-21 | 2026-04-02
PHY-0047 | PHY Ward 09 — 5G Expansion n2 | Phu Yen | PAT Complete | VNPT 5G PO2 | 5G NR n78 Q-Cell | new | 13.0339 | 109.0123 | 2026-02-20 | 2026-02-26 | 2026-03-06 | 2026-03-22 | 2026-04-07 | 2026-04-19
PHY-0048 | PHY Ward 27 — 5G Expansion n78 | Phu Yen | PAT Complete | VNPT 5G PO2 | 5G NR n78 Q-Cell | new | 12.8274 | 109.2709 | 2026-01-10 | 2026-01-16 | 2026-01-24 | 2026-02-09 | 2026-02-25 | 2026-03-09
PHY-0049 | PHY Ward 05 — 5G Expansion n2 | Phu Yen | PAT Complete | VNPT 5G PO2 | 5G NR n2 Rural | expansion | 13.2297 | 109.3854 | 2026-01-31 | 2026-02-06 | 2026-02-14 | 2026-03-02 | 2026-03-18 | 2026-03-30
PHY-0050 | PHY Ward 23 — 5G NR n2 Rural | Phu Yen | PAT Complete | VNPT 5G PO2 | 5G NR n2 Rural | new | 13.2585 | 109.1865 | 2026-02-11 | 2026-02-17 | 2026-02-25 | 2026-03-13 | 2026-03-29 | 2026-04-10
PHY-0051 | PHY Ward 01 — 5G NR n78 Q-Cell | Phu Yen | PAT Complete | VNPT 5G PO2 | 5G Expansion n2 | expansion | 13.2391 | 109.2565 | 2026-01-09 | 2026-01-15 | 2026-01-23 | 2026-02-08 | 2026-02-24 | 2026-03-08
PHY-0052 | PHY Ward 19 — 5G NR n78 Macro | Phu Yen | On Air Complete | VNPT 5G PO2 | 5G NR n78 Q-Cell | expansion | 13.1006 | 109.1723 | 2026-02-12 | 2026-02-18 | 2026-02-26 | 2026-03-14 | 2026-03-30
PHY-0053 | PHY Ward 37 — 5G Expansion n78 | Phu Yen | PAT Complete | VNPT 5G PO2 | 5G NR n78 Rooftop | new | 13.321 | 109.4609 | 2026-01-30 | 2026-02-05 | 2026-02-13 | 2026-03-01 | 2026-03-17 | 2026-03-29
PHY-0054 | PHY Ward 15 — 5G NR n2 Rural | Phu Yen | PAT Complete | VNPT 5G PO2 | 5G NR n78 Rooftop | expansion | 13.3612 | 109.157 | 2026-02-20 | 2026-02-26 | 2026-03-06 | 2026-03-22 | 2026-04-07 | 2026-04-19
PHY-0055 | PHY Ward 33 — 5G NR n78 Rooftop | Phu Yen | PAT Complete | VNPT 5G PO2 | 5G NR n2 Rural | new | 12.8359 | 109.0441 | 2026-01-01 | 2026-01-07 | 2026-01-15 | 2026-01-31 | 2026-02-16 | 2026-02-28
PHY-0056 | PHY Ward 11 — 5G NR n78 Macro | Phu Yen | PAT Complete | VNPT 5G PO2 | 5G NR n78 Rooftop | new | 13.1229 | 109.1987 | 2026-01-21 | 2026-01-27 | 2026-02-04 | 2026-02-20 | 2026-03-08 | 2026-03-20
PHY-0057 | PHY Ward 29 — 5G NR n78 Q-Cell | Phu Yen | PAT Complete | VNPT 5G PO2 | 5G NR n78 Q-Cell | expansion | 13.1873 | 109.6315 | 2026-01-06 | 2026-01-12 | 2026-01-20 | 2026-02-05 | 2026-02-21 | 2026-03-05
PHY-0058 | PHY Ward 07 — 5G Expansion n2 | Phu Yen | PAT Complete | VNPT 5G PO2 | 5G NR n78 Q-Cell | new | 12.9682 | 109.3705 | 2026-02-16 | 2026-02-22 | 2026-03-02 | 2026-03-18 | 2026-04-03 | 2026-04-15
PHY-0059 | PHY Ward 25 — 5G NR n78 Macro | Phu Yen | PAT Complete | VNPT 5G PO2 | 5G Expansion n2 | expansion | 12.9601 | 109.0589 | 2026-01-21 | 2026-01-27 | 2026-02-04 | 2026-02-20 | 2026-03-08 | 2026-03-20
PHY-0060 | PHY Ward 03 — 5G Expansion n78 | Phu Yen | PAT Complete | VNPT 5G PO2 | 5G NR n78 Q-Cell | new | 13.1768 | 109.0034 | 2026-02-14 | 2026-02-20 | 2026-02-28 | 2026-03-16 | 2026-04-01 | 2026-04-13
PHY-0061 | PHY Ward 21 — 5G NR n2 Rural | Phu Yen | On Air Complete | VNPT 5G PO2 | 5G NR n78 Macro | expansion | 12.9899 | 109.206 | 2026-02-18 | 2026-02-24 | 2026-03-04 | 2026-03-20 | 2026-04-05 | 2026-04-29
PHY-0062 | PHY Ward 39 — 5G NR n78 Rooftop | Phu Yen | PAT Complete | VNPT 5G PO2 | 5G Expansion n2 | new | 12.8834 | 109.4909 | 2026-01-22 | 2026-01-28 | 2026-02-05 | 2026-02-21 | 2026-03-09 | 2026-03-21
PHY-0063 | PHY Ward 17 — 5G Expansion n2 | Phu Yen | PAT Complete | VNPT 5G PO2 | 5G NR n78 Q-Cell | new | 13.0695 | 109.1913 | 2026-02-01 | 2026-02-07 | 2026-02-15 | 2026-03-03 | 2026-03-19 | 2026-03-31
PHY-0064 | PHY Ward 35 — 5G NR n78 Rooftop | Phu Yen | PAT Complete | VNPT 5G PO2 | 5G NR n78 Q-Cell | new | 12.8312 | 109.3341 | 2026-01-30 | 2026-02-05 | 2026-02-13 | 2026-03-01 | 2026-03-17 | 2026-03-29
PHY-0065 | PHY Ward 13 — 5G Expansion n78 | Phu Yen | PAT Complete | VNPT 5G PO2 | 5G Expansion n78 | new | 13.1806 | 109.4729 | 2026-01-14 | 2026-01-20 | 2026-01-28 | 2026-02-13 | 2026-03-01 | 2026-03-13
PHY-0066 | PHY Ward 31 — 5G NR n78 Macro | Phu Yen | PAT Complete | VNPT 5G PO2 | 5G NR n78 Macro | new | 13.3241 | 109.0196 | 2026-01-05 | 2026-01-11 | 2026-01-19 | 2026-02-04 | 2026-02-20 | 2026-03-04
PHY-0067 | PHY Ward 09 — 5G NR n78 Macro | Phu Yen | PAT Complete | VNPT 5G PO2 | 5G NR n78 Macro | new | 12.9317 | 109.2453 | 2026-01-13 | 2026-01-19 | 2026-01-27 | 2026-02-12 | 2026-02-28 | 2026-03-12
PHY-0068 | PHY Ward 27 — 5G Expansion n78 | Phu Yen | PAT Complete | VNPT 5G PO2 | 5G NR n78 Macro | expansion | 12.8217 | 109.5546 | 2026-02-17 | 2026-02-23 | 2026-03-03 | 2026-03-19 | 2026-04-04 | 2026-04-16
PHY-0069 | PHY Ward 05 — 5G Expansion n2 | Phu Yen | PAT Complete | VNPT 5G PO2 | 5G Expansion n78 | new | 13.0677 | 109.3171 | 2026-01-10 | 2026-01-16 | 2026-01-24 | 2026-02-09 | 2026-02-25 | 2026-03-09
PHY-0070 | PHY Ward 23 — 5G Expansion n78 | Phu Yen | PAT Complete | VNPT 5G PO2 | 5G Expansion n2 | expansion | 13.1651 | 109.4186 | 2026-01-01 | 2026-01-07 | 2026-01-15 | 2026-01-31 | 2026-02-16 | 2026-02-28
PHY-0071 | PHY Ward 01 — 5G Expansion n2 | Phu Yen | PAT Complete | VNPT 5G PO2 | 5G NR n2 Rural | new | 13.2941 | 109.3033 | 2026-02-01 | 2026-02-07 | 2026-02-15 | 2026-03-03 | 2026-03-19 | 2026-03-31
PHY-0072 | PHY Ward 19 — 5G NR n78 Q-Cell | Phu Yen | On Air Complete | VNPT 5G PO2 | 5G NR n78 Macro | expansion | 12.8844 | 109.586 | 2026-01-24 | 2026-01-30 | 2026-02-07 | 2026-02-23 | 2026-03-11
PHY-0073 | PHY Ward 37 — 5G NR n78 Rooftop | Phu Yen | PAT Complete | VNPT 5G PO2 | 5G NR n78 Rooftop | new | 13.1768 | 109.5187 | 2026-01-24 | 2026-01-30 | 2026-02-07 | 2026-02-23 | 2026-03-11 | 2026-03-23
PHY-0074 | PHY Ward 15 — 5G Expansion n78 | Phu Yen | PAT Complete | VNPT 5G PO2 | 5G NR n2 Rural | new | 13.1358 | 109.5891 | 2026-02-04 | 2026-02-10 | 2026-02-18 | 2026-03-06 | 2026-03-22 | 2026-04-03
PHY-0075 | PHY Ward 33 — 5G Expansion n2 | Phu Yen | PAT Complete | VNPT 5G PO2 | 5G NR n78 Macro | new | 13.1569 | 109.2674 | 2026-01-24 | 2026-01-30 | 2026-02-07 | 2026-02-23 | 2026-03-11 | 2026-03-23
PHY-0076 | PHY Ward 11 — 5G NR n78 Rooftop | Phu Yen | PAT Complete | VNPT 5G PO2 | 5G Expansion n2 | new | 13.0994 | 109.0673 | 2026-01-23 | 2026-01-29 | 2026-02-06 | 2026-02-22 | 2026-03-10 | 2026-03-22
PHY-0077 | PHY Ward 29 — 5G Expansion n78 | Phu Yen | PAT Complete | VNPT 5G PO2 | 5G NR n78 Rooftop | new | 12.9826 | 109.4177 | 2026-01-13 | 2026-01-19 | 2026-01-27 | 2026-02-12 | 2026-02-28 | 2026-03-12
PHY-0078 | PHY Ward 07 — 5G Expansion n2 | Phu Yen | PAT Complete | VNPT 5G PO2 | 5G NR n78 Q-Cell | expansion | 12.9809 | 109.6208 | 2026-01-21 | 2026-01-27 | 2026-02-04 | 2026-02-20 | 2026-03-08 | 2026-03-20
PHY-0079 | PHY Ward 25 — 5G Expansion n2 | Phu Yen | PAT Complete | VNPT 5G PO2 | 5G NR n2 Rural | new | 13.3708 | 109.4719 | 2026-01-06 | 2026-01-12 | 2026-01-20 | 2026-02-05 | 2026-02-21 | 2026-03-05
PHY-0080 | PHY Ward 03 — 5G NR n78 Rooftop | Phu Yen | PAT Complete | VNPT 5G PO2 | 5G Expansion n78 | new | 13.2583 | 109.1139 | 2026-01-19 | 2026-01-25 | 2026-02-02 | 2026-02-18 | 2026-03-06 | 2026-03-18
PHY-0081 | PHY Ward 21 — 5G Expansion n78 | Phu Yen | PAT Complete | VNPT 5G PO2 | 5G NR n78 Rooftop | new | 12.9767 | 109.2227 | 2026-01-24 | 2026-01-30 | 2026-02-07 | 2026-02-23 | 2026-03-11 | 2026-03-23
PHY-0082 | PHY Ward 39 — 5G NR n78 Macro | Phu Yen | PAT Complete | VNPT 5G PO2 | 5G NR n78 Macro | new | 13.0923 | 109.0281 | 2026-02-15 | 2026-02-21 | 2026-03-01 | 2026-03-17 | 2026-04-02 | 2026-04-14
PHY-0083 | PHY Ward 17 — 5G NR n2 Rural | Phu Yen | PAT Complete | VNPT 5G PO2 | 5G Expansion n2 | expansion | 13.0757 | 109.2739 | 2026-02-12 | 2026-02-18 | 2026-02-26 | 2026-03-14 | 2026-03-30 | 2026-04-11
PHY-0084 | PHY Ward 35 — 5G NR n78 Rooftop | Phu Yen | PAT Complete | VNPT 5G PO2 | 5G NR n78 Q-Cell | expansion | 13.0018 | 109.6071 | 2026-01-31 | 2026-02-06 | 2026-02-14 | 2026-03-02 | 2026-03-18 | 2026-03-30
PHY-0085 | PHY Ward 13 — 5G NR n2 Rural | Phu Yen | PAT Complete | VNPT 5G PO2 | 5G NR n2 Rural | new | 13.12 | 109.3488 | 2026-02-08 | 2026-02-14 | 2026-02-22 | 2026-03-10 | 2026-03-26 | 2026-04-07
PHY-0086 | PHY Ward 31 — 5G NR n78 Rooftop | Phu Yen | PAT Complete | VNPT 5G PO2 | 5G Expansion n2 | expansion | 12.8775 | 109.3119 | 2026-01-02 | 2026-01-08 | 2026-01-16 | 2026-02-01 | 2026-02-17 | 2026-03-01
PHY-0087 | PHY Ward 09 — 5G NR n2 Rural | Phu Yen | PAT Complete | VNPT 5G PO2 | 5G NR n2 Rural | new | 13.2708 | 109.4755 | 2026-01-10 | 2026-01-16 | 2026-01-24 | 2026-02-09 | 2026-02-25 | 2026-03-09
PHY-0088 | PHY Ward 27 — 5G NR n2 Rural | Phu Yen | PAT Complete | VNPT 5G PO2 | 5G Expansion n78 | expansion | 13.226 | 109.257 | 2026-01-22 | 2026-01-28 | 2026-02-05 | 2026-02-21 | 2026-03-09 | 2026-03-21
PHY-0089 | PHY Ward 05 — 5G NR n78 Q-Cell | Phu Yen | On Air Complete | VNPT 5G PO2 | 5G NR n78 Macro | expansion | 12.94 | 109.0246 | 2026-02-21 | 2026-02-27 | 2026-03-07 | 2026-03-23 | 2026-04-08
PHY-0090 | PHY Ward 23 — 5G NR n2 Rural | Phu Yen | PAT Complete | VNPT 5G PO2 | 5G NR n78 Macro | new | 13.0799 | 109.1579 | 2026-02-15 | 2026-02-21 | 2026-03-01 | 2026-03-17 | 2026-04-02 | 2026-04-14
PHY-0091 | PHY Ward 01 — 5G NR n78 Rooftop | Phu Yen | PAT Complete | VNPT 5G PO2 | 5G Expansion n78 | new | 13.0499 | 109.4345 | 2026-02-03 | 2026-02-09 | 2026-02-17 | 2026-03-05 | 2026-03-21 | 2026-04-02
PHY-0092 | PHY Ward 19 — 5G NR n78 Macro | Phu Yen | PAT Complete | VNPT 5G PO2 | 5G NR n78 Macro | new | 13.0589 | 109.3936 | 2026-02-06 | 2026-02-12 | 2026-02-20 | 2026-03-08 | 2026-03-24 | 2026-04-05
PHY-0093 | PHY Ward 37 — 5G Expansion n78 | Phu Yen | PAT Complete | VNPT 5G PO2 | 5G Expansion n2 | new | 13.2462 | 109.6377 | 2026-02-28 | 2026-03-06 | 2026-03-14 | 2026-03-30 | 2026-04-15 | 2026-04-27
PHY-0094 | PHY Ward 15 — 5G NR n78 Macro | Phu Yen | PAT Complete | VNPT 5G PO2 | 5G NR n78 Macro | new | 12.8797 | 109.6186 | 2026-02-11 | 2026-02-17 | 2026-02-25 | 2026-03-13 | 2026-03-29 | 2026-04-10
PHY-0095 | PHY Ward 33 — 5G NR n78 Macro | Phu Yen | PAT Complete | VNPT 5G PO2 | 5G NR n78 Macro | new | 13.034 | 109.2119 | 2026-01-20 | 2026-01-26 | 2026-02-03 | 2026-02-19 | 2026-03-07 | 2026-03-19
PHY-0096 | PHY Ward 11 — 5G NR n78 Macro | Phu Yen | PAT Complete | VNPT 5G PO2 | 5G NR n2 Rural | expansion | 12.9415 | 109.3895 | 2026-02-05 | 2026-02-11 | 2026-02-19 | 2026-03-07 | 2026-03-23 | 2026-04-04
PHY-0097 | PHY Ward 29 — 5G NR n78 Q-Cell | Phu Yen | PAT Complete | VNPT 5G PO2 | 5G NR n2 Rural | expansion | 12.9047 | 109.4745 | 2026-01-20 | 2026-01-26 | 2026-02-03 | 2026-02-19 | 2026-03-07 | 2026-03-19
PHY-0098 | PHY Ward 07 — 5G Expansion n2 | Phu Yen | PAT Complete | VNPT 5G PO2 | 5G Expansion n2 | new | 12.9358 | 109.2289 | 2026-02-02 | 2026-02-08 | 2026-02-16 | 2026-03-04 | 2026-03-20 | 2026-04-01
PHY-0099 | PHY Ward 25 — 5G Expansion n78 | Phu Yen | PAT Complete | VNPT 5G PO2 | 5G NR n2 Rural | expansion | 13.2777 | 109.1205 | 2026-01-17 | 2026-01-23 | 2026-01-31 | 2026-02-16 | 2026-03-04 | 2026-03-16
PHY-0100 | PHY Ward 03 — 5G Expansion n2 | Phu Yen | PAT Complete | VNPT 5G PO2 | 5G NR n2 Rural | expansion | 13.2731 | 109.3481 | 2026-01-21 | 2026-01-27 | 2026-02-04 | 2026-02-20 | 2026-03-08 | 2026-03-20
PHY-0101 | PHY Ward 21 — 5G NR n2 Rural | Phu Yen | PAT Complete | VNPT 5G PO2 | 5G NR n2 Rural | new | 13.1243 | 109.6171 | 2026-01-31 | 2026-02-06 | 2026-02-14 | 2026-03-02 | 2026-03-18 | 2026-03-30
PHY-0102 | PHY Ward 39 — 5G Expansion n2 | Phu Yen | PAT Complete | VNPT 5G PO2 | 5G NR n2 Rural | expansion | 12.8509 | 109.0398 | 2026-01-08 | 2026-01-14 | 2026-01-22 | 2026-02-07 | 2026-02-23 | 2026-03-07
PHY-0103 | PHY Ward 17 — 5G NR n78 Rooftop | Phu Yen | PAT Complete | VNPT 5G PO2 | 5G NR n78 Rooftop | expansion | 12.9706 | 109.0883 | 2026-01-17 | 2026-01-23 | 2026-01-31 | 2026-02-16 | 2026-03-04 | 2026-03-16
PHY-0104 | PHY Ward 35 — 5G Expansion n2 | Phu Yen | PAT Complete | VNPT 5G PO2 | 5G NR n78 Rooftop | new | 12.8842 | 109.002 | 2026-01-28 | 2026-02-03 | 2026-02-11 | 2026-02-27 | 2026-03-15 | 2026-03-27
PHY-0105 | PHY Ward 13 — 5G Expansion n2 | Phu Yen | PAT Complete | VNPT 5G PO2 | 5G NR n78 Q-Cell | new | 12.8893 | 109.2021 | 2026-02-04 | 2026-02-10 | 2026-02-18 | 2026-03-06 | 2026-03-22 | 2026-04-03
PHY-0106 | PHY Ward 31 — 5G NR n78 Macro | Phu Yen | PAT Complete | VNPT 5G PO2 | 5G NR n78 Rooftop | expansion | 13.0196 | 109.5716 | 2026-02-12 | 2026-02-18 | 2026-02-26 | 2026-03-14 | 2026-03-30 | 2026-04-11
PHY-0107 | PHY Ward 09 — 5G NR n78 Q-Cell | Phu Yen | PAT Complete | VNPT 5G PO2 | 5G NR n78 Q-Cell | new | 12.8575 | 109.5004 | 2026-02-21 | 2026-02-27 | 2026-03-07 | 2026-03-23 | 2026-04-08 | 2026-04-20
PHY-0108 | PHY Ward 27 — 5G NR n78 Q-Cell | Phu Yen | PAT Complete | VNPT 5G PO2 | 5G NR n78 Rooftop | expansion | 13.3464 | 109.1134 | 2026-02-06 | 2026-02-12 | 2026-02-20 | 2026-03-08 | 2026-03-24 | 2026-04-05
PHY-0109 | PHY Ward 05 — 5G NR n2 Rural | Phu Yen | PAT Complete | VNPT 5G PO2 | 5G Expansion n2 | expansion | 13.185 | 109.3854 | 2026-01-19 | 2026-01-25 | 2026-02-02 | 2026-02-18 | 2026-03-06 | 2026-03-18
PHY-0110 | PHY Ward 23 — 5G NR n78 Macro | Phu Yen | PAT Complete | VNPT 5G PO2 | 5G Expansion n78 | new | 12.9541 | 109.0518 | 2026-01-19 | 2026-01-25 | 2026-02-02 | 2026-02-18 | 2026-03-06 | 2026-03-18
PHY-0111 | PHY Ward 01 — 5G NR n78 Macro | Phu Yen | PAT Complete | VNPT 5G PO2 | 5G Expansion n2 | new | 13.0922 | 109.4758 | 2026-01-23 | 2026-01-29 | 2026-02-06 | 2026-02-22 | 2026-03-10 | 2026-03-22
PHY-0112 | PHY Ward 19 — 5G NR n78 Q-Cell | Phu Yen | On Air Complete | VNPT 5G PO2 | 5G NR n2 Rural | expansion | 12.9269 | 109.2765 | 2026-01-27 | 2026-02-02 | 2026-02-10 | 2026-02-26 | 2026-03-14
PHY-0113 | PHY Ward 37 — 5G NR n78 Q-Cell | Phu Yen | PAT Complete | VNPT 5G PO2 | 5G NR n78 Rooftop | new | 13.2719 | 109.2887 | 2026-01-15 | 2026-01-21 | 2026-01-29 | 2026-02-14 | 2026-03-02 | 2026-03-14
PHY-0114 | PHY Ward 15 — 5G NR n78 Macro | Phu Yen | PAT Complete | VNPT 5G PO2 | 5G NR n78 Q-Cell | new | 12.903 | 109.587 | 2026-01-22 | 2026-01-28 | 2026-02-05 | 2026-02-21 | 2026-03-09 | 2026-03-21
PHY-0115 | PHY Ward 33 — 5G NR n78 Q-Cell | Phu Yen | PAT Complete | VNPT 5G PO2 | 5G NR n2 Rural | new | 13.109 | 109.3908 | 2026-02-20 | 2026-02-26 | 2026-03-06 | 2026-03-22 | 2026-04-07 | 2026-04-19
PHY-0116 | PHY Ward 11 — 5G NR n2 Rural | Phu Yen | PAT Complete | VNPT 5G PO2 | 5G Expansion n2 | new | 13.266 | 109.0018 | 2026-02-21 | 2026-02-27 | 2026-03-07 | 2026-03-23 | 2026-04-08 | 2026-04-20
PHY-0117 | PHY Ward 29 — 5G NR n78 Q-Cell | Phu Yen | PAT Complete | VNPT 5G PO2 | 5G NR n78 Macro | expansion | 13.0447 | 109.173 | 2026-02-16 | 2026-02-22 | 2026-03-02 | 2026-03-18 | 2026-04-03 | 2026-04-15
PHY-0118 | PHY Ward 07 — 5G NR n2 Rural | Phu Yen | PAT Complete | VNPT 5G PO2 | 5G Expansion n78 | expansion | 13.1857 | 109.3882 | 2026-02-01 | 2026-02-07 | 2026-02-15 | 2026-03-03 | 2026-03-19 | 2026-03-31
PHY-0119 | PHY Ward 25 — 5G Expansion n78 | Phu Yen | PAT Complete | VNPT 5G PO2 | 5G NR n78 Macro | new | 12.9347 | 109.455 | 2026-01-04 | 2026-01-10 | 2026-01-18 | 2026-02-03 | 2026-02-19 | 2026-03-03

## ISSUES
week | raised | closed | open
W01 | 3 | 2 | 1
W02 | 3 | 2 | 1
W03 | 3 | 2 | 1
W04 | 3 | 2 | 1
W05 | 3 | 2 | 1
W06 | 3 | 2 | 1
W07 | 2 | 1 | 1
W08 | 3 | 1 | 2
W09 | 6 | 2 | 4
W10 | 6 | 4 | 2
W11 | 3 | 3 | 0
W12 | 4 | 1 | 3
W13 | 5 | 4 | 1
W14 | 3 | 2 | 1
W15 | 2 | 2 | 0
W16 | 2 | 2 | 0
W17 | 6 | 3 | 3
W18 | 5 | 2 | 3

## RESOURCES
week | project | install | ssv | onair | optim | total | total_plan
W01 | VNPT 5G PO2 | 13 | 4 | 4 | 1 | 22 | 27
W02 | VNPT 5G PO2 | 14 | 4 | 2 | 1 | 21 | 25
W03 | VNPT 5G PO2 | 17 | 3 | 3 | 1 | 24 | 30
W04 | VNPT 5G PO2 | 18 | 4 | 4 | 1 | 27 | 35
W05 | VNPT 5G PO2 | 25 | 4 | 6 | 2 | 37 | 46
W06 | VNPT 5G PO2 | 26 | 6 | 6 | 2 | 40 | 47
W07 | VNPT 5G PO2 | 28 | 6 | 7 | 2 | 43 | 52
W08 | VNPT 5G PO2 | 31 | 6 | 7 | 3 | 47 | 57
W09 | VNPT 5G PO2 | 35 | 7 | 8 | 3 | 53 | 63
W10 | VNPT 5G PO2 | 35 | 5 | 8 | 3 | 51 | 64
W11 | VNPT 5G PO2 | 33 | 5 | 6 | 3 | 47 | 58
W12 | VNPT 5G PO2 | 29 | 6 | 6 | 2 | 43 | 54
W13 | VNPT 5G PO2 | 30 | 5 | 7 | 3 | 45 | 54
W14 | VNPT 5G PO2 | 23 | 5 | 6 | 2 | 36 | 44
W15 | VNPT 5G PO2 | 23 | 5 | 5 | 2 | 35 | 43
W16 | VNPT 5G PO2 | 17 | 2 | 5 | 1 | 25 | 33
W17 | VNPT 5G PO2 | 12 | 2 | 2 | 1 | 17 | 21
W18 | VNPT 5G PO2 | 11 | 3 | 3 | 1 | 18 | 21

## RISKS
risk_name | priority | description | owner | resolve_date | current_status | next_steps | project
Q1 RRH Equipment Logistics | High | The n78 RRH shipment missed port schedule windows, impacting the March installation sequence. | Le Thu Ha | 2026-04-28 | Partial units were reallocated from the Singapore warehouse; around 70% of demand is now in the Central warehouse. | Confirm air-freight for the final 40 RRHs and update the Week 17 MOS plan. | VNPT 5G PO2
Power and Shelter Readiness (Expansion) | Medium | Several expansion sites require power-capacity upgrades before On Air. | Pham Quoc Anh | 2026-05-05 | Power survey is 89% complete; 11 sites are waiting for the electrical cabinet fabrication contract. | Accelerate second-batch PDU procurement and lock installation slots for Weeks 16-17. | VNPT 5G PO2
Spectrum Licensing and Local Permits | Medium | Some expansion sites in Quang Nam are delayed by local permits for auxiliary pole construction. | Tran Hoai Nam | 2026-05-10 | The 12-site list is under review; 6 sites have received supplemental approvals. | Coordinate with the provincial telecom authority and prioritize fast-track escalation in Week 18. | VNPT 5G PO2

## VNPT 5G PO2_ROLLING_PLAN
week | week_end_date | tss_plan | tssr_plan | rfi_plan | install_plan | onair_plan | pat_plan | pac_plan | ssv_plan
W01 | 2026-06-01 | 45 | 0 | 0 | 0 | 0 | 0 | 0 | 0
W02 | 2026-06-08 | 113 | 52 | 0 | 0 | 0 | 0 | 0 | 0
W03 | 2026-06-15 | 178 | 120 | 45 | 0 | 0 | 0 | 0 | 0
W04 | 2026-06-22 | 267 | 190 | 113 | 0 | 0 | 0 | 0 | 0
W05 | 2026-06-29 | 343 | 277 | 178 | 21 | 0 | 0 | 0 | 0
W06 | 2026-07-06 | 421 | 356 | 267 | 94 | 0 | 0 | 0 | 0
W07 | 2026-07-13 | 504 | 431 | 343 | 163 | 0 | 0 | 0 | 0
W08 | 2026-07-20 | 587 | 517 | 421 | 241 | 76 | 0 | 0 | 0
W09 | 2026-07-27 | 601 | 589 | 504 | 315 | 144 | 20 | 0 | 0
W10 | 2026-08-03 | 601 | 601 | 587 | 396 | 215 | 92 | 0 | 0
W11 | 2026-08-10 | 601 | 601 | 601 | 473 | 300 | 157 | 0 | 0
W12 | 2026-08-17 | 601 | 601 | 601 | 565 | 378 | 231 | 0 | 0
W13 | 2026-08-24 | 601 | 601 | 601 | 591 | 452 | 299 | 0 | 0
W14 | 2026-08-31 | 601 | 601 | 601 | 601 | 539 | 374 | 0 | 0
W15 | 2026-09-07 | 601 | 601 | 601 | 601 | 591 | 446 | 0 | 0
W16 | 2026-09-14 | 601 | 601 | 601 | 601 | 601 | 535 | 0 | 0
W17 | 2026-09-21 | 601 | 601 | 601 | 601 | 601 | 558 | 0 | 0
W18 | 2026-09-28 | 601 | 601 | 601 | 601 | 601 | 576 | 0 | 0